## SIT 3 Listing & Schedule
SIT 3 End to End Scenarios | SIT 3 Scheduled Week | 150 - Treasurer
Inventory Management Cycle | Week 4: 1/24 - 1/28
Pcard End to End Process | Week 4: 1/24 - 1/28
Project Processing (RQ, PO, Contract, INV) | Week 4: 1/24 - 1/28
XM Pcard NO Cash Advance | Week 4: 1/24 - 1/28
XM Pcard WITH Cash Advance | Week 4: 1/24 - 1/28
Payroll End to End | Week 4: 1/24 - 1/28
Fixed Asset Acquire to Retire | Week 5: 1/31 - 2/4
Statewide Contract Procure to Pay | Week 5: 1/31 - 2/4
GHR Shell | Week 5: 1/31 - 2/4
Project 1.1 Project Setup and Maintanance | Week 5: 1/31 - 2/4
Project 1.2 Project Processing Master (P&G only) | Week 5: 1/31 - 2/4
AR Credit Monitoring | Week 6: 2/7 - 2/11
Asset Management Maintenance | Week 6: 2/7 - 2/11
Service Contract Interagency Billing | Week 6: 2/7 - 2/11
Project 1.3 Reports and Inquiry Master | Week 6: 2/7 - 2/11 & Week 7: 2/14 - 2/18
Cash Ledger Payment | Week 7: 2/14 - 2/18 | X
Interagency Billing to Settlement | Week 7: 2/14 - 2/18
Non-State Billing | Week 7: 2/14 - 2/18
Procure to Pay Vendor Management Voids | Week 7: 2/14 - 2/18
Vendor Refunds | Week 7: 2/14 - 2/18 | X
Cash Management Deposit to Revenue | Week 8: 2/21 - 2/25 | X
Custodial Accounts Setup | Week 8: 2/21 - 2/25 | X
Global Ledger Entries and Analysis | Week 8: 2/21 - 2/25 | X
Punchout Request to Payment | Week 8: 2/21 - 2/25
Tax Refunds | Week 8: 2/21 - 2/25 | X
Allocations | Week 9: 2/28 - 3/4
Budget | Week 9: 2/28 - 3/4
Custodial Accounts Transaction Processing | Week 9: 2/28 - 3/4 | X
Month End/Year End | Week 9: 2/28 - 3/4 | X
Define and Generate Recurring Invoices | Week 9: 2/28 - 3/4
Chart of Accounts Maintenance | Week 10: 3/7 - 3/11 | X
3rd Party Allocations | TBD

## Instructions
Luma System Integration Testing 3 (SIT 3) Instructions
Agency Functional Testing Dates | January 24 - March 11, 2022 Testing Schedule: Monday -Thursday 8:45 -11 am and 1:45 - 4:00 pm, Friday 9:00 - 11:00 am
Agency Testers Roles and Responsibilities | 1. Execute test scripts per SIT 3 schedule. 2. Review actual results against expected results. 3. Log defects as needed. 4. Retest failed test results to resolve defects. 5. Launch integrations during test cycle per schedule.
Testing Packet | 1. Test Scenario Excel File: Cover Page, Instruction Tab, Scenario Listing, Tab with each steps script detailed instruction to execute the script. 2. Data Sheets. 3. Email Template to use to report your testing results.
Testing Steps | 1. If you are the first step in the scenario, you may begin execution according to the the Date and Time in the Testing packet. If you are not on step 1, please wait for the step before you to complete their script and you receive communication to begin. 2. Execute assigned script(s) using the testing script and data sheet that was provided to you. 3. Sending Testing results via email using to the Test Management Team. (attached email sample) 4. Communicate to the next tester they can begin their script. (Slack or Email works)
What should you do if there are issues or you need assistance while testing? | 1. The Test Management Team will host an all-day SIT 3 Testing Support Hotline (WebEx Meeting). 2. Attendance is optional for SIT testers and testers should only join if they have questions or issues regarding SIT testing. 3. Testers should have an invite on their calendar that includes the WebEx Link.
How to submit a SIT 3 Testing Defect using ServiceNow: | 1. Visit https://auth.sco.idaho.gov/ in your web browser. Google Chrome and Microsoft Edge are recommended. 2. Enter your State ID number as the username and your password. Click the Sign In button. 3. You will be presented with a second page for Multi-Factor Authentication. Select an option and acknowledge the push or call, or enter a passcode from your Duo app. 4. You will see several buttons on your Enterprise Dashboard. One of these will be labeled Service Desk. This button will take you to the Service Portal. 5. There are four main buttons across the center of the page. Click Service Requests to be taken to the service menu. 7. Locate and select LUMA SIT3 Testing Issue from the options listed. 6. Select the SCO IT Services category from the list on the left side of the page. 7. Fill out form with Primary Contact, Short Description, Description, Category, Scenario Name, Script ID, add attachments/screenshots and submit the ticket.
What to do if there is a system outage? | 1. Please join the Testing Support Hotline if you run into any issues with the system and notify the meeting moderator of the issue. 2. If there is a system outage, the Test Management Team will work with the Communications team to notify Agency Testers.

## Email Submission Template
Double click on Icon Below to Outlook Email Template

## Cash Ledger Payment
SIT 3 Scenario - Cash Ledger Payment
Agency:
SIT Week - Week 7 - 2/14 -2/18
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Enter Cash Payment | Cash Payment Entry.xlsx | 12075 | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Angela Bonaminio | angela.bonaminio@sto.idaho.gov | Rotary/Site Draft, L Warrants |  | 2022-02-14 | 8:45 - 10 AM
1A | Record Cash Payment |  | 12525 | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Angela Bonaminio | angela.bonaminio@sto.idaho.gov |  |  | 2022-02-14 | 8:45 - 10 AM
2 | Approve Cash Payment | Cash Approve Cash Payment.xlsx | 12076 | Cash Manager | Manage all cash transactions. Review and update cash management policy as needed. | Assigned Agency | Angela Bonaminio | angela.bonaminio@sto.idaho.gov |  |  | 2022-02-14 | 10 - 11:30 AM
3 | Cash Requirements | Cash Requirements.xlsx | 12077 | Payables Payment Processor | Perform Cash Requirements, Schedule Payments, Complete Payment Cycle | Assigned Agency | John Faltin | john.faltin@sto.idaho.gov |  | MF-070-100 Process Invoice Payments | 2022-02-14 | 1 - 2:30 PM
4 | Review Check in Cash | Cash Review Check in Cash Management.xlsx | 12078 | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Angela Bonaminio | angela.bonaminio@sto.idaho.gov | Redeem or Void then Review again |  | 2022-02-14 | 2:30 - 4 PM
5 | Journalize Distributions | Cash Journalize Cash Transaction.xlsx | 12079 | Cash Manager | Manage all cash transactions. Review and update cash management policy as needed. | Assigned Agency | Angela Bonaminio | angela.bonaminio@sto.idaho.gov |  |  | 2022-02-15 | 8:45 - 10 AM
6 | Verify Results in Global Ledger Account Analysis |  | 12082 | Staff Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Laura Steffler | laura.steffler@sto.idaho.gov |  |  | 2022-02-15 | 10 - 11:30 AM
7 | Optional Void Cash Payment for Status Updates | Cash Void Cash Payment.xlsx | 12080 | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Angela Bonaminio | angela.bonaminio@sto.idaho.gov |  |  | 2022-02-15 | 1 - 2:30 PM
8 | Optional Void Cash Payment: Payment Void Stop Pay Update | 12161 | 12161 | Payables Payment Processor | Perform Cash Requirements, Schedule Payments, Complete Payment Cycle | Assigned Agency | John Faltin | john.faltin@sto.idaho.gov |  |  | 2022-02-15 | 1 - 2:30 PM
9 | Optional Redeem Warrant for Status Updates | Cash Redeem Warrant.xlsx | 12081 | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Angela Bonaminio | angela.bonaminio@sto.idaho.gov |  |  | 2022-02-15 | 2:30 - 4 PM
Note on I4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard
Note on K5: Glenda Smith: Cash BPR's are not correct, do not reference.

## Vendor Refund
SIT 3 Scenario - Vendor Refund
Agency:
SIT 3 Week - Week 7 - 2/14 - 2/18
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Invoice Entry - Non-PO | 12444 | 12444 | Payables Invoice Processor |  |  | John Faltin | john.faltin@sto.idaho.gov |  | MF-070-060 Enter Non-PO Invoice | 2022-02-15 | 8:45-9:30 AM
2 | Invoice Approver | 12445 | 12445 | Approver |  |  | Laura Steffler, Angela Bonaminio, Julie Ellsworth | laura.steffler@sto.idaho.gov, Angela.bonaminio@sto.idaho.gov, julie.ellsworth@sto.idaho.gov |  | MF-070-056 Invoice Approval Process | 2022-02-15 | 9:30-10AM
3 | Cash Requirements | 12442 | 12442 | Payables Manager |  |  | John Faltin | john.faltin@sto.idaho.gov |  | MF-070-100 Process Invoice Payments | 2022-02-15 | 10-10:30 AM
4 | Journalize | 12443 | 12443 | Payables Manager |  |  | John Faltin | john.faltin@sto.idaho.gov |  | MF-070-110 Journalize AP Distributions | 2022-02-15 | 10:30 - 11 AM
5 | Create Cash Receipts |  | TBD | Cash Accountant |  |  | Angela Bonaminio | angela.bonaminio@sto.idaho.gov |  |  | 2022-02-15 | 1-1:30PM
6 | Approve Cash Receipt |  | TBD | Approver |  |  | Angela Bonaminio | angela.bonaminio@sto.idaho.gov |  |  | 2022-02-15 | 1:30-2PM
7 | Cash Receipt Final Release |  | TBD | Cash Manager |  |  | Angela Bonaminio | angela.bonaminio@sto.idaho.gov |  |  | 2022-02-15 | 2-2:30PM
8 | Jornalize Cash Transactions |  | TBD | Staff Accountant |  |  | Laura Steffler | laura.steffler@sto.idaho.gov |  |  | 2022-02-15 | 2:30-3PM
9 | Post GL Journals |  | TBD | Staff Accountant |  |  | Laura Steffler | laura.steffler@sto.idaho.gov |  |  | 2022-02-15 | 3 - 3:30 PM
10 | Adjust Reportable Income | 11837 | 12047 | Payables Manager | Void & cancel payments. Reissue & mail warrants. Process period close. | Assigned Agency | John Faltin | john.faltin@sto.idaho.gov |  | MF-070-020 Maintain Invoice | 2022-02-15 | 3:30 - 4 PM
Note on J5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard

## Cash Managem Deposit to Revenue
SIT 3 Scenario - Deposit to Revenue
Agency:
SIT Week - Week 8 - 2/21/ - 2/25
Sequence | Script ID | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 BPR PROCESSES | Execution date | Window to Complete Script
1 | Cash Fund Balance - Before Processing Transactions | TBD | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Angela Bonaminio | angela.bonaminio@sto.idaho.gov |  |  | 2022-02-22 | 8:45-9:30 AM
2 | Create Cash Receipt | TBD | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Angela Bonaminio | angela.bonaminio@sto.idaho.gov |  |  | 2022-02-22 | 9:30-10AM
3 | Approve Cash Receipt (Approve Cash Transactions in InBasket) | TBD | Cash Manager | Manage all cash transactions. Review and update cash management policy as needed. | Assigned Agency | Angela Bonaminio | angela.bonaminio@sto.idaho.gov |  |  | 2022-02-22 | 10-11AM
4 | Cash Receipt Final Release (Approve Cash Transactions in InBasket) | TBD | Cash Manager | Manage all cash transactions. Review and update cash management policy as needed. | 150 | Angela Bonaminio | angela.bonaminio@sto.idaho.gov |  |  | 2022-02-22 | 1-1:30PM
5 | Process NSF | TBD | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Angela Bonaminio | angela.bonaminio@sto.idaho.gov |  |  | 2022-02-22 | 1:30-2PM
6 | Approve NSF (Approve Cash Transactions in InBasket) | TBD | Cash Manager | Manage all cash transactions. Review and update cash management policy as needed. | Assigned Agency | Angela Bonaminio | angela.bonaminio@sto.idaho.gov |  |  | 2022-02-22 | 2-2:30PM
7 | NSF Final Release (Approve Cash Transactions in InBasket) | TBD | Cash Manager | Manage all cash transactions. Review and update cash management policy as needed. | 150 | Angela Bonaminio | angela.bonaminio@sto.idaho.gov |  |  | 2022-02-22 | 2:30-3PM
8 | Reclass From Suspense: No Customer (Cash Receipt Transfer) | TBD | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Angela Bonaminio | angela.bonaminio@sto.idaho.gov |  |  | 2022-02-22 | 3-3:30PM
9 | Reclass From Suspense Customer (Go to AR Scenario) | TBD | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Angela Bonaminio | angela.bonaminio@sto.idaho.gov | Process under development. |  | 2022-02-23 | 8:45-9:30 AM
10 | Operating Transfer (Cash Ledger Transaction Transfer) | TBD | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Angela Bonaminio | angela.bonaminio@sto.idaho.gov |  |  | 2022-02-23 | 9:30-10AM
11 | Statutory Transfer (Cash Ledger Transaction Transfer) | TBD | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Angela Bonaminio | angela.bonaminio@sto.idaho.gov |  |  | 2022-02-23 | 10-11AM
12 | Approve Cash Transfer (Approve Cash Transactions in InBasket) | TBD | Cash Manager | Manage all cash transactions. Review and update cash management policy as needed. | Assigned Agency | Angela Bonaminio | angela.bonaminio@sto.idaho.gov |  |  | 2022-02-23 | 1-1:30PM
13 | Cash Fund Balance - After Processing Transactions | TBD | Cash Manager | Manage all cash transactions. Review and update cash management policy as needed. | Assigned Agency | Angela Bonaminio | angela.bonaminio@sto.idaho.gov |  |  | 2022-02-23 | 1:30-2PM
14 | Journalize Cash Transactions | TBD | Cash Manager | Manage all cash transactions. Review and update cash management policy as needed. | Assigned Agency | Angela Bonaminio | angela.bonaminio@sto.idaho.gov |  |  | 2022-02-23 | 2-2:30PM
15 | Post GL Journals | TBD | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate, and update allocations. | Assigned Agency | Laura Steffler | laura.steffler@sto.idaho.gov | Check for autopost |  | 2022-02-23 | 2:30-3PM
16 | Review Global Ledger for Transactions Processed | TBD | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate, and update allocations. | Assigned Agency | Laura Steffler | laura.steffler@sto.idaho.gov |  |  | 2022-02-23 | 3-3:30PM
Note on I5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard

## Custodial Account Set Up
SIT 3 Scenario - Custodial Account Set Up
Agency:
SIT Week - Week 8 - 2/21/ - 2/25
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Custodial Account Setup | TBD | 12071 | Custodial Account Manager | Monitor financial structure and Chart of Account dimensions for their Agency and recommendations for updates. Manage all financial processes. | Assigned Agency | Laura Steffler | laura.steffler@sto.idaho.gov |  |  | 2022-02-22 | 8:45 - 10AM
2 | CAM Structure Setup | Refer to Upload Template | 12072 | Custodial Account Manager | 0 | Assigned Agency | Laura Steffler | laura.steffler@sto.idaho.gov |  |  | 2022-02-22 | 10 - 11:30 AM
3 | Custodial Account Hierarchy Setup | Refer to Upload Template | 12073 | Custodial Account Manager | Monitor financial structure and Chart of Account dimensions for their Agency and recommendations for updates. Manage all financial processes. | Assigned Agency | Laura Steffler | laura.steffler@sto.idaho.gov |  |  | 2022-02-22 | 1 - 2:30 PM
4 | Custodial Account Record Setup | Refer to Upload Template | 12074 | Custodial Account Manager | 0 | Assigned Agency | Laura Steffler | laura.steffler@sto.idaho.gov |  |  | 2022-02-22 | 2:30 -4 PM
Note on J5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard

## Tax Refunds
SIT 3 Scenario - Tax Refunds
Agency:352
SIT Week - Week 8 - 2/21 - 2/25
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | Level 3 BPR | Execution date | Window to Complete Script
1 | IFS201 - Tax Refund Interface | 8801 | 12491 | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | 352 | Angela Bonaminio | angela.bonaminio@sto.idaho.gov |  |  | 2022-02-22 | 8:45-9:30 AM
2 | Cash Requirements | 11442 | 12494 | Payables Payment Processor | Perform Cash Requirements, Schedule Payments, Complete Payment Cycle | 352 | John Faltin | john.faltin@sto.idaho.gov |  | MF-070-100 Process Invoice Payments | 2022-02-22 | 9:30-10AM
3 | IFS517 ACH File | 10936 | 12492 | TBD | Who is generating the single statewide ACH file? | 140 |  |  |  |  | 2022-02-22 | 10-11AM
4 | IFS513 - Review IFS517 Tax Refund Data in ACH File | 11199 | 12493 | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | 352 | Angela Bonaminio | angela.bonaminio@sto.idaho.gov |  |  | 2022-02-22 | 1-1:30PM
5 | IFS342 - Warrant numbers to GenTax | 8333 | 12488 | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | 352 | Angela Bonaminio | angela.bonaminio@sto.idaho.gov |  |  | 2022-02-23 | LUMA Overnight
6 | IFS373 - Redemtion File | 8204 | 12487 | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | 150 | Angela Bonaminio | angela.bonaminio@sto.idaho.gov |  |  | 2022-02-23 | 8:45 AM - 4 PM
7 | IFS514 - Warrant Status Updates to GenTAx | 8417 | 12489 | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | 352 | Angela Bonaminio | angela.bonaminio@sto.idaho.gov |  |  | 2022-02-24 | LUMA Overnight
8 | Run GenTax Job Warrant Status Update | n/a | 12497 | GenTax User |  | 352 |  |  |  |  | 2022-02-24 | 8:45-9:30 AM
9 | Cancel Warrants in GenTax Manually | n/a | 12498 | GenTax User |  | 352 |  |  |  |  | 2022-02-24 | 9:30-10AM
10 | Run GenTax Job, Send File for IFS515 | n/a | 12499 | GenTax User |  | 352 |  |  |  |  | 2022-02-24 | 10-11AM
11 | IFS515 - GenTax Warrant Cancelations | 8636 | 12490 | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | 352 | Angela Bonaminio | angela.bonaminio@sto.idaho.gov |  |  | 2022-02-24 | 1-1:30PM
12 | Manually Void Tax Refund in LUMA | Cash Void Cash Payment.xlsx (in ALM?) | TBD | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | 352 | Angela Bonaminio | angela.bonaminio@sto.idaho.gov |  |  | 2022-02-24 | 1:30 - 4 PM
13 | IFS514 - Warrant Status Updates to GenTAx | 8417 | 12505 | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | 352 | Angela Bonaminio | angela.bonaminio@sto.idaho.gov |  |  | 2022-02-25 | LUMA Overnight
14 | Run GenTax Job Warrant Status Update | n/a | 12500 | GenTax User |  | 352 |  |  |  |  | 2022-02-25 | 8:45-9:30 AM
15 | Journalize Cash Transactions | 12079 | 12485 | Cash Manager | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | 352 | Angela Bonaminio | angela.bonaminio@sto.idaho.gov |  |  | 2022-02-25 | 9:30-10AM
16 | Post Journalized Transactions | GL Post Journal Entries.xlsx (in ALM?) | TBD | Staff Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | 352 | Laura Steffler | laura.steffler@sto.idaho.gov |  |  | 2022-02-25 | 10-11AM
17 | Review GL for results of Cash transactions | 12082 | 12486 | Staff Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | 352 | Laura Steffler | laura.steffler@sto.idaho.gov |  |  | 2022-02-25 | 1-1:30PM
Note on I4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard

## Custodial Accounts
SIT 3 Scenario - Budget Reporting and Trust Accounting
Agency:
SIT 3 Week - Week 9 - 2/28 - 3/4
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Set up Custodial Accounts |  | TBD | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate, and update allocations. | Assigned Agency | Laura Steffler | laura.steffler@sto.idaho.gov | Associate with project | PR-050-070 | 2022-02-28 | 8:45-9:30 AM
2 | Enter cash receipt for the Custodial Account |  | TBD | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Angela Bonaminio | angela.bonaminio@sto.idaho.gov | Deny Requisition - add note - need more information Approve Requisition | MF-260-070 Enter Cash Receipts | 2022-02-28 | 9:30-10AM
2 | Approve Cash Receipt |  | TBD | Cash Manager | Manage all cash transactions. Review and update cash management policy as needed. | Assigned Agency | Angela Bonaminio | angela.bonaminio@sto.idaho.gov |  | MF-260-070 Enter Cash Receipts | 2022-02-28 | 10-11AM
3 | Final Approval of Cash Receipt |  | TBD | Cash Manager | Manage all cash transactions. Review and update cash management policy as needed. | STO | Angela Bonaminio | angela.bonaminio@sto.idaho.gov |  | MF-260-070 Enter Cash Receipts | 2022-02-28 | 1-1:30PM
4 | Journalize Cash Management |  | TBD | Cash Manager | Manage all cash transactions. Review and update cash management policy as needed. | Assigned Agency | Angela Bonaminio | angela.bonaminio@sto.idaho.gov |  | MF-260-090 Post to General Ledger | 2022-02-28 | 1:30-2PM
5 | View Trust Balance report in Birst |  | TBD | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate, and update allocations. | Assigned Agency | Laura Steffler | laura.steffler@sto.idaho.gov |  |  | 2022-02-28 | 2-2:30PM
6 | Enter Invoice for trust account | 11443 | TBD | Payables Invoice Processor | Process interface and XM files. Match payables invoices, and vendor list. Process payables payments. Generate 1099. | Assigned Agency | John Faltin | john.faltin@sto.idaho.gov |  | MF-070-060 Enter a Non-PO invoice | 2022-02-28 | 2:30-3PM
7 | Enter Comments & Attachments | 11445 | TBD | Payables Invoice Processor |  |  | John Faltin | john.faltin@sto.idaho.gov |  | MF-070-060 Enter a Non-PO invoice | 2022-02-28 | 3-3:30PM
8 | Approve invoice | 11444 | TBD | Approver | Approve transactions such as requisitions, purchase orders, solicitations, and journal entries. | Assigned Agency | Laura Steffler, Julie Ellsworth, or Angela Bonaminio | laura.steffler@sto.idaho.gov, Angela.bonaminio@sto.idaho.gov, julie.ellsworth@sto.idaho.gov |  | MF-070-080 Invoice Approval Process | 2022-03-02 | 8:45-9:30 AM
9 | Run Cash Requirements | 11442 | TBD | Payables Manager | Void & cancel payments. Reissue & mail warrants. Process period close. | Assigned Agency | John Faltin | john.faltin@sto.idaho.gov |  | MF-070-100 Process Invoice Payments | 2022-03-02 | 9:30-10AM
10 | Journalize Payables | 11440 | TBD | Payables Manager | Void & cancel payments. Reissue & mail warrants. Process period close. | Assigned Agency | John Faltin | john.faltin@sto.idaho.gov |  | MF-070-110 Journalize Distributions | 2022-03-02 | 10-11AM
11 | View Trust Balance Report in Birst |  | TBD | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate, and update allocations. | Assigned Agency | Laura Steffler | laura.steffler@sto.idaho.gov | Receive less/more than ordered |  | 2022-03-02 | 1-1:30PM
12 | Run Average Daily Balance Report |  | TBD | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate, and update allocations. | Assigned Agency | Laura Steffler | laura.steffler@sto.idaho.gov | Inspection Failed, Vendor Return |  | 2022-03-02 | 1:30-2PM
Note on J5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard

## Month End
NOTE: The Month End Close Process Scenario testing will be coordinated with the assigned Agencies and executed one time during UAT.
SIT 3 Scenario - Month End Close Process
Agency:
SIT Week - (dates)
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Close Purchasing: Resolve all Buyer & Invoice Messages | Refer to Upload Template | 12140 | Purchasing Manager | Review requisitions & sourcing event requests. Review purchase requirement. Assign buyers and approve method of purchase. | Assigned Agency | Laura Steffler | laura.steffler@sto.idaho.gov |  | PR-050-090 Determine Inventory Strategy and Approach | 2022-03-01 | All Day Testing
2 | Close Purchasing: Received Not Invoiced Report | 3005 |  | Purchasing Manager | Review requisitions & sourcing event requests. Review purchase requirement. Assign buyers and approve method of purchase. | Assigned Agency | Laura Steffler | laura.steffler@sto.idaho.gov |  | PR-050-090 Determine Inventory Strategy and Approach | 2022-03-01 | All Day Testing
3 | Close Purchasing: Matched, Not Received Report | 3003 |  | Purchasing Manager | Review requisitions & sourcing event requests. Review purchase requirement. Assign buyers and approve method of purchase. | Assigned Agency | Laura Steffler | laura.steffler@sto.idaho.gov |  | PR-050-090 Determine Inventory Strategy and Approach | 2022-03-01 | All Day Testing
4 | Close Purchasing: Invoiced, Not Received Closing | 3002 |  | Purchasing Manager | Review requisitions & sourcing event requests. Review purchase requirement. Assign buyers and approve method of purchase. | Assigned Agency | Laura Steffler | laura.steffler@sto.idaho.gov |  | PR-050-090 Determine Inventory Strategy and Approach | 2022-03-01 | All Day Testing
5 | Close Purchasing: Close Purchase Order Header | 3001 |  | Purchasing Manager | Review requisitions & sourcing event requests. Review purchase requirement. Assign buyers and approve method of purchase. | LUMA | Laura Steffler | laura.steffler@sto.idaho.gov |  | MF-030-050 Close Purchase Order | 2022-03-01 | All Day Testing
6 | Close Purchasing: Purchase System Close | 3004 |  | Purchasing Manager | Review requisitions & sourcing event requests. Review purchase requirement. Assign buyers and approve method of purchase. | LUMA | Laura Steffler | laura.steffler@sto.idaho.gov |  | MF-030-050 Close Purchase Order | 2022-03-01 | All Day Testing
7 | Close Payables | 11441 - just the close steps not all the reports leading up to this |  | Payables Manager | Void & cancel payments. Reissue & mail warrants. Process period close. | Assigned Agency | John Faltin | john.faltin@sto.idaho.gov |  | MF-070-120 Perform AP Period End Close / MF-030-070 Close Payables | 2022-03-01 | All Day Testing
8 | Close Biling - Recurring Invoice Creation | Billing > RunProcesses > Create RecurringInvoices |  | Billing Manager | Create and maintain bills for Accounts Receivable. | Assigned Agency | Angela Bonaminio | angela.bonaminio@sto.idaho.gov |  | MF-030-080 Close Billing | 2022-03-01 | All Day Testing
9 | Close Billing - Invoice Batch Release | Billing Manager > Processing > Create Billing Processes > Invoice Batch Release |  | Billing Manager | Create and maintain bills for Accounts Receivable. | Assigned Agency | Angela Bonaminio | angela.bonaminio@sto.idaho.gov |  |  | 2022-03-01 | All Day Testing
10 | Close Billing - Invoice Verification Report | Billing > RunProcesses > Create BillingProcess > Invoice VerificationReport |  | Billing Manager | Create and maintain bills for Accounts Receivable. | Assigned Agency | Angela Bonaminio | angela.bonaminio@sto.idaho.gov |  |  | 2022-03-01 | All Day Testing
11 | Close Billing - Invoice and Register Print | Billing > RunProcesses > Create BillingProcess > Invoice and Register Print |  | Billing Manager | Create and maintain bills for Accounts Receivable. | Assigned Agency | Angela Bonaminio | angela.bonaminio@sto.idaho.gov |  |  | 2022-03-01 | All Day Testing
12 | Close Billig - Sub-system Update | Billing > RunProcesses > Create BillingProcess > Sub System Up-date |  | Billing Manager | Create and maintain bills for Accounts Receivable. | Assigned Agency | Angela Bonaminio | angela.bonaminio@sto.idaho.gov |  |  | 2022-03-01 | All Day Testing
13 | Close Billing - Billing Invoice | Billing Manager > Manage Processing > Invoice |  | Billing Manager | Create and maintain bills for Accounts Receivable. | Assigned Agency | Angela Bonaminio | angela.bonaminio@sto.idaho.gov |  |  | 2022-03-01 | All Day Testing
14 | Billing System Period Close | Billing Manager > Manage Processing > Billing System Period Close |  | Billing Manager | Create and maintain bills for Accounts Receivable. | Assigned Agency | Angela Bonaminio | angela.bonaminio@sto.idaho.gov |  |  | 2022-03-01 | All Day Testing
15 | Close Inventory Control - Unreleased Documents | 2579 |  | Inventory Manager | Manage/monitor: reconciliation of counts, item master, forecast methods & replenishment, reorder & disposal policy compliance. | Assigned Agency | Laura Steffler | laura.steffler@sto.idaho.gov |  | MF-030-090 Close Inventory Control | 2022-03-01 | All Day Testing
16 | Close Inventory Control - Journalize | 2577 |  | Inventory Manager | Manage/monitor: reconciliation of counts, item master, forecast methods & replenishment, reorder & disposal policy compliance. | LUMA | Laura Steffler | laura.steffler@sto.idaho.gov |  | MF-030-090 Close Inventory Control | 2022-03-01 | All Day Testing
17 | Close Inventory Control - Inventory Period Close | 2575 |  | Inventory Manager | Manage/monitor: reconciliation of counts, item master, forecast methods & replenishment, reorder & disposal policy compliance. | LUMA | Laura Steffler | laura.steffler@sto.idaho.gov |  | MF-030-090 Close Inventory Control | 2022-03-01 | All Day Testing
18 | Close Inventory Control - Close Inventory Control | 2574 |  | Inventory Manager | Manage/monitor: reconciliation of counts, item master, forecast methods & replenishment, reorder & disposal policy compliance. | LUMA | Laura Steffler | laura.steffler@sto.idaho.gov |  | MF-030-090 Close Inventory Control | 2022-03-01 | All Day Testing
19 | Close Inventory Control - Inventory Valuation (Report) | 2576 |  | Inventory Manager | Manage/monitor: reconciliation of counts, item master, forecast methods & replenishment, reorder & disposal policy compliance. | Assigned Agency | Laura Steffler | laura.steffler@sto.idaho.gov |  | MF-030-090 Close Inventory Control | 2022-03-01 | All Day Testing
20 | Close Inventory Control - Period End Valuation (Report) | 2578 |  | Inventory Manager | Manage/monitor: reconciliation of counts, item master, forecast methods & replenishment, reorder & disposal policy compliance. | Assigned Agency | Laura Steffler | laura.steffler@sto.idaho.gov |  | MF-030-090 Close Inventory Control | 2022-03-01 | All Day Testing
21 | Receivables - Cash Batch Exception | Receivables Manager > Processing > Payments > Cash Batch Exception tab > CashBatch Exception Payments |  | Receivables Manager | Reconcile accounts receivables & collections and assess late fees. |  | Laura Steffler | laura.steffler@sto.idaho.gov |  | MF-030-100 Close Receivables | 2022-03-01 | All Day Testing
22 | Receivables - Application Audit | Receivables Manager > Processing > Run ReceivablesProcesses > Application Audit |  | Receivables Manager | Reconcile accounts receivables & collections and assess late fees. |  | Laura Steffler | laura.steffler@sto.idaho.gov |  |  | 2022-03-01 | All Day Testing
23 | Receivables - AR Statement Print | Receivables Manager > Processing > Credit And Collection > Statement Print |  | Receivables Manager | Reconcile accounts receivables & collections and assess late fees. |  | Laura Steffler | laura.steffler@sto.idaho.gov |  |  | 2022-03-01 | All Day Testing
24 | Receivables - Application Close | Receivables Manager > Processing > Run ReceivablesProcesses > ReceivablesClose Menu > Application Close Receivables Manager > Processing > Run ReceivablesProcesses > ReceivablesClose Menu > Application Close Results |  | Receivables Manager | Reconcile accounts receivables & collections and assess late fees. |  | Laura Steffler | laura.steffler@sto.idaho.gov |  |  | 2022-03-01 | All Day Testing
25 | Receivables - Unrealized Gain Loss Report | Receivables Manager > Processing > Run ReceivablesProcesses > Unrealized GainLoss Report |  | Receivables Manager | Reconcile accounts receivables & collections and assess late fees. |  | Laura Steffler | laura.steffler@sto.idaho.gov |  |  | 2022-03-01 | All Day Testing
26 | Receivables - Journalize | Receivables Manager > Processing > > Run ReceivablesProcesses > Receivables CloseMenu > Journalize |  | Receivables Manager | Reconcile accounts receivables & collections and assess late fees. |  | Laura Steffler | laura.steffler@sto.idaho.gov |  |  | 2022-03-01 | All Day Testing
27 | Receivables - Receivable Tie Back Report | Receivables Manager > Processing > Run ReceivablesListing > Receivables TieBack Report |  | Receivables Manager | Reconcile accounts receivables & collections and assess late fees. |  | Laura Steffler | laura.steffler@sto.idaho.gov |  |  | 2022-03-01 | All Day Testing
28 | Receivable Activity Summary | Receivables Manager > Processing > Run ReceivablesProcesses > ReceivablesClose Menu > Receivable Activity Summary |  | Receivables Manager | Reconcile accounts receivables & collections and assess late fees. |  | Laura Steffler | laura.steffler@sto.idaho.gov |  |  | 2022-03-01 | All Day Testing
29 | Receivables - Period Close Report | Receivables Manager > Processing > Run ReceivablesProcesses > ReceivablesClose Menu > Period CloseReport |  | Receivables Manager | Reconcile accounts receivables & collections and assess late fees. |  | Laura Steffler | laura.steffler@sto.idaho.gov |  |  | 2022-03-01 | All Day Testing
30 | Cash -Manage Cash Ledger Transaction | CashManager > Manage Cash Ledger Transaction |  | Cash Manager | Manage all cash transactions. Review and update cash management policy as needed. |  | Angela Bonaminio | angela.bonaminio@sto.idaho.gov |  |  | 2022-03-01 | All Day Testing
31 | Cash - Journalize Preview Cash Ledger GL Distribution | Cash Manager > Journalize Preview > <Distribution Type> |  | Cash Manager | Manage all cash transactions. Review and update cash management policy as needed. |  | Angela Bonaminio | angela.bonaminio@sto.idaho.gov |  |  | 2022-03-01 | All Day Testing
32 | Cash - Journalize Cash Ledger GL Distribution | Cash Manager > Journalize Preview > <Distribution Type> > Click Journalize Distribution Button > Cash Management Group <HE> > Cash Code or Cash Code Group > Company or Company Group > Post Thru Date <Month End Date> > Click OK |  | Cash Manager | Manage all cash transactions. Review and update cash management policy as needed. |  | Angela Bonaminio | angela.bonaminio@sto.idaho.gov |  |  | 2022-03-01 | All Day Testing
33 | Cash - Close Cash Management Period | Cash Accountant > Process Month End > Bank Company Period Close Company or Company Group > Detail Report <yes> > Update <yes> > Bank Company Period Close Report <report receivers> > Error Report <report receivers> > Click Ok |  | Cash Manager | Manage all cash transactions. Review and update cash management policy as needed. |  | Angela Bonaminio | angela.bonaminio@sto.idaho.gov |  |  | 2022-03-01 | All Day Testing
34 | Close Asset Management: Run Release Assets | 11424 |  | Asset Manager | Manage the process to tract fixed asset activity: create, transfer, and retire fixed assets. | Assigned Agency | Laura Steffler | laura.steffler@sto.idaho.gov |  | MF-040-070-870 | 2022-03-01 | All Day Testing
35 | Close Asset Management: Generate Asset Depreciation Calculation and List | 11425 |  | Asset Manager | Manage the process to tract fixed asset activity: create, transfer, and retire fixed assets. | Assigned Agency | Laura Steffler | laura.steffler@sto.idaho.gov |  | MF-040-070-020 | 2022-03-01 | All Day Testing
36 | Close Asset Management: Generate Asset Report | 11430 |  | Asset Manager | Manage the process to tract fixed asset activity: create, transfer, and retire fixed assets. | Assigned Agency | Laura Steffler | laura.steffler@sto.idaho.gov |  | MF-040-070-880 | 2022-03-01 | All Day Testing
37 | Close Asset Management: Perform Asset Period Close | 11426 |  | Asset Manager | Manage the process to tract fixed asset activity: create, transfer, and retire fixed assets. | Assigned Agency | Laura Steffler | laura.steffler@sto.idaho.gov |  | MF-040-080-020 Perform Asset Period Close | 2022-03-01 | All Day Testing
38 | Process Recurring Journal Entries | Financial Business Analyst > Processing > Journal > Recurring Journal Actions > Journalize |  | Financial Business Analyst | Set up Global Ledger/Budget, monitor allocation & interfacing GL transactions, and maintain journal controls. | Assigned Agency | Laura Steffler | laura.steffler@sto.idaho.gov |  | MF-030-140 Close Recurring Journals | 2022-03-01 | All Day Testing
39 | GL - Reconcile accounts | Verify that all accounts that need to be reconciled, are reconciled. |  | Financial Business Analyst | Set up Global Ledger/Budget, monitor allocation & interfacing GL transactions, and maintain journal controls. | Assigned Agency | Laura Steffler | laura.steffler@sto.idaho.gov |  | MF-030-260 Process Year-end Adjustments and Accruals | 2022-03-01 | All Day Testing
40 | GL - Journal Posting | Create Jouranl Entry to reverse all AP Accruals if needed by Agency |  | Financial Business Analyst | Set up Global Ledger/Budget, monitor allocation & interfacing GL transactions, and maintain journal controls. |  | Laura Steffler | laura.steffler@sto.idaho.gov |  |  | 2022-03-01 | All Day Testing
41 | AR Accruals | Create Jouranl Entry to reverse all AR Accruals if needed by Agency |  | Financial Business Analyst | Set up Global Ledger/Budget, monitor allocation & interfacing GL transactions, and maintain journal controls. |  | Laura Steffler | laura.steffler@sto.idaho.gov |  |  | 2022-03-01 | All Day Testing
42 | PO/IC Accruals | Create Jouranl Entry to reverse all PO/IC Accruals if needed by Agency |  | Financial Business Analyst | Set up Global Ledger/Budget, monitor allocation & interfacing GL transactions, and maintain journal controls. |  | Laura Steffler | laura.steffler@sto.idaho.gov |  |  | 2022-03-01 | All Day Testing
43 | Journal Posting | Post all journal entries |  | Financial Business Analyst | Set up Global Ledger/Budget, monitor allocation & interfacing GL transactions, and maintain journal controls. |  | Laura Steffler | laura.steffler@sto.idaho.gov |  |  | 2022-03-01 | All Day Testing
44 | Allocations | Verify that all allocatins have been processed for period |  | Financial Business Analyst | Set up Global Ledger/Budget, monitor allocation & interfacing GL transactions, and maintain journal controls. |  | Laura Steffler | laura.steffler@sto.idaho.gov |  |  | 2022-03-01 | All Day Testing
45 | CAM ? |  |  | Financial Business Analyst | Set up Global Ledger/Budget, monitor allocation & interfacing GL transactions, and maintain journal controls. |  | Laura Steffler | laura.steffler@sto.idaho.gov |  |  | 2022-03-01 | All Day Testing
46 | Period Closing | Financial Business Analyst > Processing > Period Close > Close Period for Entity Select Entity, Year, Period > Actions > Limited Close |  | Financial Business Analyst | Set up Global Ledger/Budget, monitor allocation & interfacing GL transactions, and maintain journal controls. |  | Laura Steffler | laura.steffler@sto.idaho.gov |  |  | 2022-03-01 | All Day Testing
47 | Final Review of Period Close |  |  | Controller | Monitor financial structure and Chart of Account dimensions for their Agency and recommendations for updates. Manage all financial processes. | Assigned Agency | Laura Steffler | laura.steffler@sto.idaho.gov |  | MF-030-260 Process Year-end Adjustments and Accruals | 2022-03-01 | All Day Testing
48 | Year end Processing |  |  | Controller | Monitor financial structure and Chart of Account dimensions for their Agency and recommendations for updates. Manage all financial processes. | Assigned Agency | Laura Steffler | laura.steffler@sto.idaho.gov |  | MF-030-260 Process Year-end Adjustments and Accruals | 2022-03-01 | All Day Testing
Note on J5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard

## Global Ledger Entries and Analy
SIT 3 Scenario - Global Legder Processing and Analysis
Agency:
SIT Week - Week 8 - 2/21/ - 2/25
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Create a Front-End Split Journal Entry (Front End Split Projects Only) | Refer to Upload Template | 12154 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Laura Steffler | laura.steffler@sto.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-010 | 2022-02-23 | 8:45-9:30 AM
2 | Create a Journal Entry | Refer to Upload Template | 11668 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Laura Steffler | laura.steffler@sto.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-010 | 2022-02-23 | 9:30-10AM
3 | Approve a Journal Entry | Refer to Upload Template | 11669 | Approver | Approve transactions such as requisitions, purchase orders, solicitation & journal entries. | Assigned Agency | Laura Steffler, Angela Bonaminio, or Julie Ellsworth | laura.steffler@sto.idaho.gov, Angela.bonaminio@sto.idaho.gov, julie.ellsworth@sto.idaho.gov |  | MF-025-060 | 2022-02-23 | 10-11AM
4 | Create a Journal Entry from an Existing Journal | Refer to Upload Template | 11671 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Laura Steffler | laura.steffler@sto.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-010 | 2022-02-23 | 1-1:30PM
5 | Create a Journal Entry from a Template | Refer to Upload Template | 11670 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Laura Steffler | laura.steffler@sto.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-010 | 2022-02-23 | 1:30-2PM
6 | Create a Recurring Journal | Refer to Upload Template | 11673 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Laura Steffler | laura.steffler@sto.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-020 | 2022-02-23 | 2-2:30PM
7 | Journalize a Recurring Journal Entry | Refer to Upload Template | 12155 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Laura Steffler | laura.steffler@sto.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-030 | 2022-02-23 | 2:30-3PM
8 | Post Multiple Journal Entries | Refer to Upload Template | 12156 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Laura Steffler | laura.steffler@sto.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-23 | 3-3:30PM
9 | Post Journals from Subsystems | Refer to Upload Template | 12157 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Laura Steffler | laura.steffler@sto.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-050 | 2022-02-24 | 8:45-9:30 AM
10 | Validate (here) Reconcile (close) Subsystems to the General Ledger | Bill will put these scripts here and in close scenario | TBD | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Laura Steffler | laura.steffler@sto.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-24 | 9:30-10AM
11 | Analyze Global Ledger Totals | Refer to Upload Template | 12158 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Laura Steffler | laura.steffler@sto.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-24 | 10-11AM
12 | Perform Account Analysis | Refer to Upload Template | 11672 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Laura Steffler | laura.steffler@sto.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-24 | 1-1:30PM
13 | Perform Fund Analysis | Refer to Upload Template | 12159 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Laura Steffler | laura.steffler@sto.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-24 | 1:30-2PM
14 | Perform Organizational Unit Analysis | Refer to Upload Template | 12160 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Laura Steffler | laura.steffler@sto.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-24 | 2-2:30PM
15 | View Transactions by Entity-Account | Refer to Upload Template | 11674 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Laura Steffler | laura.steffler@sto.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-25 | 9- 9:30 AM
16 | BIRST/BI/CSF Analytic Reporting |  | TBD | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Laura Steffler | laura.steffler@sto.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-25 | 9:30 - 10 AM
17 | Evaluate Encumbrances | Placeholder - Judy and Bill (and Eileen/Cathy) are working on script for this; will have this week (12/23/21) | TBD | Staff Accountant |  | Assigned Agency | Laura Steffler | laura.steffler@sto.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-25 | 10 - 11 AM
Note on J5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard

## Chart of Accounts Maintenance
SIT 3 Scenario - Chart of Accounts Maintenance
Agency:
SIT Week - Week 10 - 3/7 - 3/11
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | View and Validate an Organizational Unit |  | TBD | Staff Accountant |  |  | Laura Steffler | laura.steffler@sto.idaho.gov |  |  | 2022-03-07 | 8:45-9:30 AM
2 | View and Validate a Project |  | TBD | Staff Accountant |  |  | Laura Steffler | laura.steffler@sto.idaho.gov |  |  | 2022-03-07 | 9:30-10AM
3 | View and Validate a Program |  | TBD | Staff Accountant |  |  | Laura Steffler | laura.steffler@sto.idaho.gov |  |  | 2022-03-07 | 10-11AM
4 | View and Validate a Location |  | TBD | Staff Accountant |  |  | Laura Steffler | laura.steffler@sto.idaho.gov |  |  | 2022-03-07 | 1-1:30PM
5 | View and Validate Additional Reporting |  | TBD | Staff Accountant |  |  | Laura Steffler | laura.steffler@sto.idaho.gov |  |  | 2022-03-07 | 1:30-2PM
6 | View and Validate Custodial Accounts (CAM) |  | TBD | Staff Accountant |  |  | Laura Steffler | laura.steffler@sto.idaho.gov |  |  | 2022-03-07 | 2-2:30PM
7 | Request a new account |  | TBD | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Laura Steffler | laura.steffler@sto.idaho.gov |  |  | 2022-03-07 | 2:30-3PM
8 | Request a new organizational unit |  | TBD | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Laura Steffler | laura.steffler@sto.idaho.gov |  |  | 2022-03-07 | 3-3:30PM
9 | View and Validate Beginning Balances |  | TBD | Staff Accountant |  |  | Laura Steffler | laura.steffler@sto.idaho.gov |  |  | 2022-03-08 | 8:45-9:30 AM
10 | Update Summary Conversion Balances to Detail |  | TBD | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. |  | Laura Steffler | laura.steffler@sto.idaho.gov |  |  | 2022-03-08 | 9:30-10AM
Note on J5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard