## SIT 3 Listing & Schedule
SIT 3 End to End Scenarios | SIT 3 Scheduled Week | 200 - Department of Administration
Inventory Management Cycle | Week 4: 1/24 - 1/28
Pcard End to End Process | Week 4: 1/24 - 1/28
Project Processing (RQ, PO, Contract, INV) | Week 4: 1/24 - 1/28
XM Pcard NO Cash Advance | Week 4: 1/24 - 1/28
XM Pcard WITH Cash Advance | Week 4: 1/24 - 1/28
Payroll End to End | Week 4: 1/24 - 1/28
Fixed Asset Acquire to Retire | Week 5: 1/31 - 2/4 | X
Statewide Contract Procure to Pay | Week 5: 1/31 - 2/4 | X
GHR Shell | Week 5: 1/31 - 2/4
Project 1.1 Project Setup and Maintanance | Week 5: 1/31 - 2/4
Project 1.2 Project Processing Master (P&G only) | Week 5: 1/31 - 2/4
AR Credit Monitoring | Week 6: 2/7 - 2/11 | X
Asset Management Maintenance | Week 6: 2/7 - 2/11
Service Contract Interagency Billing | Week 6: 2/7 - 2/11 | X
Project 1.3 Reports and Inquiry Master | Week 6: 2/7 - 2/11 & Week 7: 2/14 - 2/18
Cash Ledger Payment | Week 7: 2/14 - 2/18 | X
Interagency Billing to Settlement | Week 7: 2/14 - 2/18 | X
Non-State Billing | Week 7: 2/14 - 2/18 | X
Procure to Pay Vendor Management Voids | Week 7: 2/14 - 2/18 | X
Vendor Refunds | Week 7: 2/14 - 2/18 | X
Cash Management Deposit to Revenue | Week 8: 2/21 - 2/25 | X
Custodial Accounts Setup | Week 8: 2/21 - 2/25
Global Ledger Entries and Analysis | Week 8: 2/21 - 2/25 | X
Punchout Request to Payment | Week 8: 2/21 - 2/25 | X
Tax Refunds | Week 8: 2/21 - 2/25
Allocations | Week 9: 2/28 - 3/4
Budget | Week 9: 2/28 - 3/4
Custodial Accounts Transaction Processing | Week 9: 2/28 - 3/4
Month End/Year End | Week 9: 2/28 - 3/4 | X
Define and Generate Recurring Invoices | Week 9: 2/28 - 3/4
Chart of Accounts Maintenance | Week 10: 3/7 - 3/11 | X
3rd Party Allocations | TBD

## Instructions
Luma System Integration Testing 3 (SIT 3) Instructions
Agency Functional Testing Dates | January 24 - March 11, 2022 Testing Schedule: Monday -Thursday 8:45 -11 am and 1:45 - 4:00 pm, Friday 9:00 - 11:00 am
Agency Testers Roles and Responsibilities | 1. Execute test scripts per SIT 3 schedule. 2. Review actual results against expected results. 3. Log defects as needed. 4. Retest failed test results to resolve defects. 5. Launch integrations during test cycle per schedule.
Testing Packet | 1. Test Scenario Excel File: Cover Page, Instruction Tab, Scenario Listing, Tab with each steps script detailed instruction to execute the script. 2. Data Sheets. 3. Email Template to use to report your testing results.
Testing Steps | 1. If you are the first step in the scenario, you may begin execution according to the the Date and Time in the Testing packet. If you are not on step 1, please wait for the step before you to complete their script and you receive communication to begin. 2. Execute assigned script(s) using the testing script and data sheet that was provided to you. 3. Sending Testing results via email using to the Test Management Team. (attached email sample) 4. Communicate to the next tester they can begin their script. (Slack or Email works)
What should you do if there are issues or you need assistance while testing? | 1. The Test Management Team will host an all-day SIT 3 Testing Support Hotline (WebEx Meeting). 2. Attendance is optional for SIT testers and testers should only join if they have questions or issues regarding SIT testing. 3. Testers should have an invite on their calendar that includes the WebEx Link.
How to submit a SIT 3 Testing Defect using ServiceNow: | 1. Visit https://auth.sco.idaho.gov/ in your web browser. Google Chrome and Microsoft Edge are recommended. 2. Enter your State ID number as the username and your password. Click the Sign In button. 3. You will be presented with a second page for Multi-Factor Authentication. Select an option and acknowledge the push or call, or enter a passcode from your Duo app. 4. You will see several buttons on your Enterprise Dashboard. One of these will be labeled Service Desk. This button will take you to the Service Portal. 5. There are four main buttons across the center of the page. Click Service Requests to be taken to the service menu. 7. Locate and select LUMA SIT3 Testing Issue from the options listed. 6. Select the SCO IT Services category from the list on the left side of the page. 7. Fill out form with Primary Contact, Short Description, Description, Category, Scenario Name, Script ID, add attachments/screenshots and submit the ticket.
What to do if there is a system outage? | 1. Please join the Testing Support Hotline if you run into any issues with the system and notify the meeting moderator of the issue. 2. If there is a system outage, the Test Management Team will work with the Communications team to notify Agency Testers.

## Email Submission Template
Click on Icon Below to Outlook Email Template

## Fixed Assets Acquire To Retire
SIT 3 Scenario - Acquire Fixed Asset to Retire
Agency:
SIT 3 Week - Week 5 - 1/31-2/4
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | NEW SIT 3 ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Create Fixed Asset Requisition | 3041 | 11563 | Requester | Determines requirements & cost estimates for purchase of goods & services. Submits purchase requisition. | Assigned Agency | Laura Gallivan or Linda Edkins | linda.edkins@adm.idaho.gov or laura.gallivan@adm.idaho.gov | Associate with project | PR-010-060 | 2022-01-31 | 8:45-9:30 AM
2 | Approve Requisition | 8539 | 11564 | Approver | Approve transactions such as requisitions, purchase orders, solicitations, and journal entries. | Assigned Agency | Lvl 1 Chelsea Robillard Lvl 2 Lynn Christian Lvl 3 Genny Casiano | chelsea.robillard@adm.idaho.gov lynn.christian@adm.idaho.gov genny.casiano@adm.idaho.gov | Deny Requisition - add note - need more information Approve Requisition | PR-020-020 | 2022-01-31 | 9:30-10AM
3 | Identify Requistions to send to Sourcing Event | 2896 | 11565 | Buyer | Review requisition and create purchase orders. Conduct market research, and monitor vendor commitments. Approve vendor returns. | Assigned Agency | Laura Gallivan or Linda Edkins | linda.edkins@adm.idaho.gov or laura.gallivan@adm.idaho.gov |  | PR-030-020 | 2022-01-31 | 10-11AM
4 | Create Sourcing Event RFQ | 7186 | 11566 | Sourcing Manager | Create souring events, evaluate supplier responses, and oversee selection & award of sourcing events. | Assigned Agency | Bob Morlan, Chelsea Robillard, Forrest Benedict, Joseph Nelson, Laura Gallivan, Mike Gwinn, Patrick Murphy, Quinn Shea, Thayne Pearson, or Valierie Bollinger | bob.morlan@adm.idaho.gov, chelsea.robillard@adm.idaho.gov, forrest.benedict@adm.idaho.gov, joseph.nelson@adm.idaho.gov, laura.gallivan@adm.idaho.gov, mike.gwinn@adm.idaho.gov, patrick.murphy@adm.idaho.gov, quinn.shea@adm.idaho.gov, thayne.pearson@adm.idaho.gov, valerie.bollinger@adm.idaho.gov |  | PR-030-030 | 2022-01-31 | 1-1:30PM
5 | Approve Sourcing Event to Post | 8439 | 11567 | Approver | Approve transactions such as requisitions, purchase orders, solicitations, and journal entries. | Assigned Agency | 0-99,999.99 Mike Gwinn, Chelsea Robillard, Valerie Bollinger 100,000.00-249,999.99 Mike Gwinn, Chelsea Robillard, Valerie Bollinger 250,000.00-9,999,999,999.99 Mike Gwinn, Chelsea Robillard, Valerie Bollinger | mike.gwinn@adm.idaho.gov chelsea.robillard@adm.idaho.gov valierie.bollinger@adm.idaho.gov | Approve/Deny/Reject Sourcing Event to Post | PR-030-010 | 2022-01-31 | 1:30-2PM
6 | Enter A Manual response | 7187 | 11568 | Sourcing Manager | Develop/oversee supplier list; monitor & evaluate vendors. Evaluate proposals; create souring events, oversee selection & award contracts. | Assigned Agency | Bob Morlan, Chelsea Robillard, Forrest Benedict, Joseph Nelson, Laura Gallivan, Mike Gwinn, Patrick Murphy, Quinn Shea, Thayne Pearson, or Valierie Bollinger | bob.morlan@adm.idaho.gov, chelsea.robillard@adm.idaho.gov, forrest.benedict@adm.idaho.gov, joseph.nelson@adm.idaho.gov, laura.gallivan@adm.idaho.gov, mike.gwinn@adm.idaho.gov, patrick.murphy@adm.idaho.gov, quinn.shea@adm.idaho.gov, thayne.pearson@adm.idaho.gov, valerie.bollinger@adm.idaho.gov |  | PR-030-050 | 2022-01-31 | 2-2:30PM
7 | Analyze and Award an Event to Contract | 7189 | 11569 | Sourcing Manager | Develop/oversee supplier list; monitor & evaluate vendors. Evaluate proposals; create souring events, oversee selection & award contracts. | Assigned Agency | Bob Morlan, Chelsea Robillard, Forrest Benedict, Joseph Nelson, Laura Gallivan, Mike Gwinn, Patrick Murphy, Quinn Shea, Thayne Pearson, or Valierie Bollinger | bob.morlan@adm.idaho.gov, chelsea.robillard@adm.idaho.gov, forrest.benedict@adm.idaho.gov, joseph.nelson@adm.idaho.gov, laura.gallivan@adm.idaho.gov, mike.gwinn@adm.idaho.gov, patrick.murphy@adm.idaho.gov, quinn.shea@adm.idaho.gov, thayne.pearson@adm.idaho.gov, valerie.bollinger@adm.idaho.gov | Split Award by Line | PR-030-050 | 2022-01-31 | 2:30-3PM
8 | Sourcing Event Award Approval | 8440 | 11570 | Approver | Approve transactions such as requisitions, purchase orders, solicitations, and journal entries. | Assigned Agency | 0-99,999.99 Mike Gwinn, Chelsea Robillard, Valerie Bollinger 100,000.00-249,999.99 Mike Gwinn, Chelsea Robillard, Valerie Bollinger 250,000.00-9,999,999,999.99 Mike Gwinn, Chelsea Robillard, Valerie Bollinger | mike.gwinn@adm.idaho.gov chelsea.robillard@adm.idaho.gov valierie.bollinger@adm.idaho.gov | Approve/Deny/Reject | PR-030-050 | 2022-01-31 | 3-3:30PM
9 | Create Contract - Create a Contract - Contract Tab | 7219 | 11571 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | Assigned Agency | Bob Morlan, Chelsea Robillard, Forrest Benedict, Joseph Nelson, Laura Gallivan, Mike Gwinn, Patrick Murphy, Quinn Shea, or Thayne Pearson, | bob.morlan@adm.idaho.gov, chelsea.robillard@adm.idaho.gov, forrest.benedict@adm.idaho.gov, joseph.nelson@adm.idaho.gov, laura.gallivan@adm.idaho.gov, mike.gwinn@adm.idaho.gov, patrick.murphy@adm.idaho.gov, quinn.shea@adm.idaho.gov, thayne.pearson@adm.idaho.gov |  | PR-040-010 | 2022-02-01 | 8:45 - 10:30AM
10 | Create Contract - Contract Draft - Articles Tab | 7204 | 11572 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | Assigned Agency | Bob Morlan, Chelsea Robillard, Forrest Benedict, Joseph Nelson, Laura Gallivan, Mike Gwinn, Patrick Murphy, Quinn Shea, or Thayne Pearson, | bob.morlan@adm.idaho.gov, chelsea.robillard@adm.idaho.gov, forrest.benedict@adm.idaho.gov, joseph.nelson@adm.idaho.gov, laura.gallivan@adm.idaho.gov, mike.gwinn@adm.idaho.gov, patrick.murphy@adm.idaho.gov, quinn.shea@adm.idaho.gov, thayne.pearson@adm.idaho.gov |  | PR-040-010 | 2022-02-01 | 8:45 - 10:30AM
11 | Create Contract - Contract Draft - Participants Tab | 2667 | 11573 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | Assigned Agency | Bob Morlan, Chelsea Robillard, Forrest Benedict, Joseph Nelson, Laura Gallivan, Mike Gwinn, Patrick Murphy, Quinn Shea, or Thayne Pearson, | bob.morlan@adm.idaho.gov, chelsea.robillard@adm.idaho.gov, forrest.benedict@adm.idaho.gov, joseph.nelson@adm.idaho.gov, laura.gallivan@adm.idaho.gov, mike.gwinn@adm.idaho.gov, patrick.murphy@adm.idaho.gov, quinn.shea@adm.idaho.gov, thayne.pearson@adm.idaho.gov |  | PR-040-010 | 2022-02-01 | 8:45 - 10:30AM
12 | Create Contract - Contract Draft - Lines Tab - Special | 8909 | 11574 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | Assigned Agency | Bob Morlan, Chelsea Robillard, Forrest Benedict, Joseph Nelson, Laura Gallivan, Mike Gwinn, Patrick Murphy, Quinn Shea, or Thayne Pearson, | bob.morlan@adm.idaho.gov, chelsea.robillard@adm.idaho.gov, forrest.benedict@adm.idaho.gov, joseph.nelson@adm.idaho.gov, laura.gallivan@adm.idaho.gov, mike.gwinn@adm.idaho.gov, patrick.murphy@adm.idaho.gov, quinn.shea@adm.idaho.gov, thayne.pearson@adm.idaho.gov |  | PR-040-010 | 2022-02-01 | 8:45 - 10:30AM
13 | Create Contract - Contract Draft - Contacts Tab | 3335 | 11575 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | Assigned Agency | Bob Morlan, Chelsea Robillard, Forrest Benedict, Joseph Nelson, Laura Gallivan, Mike Gwinn, Patrick Murphy, Quinn Shea, or Thayne Pearson, | bob.morlan@adm.idaho.gov, chelsea.robillard@adm.idaho.gov, forrest.benedict@adm.idaho.gov, joseph.nelson@adm.idaho.gov, laura.gallivan@adm.idaho.gov, mike.gwinn@adm.idaho.gov, patrick.murphy@adm.idaho.gov, quinn.shea@adm.idaho.gov, thayne.pearson@adm.idaho.gov |  | PR-040-010 | 2022-02-01 | 8:45 - 10:30AM
14 | Create Contract - Contract Draft - Releasing a Contract | 7203 | 11576 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | Assigned Agency | Bob Morlan, Chelsea Robillard, Forrest Benedict, Joseph Nelson, Laura Gallivan, Mike Gwinn, Patrick Murphy, Quinn Shea, or Thayne Pearson, | bob.morlan@adm.idaho.gov, chelsea.robillard@adm.idaho.gov, forrest.benedict@adm.idaho.gov, joseph.nelson@adm.idaho.gov, laura.gallivan@adm.idaho.gov, mike.gwinn@adm.idaho.gov, patrick.murphy@adm.idaho.gov, quinn.shea@adm.idaho.gov, thayne.pearson@adm.idaho.gov |  | PR-040-010 | 2022-02-01 | 8:45 - 10:30AM
16 | Contract Approval | 8353 | 11578 | Approver | Approve transactions such as requisitions, purchase orders, solicitation & journal entries. | Assigned Agency | 0-99,999.99 Mike Gwinn, Chelsea Robillard, Valerie Bollinger 100,000.00-249,999.99 Mike Gwinn, Chelsea Robillard, Valerie Bollinger 250,000.00-9,999,999,999.99 Mike Gwinn, Chelsea Robillard, Valerie Bollinger | mike.gwinn@adm.idaho.gov chelsea.robillard@adm.idaho.gov valierie.bollinger@adm.idaho.gov | Approve/Deny/Reject | PR-040-010 | 2022-02-01 | 10:30-11AM
15 | Create Contract - Contract Draft - Activating a Contract | 7202 | 11577 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | Assigned Agency | Bob Morlan, Chelsea Robillard, Forrest Benedict, Joseph Nelson, Laura Gallivan, Mike Gwinn, Patrick Murphy, Quinn Shea, or Thayne Pearson, | bob.morlan@adm.idaho.gov, chelsea.robillard@adm.idaho.gov, forrest.benedict@adm.idaho.gov, joseph.nelson@adm.idaho.gov, laura.gallivan@adm.idaho.gov, mike.gwinn@adm.idaho.gov, patrick.murphy@adm.idaho.gov, quinn.shea@adm.idaho.gov, thayne.pearson@adm.idaho.gov |  | PR-040-010 | 2022-02-01 | 8:45 - 10:30AM
17 | Create Fixed Asset Requisition | 3041 | 11579 | Requester | Determines requirements & cost estimates for purchase of goods & services. Submits purchase requisition. | Assigned Agency | Laura Gallivan or Linda Edkins | linda.edkins@adm.idaho.gov or laura.gallivan@adm.idaho.gov |  | PR-010-060 | 2022-02-01 | 1-1:30PM
18 | Approve Requisition | 8539 | 11580 | Approver | Approve transactions such as requisitions, purchase orders, solicitations, and journal entries. | Assigned Agency | Lvl 1 Chelsea Robillard Lvl 2 Lynn Christian Lvl 3 Genny Casiano | chelsea.robillard@adm.idaho.gov lynn.christian@adm.idaho.gov genny.casiano@adm.idaho.gov |  | PR-020-020 | 2022-02-01 | 1:30-2PM
19 | Create Purchase Order | 2753 | 11581 | Buyer | Review requisition and create purchase orders. Conduct market research, and monitor vendor commitments. Approve vendor returns. | Assigned Agency | Laura Gallivan or Linda Edkins | linda.edkins@adm.idaho.gov or laura.gallivan@adm.idaho.gov |  | PR-050-040 | 2022-02-01 | 2-2:30PM
20 | Receive Purchase Order | 2178 | 11582 | Receiver | Receive and inspect incoming goods. Pick items for shipment/transfer. Dispose of items. Conduct vendor returns. Document variances. | Assigned Agency | Laura Gallivan or Linda Edkins | linda.edkins@adm.idaho.gov or laura.gallivan@adm.idaho.gov | Receive less/more than ordered | PR-050-070 | 2022-02-01 | 2:30-3PM
21 | Inspect Item | 2181 | 11583 | Receiver | Receive and inspect incoming goods. Pick items for shipment/transfer. Dispose of items. Conduct vendor returns. Document variances. | Assigned Agency | Laura Gallivan or Linda Edkins | linda.edkins@adm.idaho.gov or laura.gallivan@adm.idaho.gov | Inspection Failed, Vendor Return | PR-050-070 | 2022-02-01 | 3-3:30PM
22 | Create Invoice | 11447 | 11584 | Payables Invoice Processor | Process interface and XM files. Match payables invoices, and vendor list. Process payables payments. Generate 1099. | Assigned Agency | Sheri Jones | sheri.jones@adm.idaho.gov |  | MF-070-050 Enter a PO Invoice | 2022-02-02 | 8:45-9:30 AM
23 | Approve Invoice | 11448 | 11585 | Approver | Approve transactions such as requisitions, purchase orders, solicitations, and journal entries. | Assigned Agency | Lvl 1 Arvin Deleon Guerrero, Lynn Christian or Genny Casiano Lvl 2 Genny Casiano or Kim Rau | arvin.deleon-guerrero@adm.idaho.gov lynn.christian@adm.idaho.gov genny.casiano@adm.idaho.gov kim.rau@adm.idaho.gov |  | MF-070-056 Invoice Approval Process | 2022-02-02 | 9:30-10AM
24 | Match Invoice | 11455 | 11586 | Payables Manager | Void & cancel payments. Reissue & mail warrants. Process period close. | Assigned Agency | Lynn Christian | Lynn.christian@adm.idaho.gov |  | MF-070-070 Match Invoices | 2022-02-02 | 10-10:30AM
25 | Process Payment for Invoice | 11442 | 11587 | Payables Manager | Void & cancel payments. Reissue & mail warrants. Process period close. | Assigned Agency | Lynn Christian | Lynn.christian@adm.idaho.gov |  | MF-070-100 Process Invoice Payments | 2022-02-02 | 10:30-11AM
26 | Interface AP Asset to Asset Management | 2713 | 11900 | Asset Analyst | Create, add, transfer, adjust, retire, or dispose of assets, including privileges to run depreciation. | Assigned Agency | Sheri Jones | sheri.jones@adm.idaho.gov |  | MF-040-030-010 | 2022-02-02 | 1-1:30PM
27 | Run Release Assets - Update | 8524 | 11905 | Asset Analyst | Create, add, transfer, adjust, retire, or dispose of assets, including privileges to run depreciation. | Assigned Agency | Sheri Jones | sheri.jones@adm.idaho.gov | Associate with project | MF-040-030-020 | 2022-02-02 | 1:30-2PM
28 | Run Depreciation | 8522 | 11904 | Asset Manager | Manage the process to tract fixed asset activity: create, transfer, and retire fixed assets. | Assigned Agency | Genny Casiano or Steven Bailey | steven.bailey@adm.idaho.gov |  | MF-040-070-020 | 2022-02-02 | 2-2:30PM
29 | Review Fixed Asset GL Account Transactions |  |  | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate, and update allocations. | Assigned Agency | Lynn Christian or Sheri Jones | Lynn.christian@adm.idaho.gov & sheri.jones@adm.idaho.gov |  | MF-020-010 | 2022-02-02 | 2:30-3PM
30 | Asset Surplus Disposal | 11062 | 11902 | Asset Analyst | Create, add, transfer, adjust, retire, or dispose of assets, including privileges to run depreciation. | Assigned Agency | Sheri Jones | sheri.jones@adm.idaho.gov & genny.casiano@adm.idaho.gov | Transfer, retire | MF-040-060-020 | 2022-02-02 | 3-3:30PM
31 | Approve Disposal | 11263 | 11903 | Asset Manager | Manage the process to tract fixed asset activity: create, transfer, and retire fixed assets. | Assigned Agency | Genny Casiano or Steven Bailey | sheri.jones@adm.idaho.gov & genny.casiano@adm.idaho.gov | Transfer | MF-040-060-020 | 2022-02-02 | 3:30-4PM
32 | Close Contract | 2636 | 11901 | Contract Manager | Compile contract file, including entering contract line-item details, terms & conditions, and pricing, and amends and renews contracts. | Assigned Agency | Bob Morlan, Chelsea Robillard, Forrest Benedict, Joseph Nelson, Laura Gallivan, Mike Gwinn, Patrick Murphy, Quinn Shea, or Thayne Pearson, | bob.morlan@adm.idaho.gov, chelsea.robillard@adm.idaho.gov, forrest.benedict@adm.idaho.gov, joseph.nelson@adm.idaho.gov, laura.gallivan@adm.idaho.gov, mike.gwinn@adm.idaho.gov, patrick.murphy@adm.idaho.gov, quinn.shea@adm.idaho.gov, thayne.pearson@adm.idaho.gov |  | PR-050-030 | 2022-02-03 | 8:45-9:30 AM
Note on J5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard

## Statewide Contract Procure to P
SIT 3 Scenario - Statewide Contract Procure to Pay
Agency:
SIT 3 Week - Week 5 - 1/31-2/4
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Create Contract with Rebate and Price Breaks Statewide for Envelopes - Create a Contract (Contract Tab) | 7219 | 11992 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | DOP | Bob Morlan, Chelsea Robillard, Forrest Benedict, Joseph Nelson, Laura Gallivan, Mike Gwinn, Patrick Murphy, Quinn Shea, or Thayne Pearson, | bob.morlan@adm.idaho.gov, chelsea.robillard@adm.idaho.gov, forrest.benedict@adm.idaho.gov, joseph.nelson@adm.idaho.gov, laura.gallivan@adm.idaho.gov, mike.gwinn@adm.idaho.gov, patrick.murphy@adm.idaho.gov, quinn.shea@adm.idaho.gov, thayne.pearson@adm.idaho.gov |  | PR-040-020 | 2022-01-31 | 8:45 - 11 AM
2 | Create Contract with Rebate and Price Breaks Statewide for Envelopes - Contract Draft (Articles) | 7204 | 11987 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | DOP | Bob Morlan, Chelsea Robillard, Forrest Benedict, Joseph Nelson, Laura Gallivan, Mike Gwinn, Patrick Murphy, Quinn Shea, or Thayne Pearson, | bob.morlan@adm.idaho.gov, chelsea.robillard@adm.idaho.gov, forrest.benedict@adm.idaho.gov, joseph.nelson@adm.idaho.gov, laura.gallivan@adm.idaho.gov, mike.gwinn@adm.idaho.gov, patrick.murphy@adm.idaho.gov, quinn.shea@adm.idaho.gov, thayne.pearson@adm.idaho.gov |  | PR-040-020 | 2022-01-31 | 8:45 - 11 AM
3 | Create Contract with Rebate and Price Breaks Statewide for Envelopes - Contract Draft - Participants | 2667 | 11997 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | DOP | Bob Morlan, Chelsea Robillard, Forrest Benedict, Joseph Nelson, Laura Gallivan, Mike Gwinn, Patrick Murphy, Quinn Shea, or Thayne Pearson, | bob.morlan@adm.idaho.gov, chelsea.robillard@adm.idaho.gov, forrest.benedict@adm.idaho.gov, joseph.nelson@adm.idaho.gov, laura.gallivan@adm.idaho.gov, mike.gwinn@adm.idaho.gov, patrick.murphy@adm.idaho.gov, quinn.shea@adm.idaho.gov, thayne.pearson@adm.idaho.gov |  | PR-040-020 | 2022-01-31 | 8:45 - 11 AM
4 | Create Contract with Rebate and Price Breaks Statewide for Envelopes - Contract Draft - Lines - Special | 8909 | 11995 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | DOP | Bob Morlan, Chelsea Robillard, Forrest Benedict, Joseph Nelson, Laura Gallivan, Mike Gwinn, Patrick Murphy, Quinn Shea, or Thayne Pearson, | bob.morlan@adm.idaho.gov, chelsea.robillard@adm.idaho.gov, forrest.benedict@adm.idaho.gov, joseph.nelson@adm.idaho.gov, laura.gallivan@adm.idaho.gov, mike.gwinn@adm.idaho.gov, patrick.murphy@adm.idaho.gov, quinn.shea@adm.idaho.gov, thayne.pearson@adm.idaho.gov |  | PR-040-020 | 2022-01-31 | 8:45 - 11 AM
5 | Create Contract with Rebate and Price Breaks Statewide for Envelopes - Contract Draft - Lines - Purchase Type Detail - Purchase Pricing | 2663 | 11996 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | DOP | Bob Morlan, Chelsea Robillard, Forrest Benedict, Joseph Nelson, Laura Gallivan, Mike Gwinn, Patrick Murphy, Quinn Shea, or Thayne Pearson, | bob.morlan@adm.idaho.gov, chelsea.robillard@adm.idaho.gov, forrest.benedict@adm.idaho.gov, joseph.nelson@adm.idaho.gov, laura.gallivan@adm.idaho.gov, mike.gwinn@adm.idaho.gov, patrick.murphy@adm.idaho.gov, quinn.shea@adm.idaho.gov, thayne.pearson@adm.idaho.gov |  | PR-040-020 | 2022-01-31 | 8:45 - 11 AM
6 | Create Contract with Rebate and Price Breaks Statewide for Envelopes - Contract Draft - Rebates | 2671 | 11998 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | DOP | Bob Morlan, Chelsea Robillard, Forrest Benedict, Joseph Nelson, Laura Gallivan, Mike Gwinn, Patrick Murphy, Quinn Shea, or Thayne Pearson, | bob.morlan@adm.idaho.gov, chelsea.robillard@adm.idaho.gov, forrest.benedict@adm.idaho.gov, joseph.nelson@adm.idaho.gov, laura.gallivan@adm.idaho.gov, mike.gwinn@adm.idaho.gov, patrick.murphy@adm.idaho.gov, quinn.shea@adm.idaho.gov, thayne.pearson@adm.idaho.gov |  | PR-040-020 | 2022-01-31 | 8:45 - 11 AM
7 | Create Contract with Rebate and Price Breaks Statewide for Envelopes - Contract Draft - Contacts | 3335 | 11993 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | DOP | Bob Morlan, Chelsea Robillard, Forrest Benedict, Joseph Nelson, Laura Gallivan, Mike Gwinn, Patrick Murphy, Quinn Shea, or Thayne Pearson, | bob.morlan@adm.idaho.gov, chelsea.robillard@adm.idaho.gov, forrest.benedict@adm.idaho.gov, joseph.nelson@adm.idaho.gov, laura.gallivan@adm.idaho.gov, mike.gwinn@adm.idaho.gov, patrick.murphy@adm.idaho.gov, quinn.shea@adm.idaho.gov, thayne.pearson@adm.idaho.gov |  | PR-040-020 | 2022-01-31 | 8:45 - 11 AM
8 | Create Contract with Rebate and Price Breaks Statewide for Envelopes - Releasing a Contract | 7203 | 11985 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | DOP | Bob Morlan, Chelsea Robillard, Forrest Benedict, Joseph Nelson, Laura Gallivan, Mike Gwinn, Patrick Murphy, Quinn Shea, or Thayne Pearson, | bob.morlan@adm.idaho.gov, chelsea.robillard@adm.idaho.gov, forrest.benedict@adm.idaho.gov, joseph.nelson@adm.idaho.gov, laura.gallivan@adm.idaho.gov, mike.gwinn@adm.idaho.gov, patrick.murphy@adm.idaho.gov, quinn.shea@adm.idaho.gov, thayne.pearson@adm.idaho.gov |  | PR-040-020 | 2022-01-31 | 8:45 - 11 AM
10 | Contract Approval | 8353 | 11979 | Approver | Approve transactions such as requisitions, purchase orders, solicitation & journal entries. | DOP | 0-99,999.99 Mike Gwinn, Chelsea Robillard, Valerie Bollinger 100,000.00-249,999.99 Mike Gwinn, Chelsea Robillard, Valerie Bollinger 250,000.00-9,999,999,999.99 Mike Gwinn, Chelsea Robillard, Valerie Bollinger | mike.gwinn@adm.idaho.gov chelsea.robillard@adm.idaho.gov valierie.bollinger@adm.idaho.gov |  | PR-040-020 | 2022-01-31 | 1 - 1:30 PM
9 | Create Contract with Rebate and Price Breaks Statewide for Envelopes - Activating a Contract | 7202 | 11978 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | DOP | Bob Morlan, Chelsea Robillard, Forrest Benedict, Joseph Nelson, Laura Gallivan, Mike Gwinn, Patrick Murphy, Quinn Shea, or Thayne Pearson, | bob.morlan@adm.idaho.gov, chelsea.robillard@adm.idaho.gov, forrest.benedict@adm.idaho.gov, joseph.nelson@adm.idaho.gov, laura.gallivan@adm.idaho.gov, mike.gwinn@adm.idaho.gov, patrick.murphy@adm.idaho.gov, quinn.shea@adm.idaho.gov, thayne.pearson@adm.idaho.gov |  | PR-040-020 | 2022-01-31 | 8:45 - 11 AM
11 | Requisition - RSS | 8325 | 11988 | Requester | Determines requirements & cost estimates for purchase of goods & services. Submits purchase requisition. | Assigned Agency | Laura Gallivan or Linda Edkins | linda.edkins@adm.idaho.gov or laura.gallivan@adm.idaho.gov | distribution to multiple org unit and agencies | PR-020-010 | 2022-01-31 | 1:30 - 2:30 PM
12 | Approve Requisition | 8539 | 11984 | Approver | Approve transactions such as requisitions, purchase orders, solicitation & journal entries. | Assigned Agency | Lvl 1 Chelsea Robillard Lvl 2 Lynn Christian Lvl 3 Genny Casiano | chelsea.robillard@adm.idaho.gov lynn.christian@adm.idaho.gov genny.casiano@adm.idaho.gov |  | PR-020-010 | 2022-01-31 | 2:30 - 3 PM
13 | Create PO from Requisition | 8327 | 11991 | Buyer | Review requisitions & create purchase orders. Conduct market research & monitor vendor commitments. Approve vendor returns. | Assigned Agency | Laura Gallivan or Linda Edkins | linda.edkins@adm.idaho.gov or laura.gallivan@adm.idaho.gov |  | PR-050-040 | 2022-02-01 | 8:45-9:30 AM
14 | Receive Purchase Order | 3064 | 11977 | Receiver | Receive and inspect incoming goods. Pick items for shipment/transfer. Dispose of items. Vendor returns. Document variances. | Assigned Agency | Laura Gallivan or Linda Edkins | linda.edkins@adm.idaho.gov or laura.gallivan@adm.idaho.gov |  | PR-050-070 | 2022-02-01 | 9:30-10AM
15 | Create Invoice | 11606 | 11983 | Payables Invoice Processor | Process interface and XM files. Match payables invoices, and vendor list. Process payables payments. Generate 1099. | Assigned Agency | Sheri Jones | sheri.jones@adm.idaho.gov |  | MF-070-050 Enter a PO Invoice | 2022-02-01 | 10-11AM
16 | Notify Buyer of Discrepancy | 11605 | 11982 | Payables Invoice Processor | Process interface and XM files. Match payables invoices, and vendor list. Process payables payments. Generate 1099. |  | Sheri Jones | sheri.jones@adm.idaho.gov |  | MF-070-050 Enter a PO Invoice | 2022-02-01 | 1-1:30PM
17 | Resolve Cost Discrepancy | New | 12004 | Buyer | Review requisition and create purchase orders. Conduct market research, and monitor vendor commitments. Approve vendor returns. | Assigned Agency | Laura Gallivan or Linda Edkins | linda.edkins@adm.idaho.gov or laura.gallivan@adm.idaho.gov |  |  | 2022-02-01 | 1:30-2PM
18 | Submit Resolved Invoice for Approval | 11607 | 11989 | Payables Invoice Processor | Process interface and XM files. Match payables invoices, and vendor list. Process payables payments. Generate 1099. |  | Sheri Jones | sheri.jones@adm.idaho.gov |  | MF-070-050 Enter a PO Invoice | 2022-02-01 | 2-2:30PM
19 | Approve Invoice | 11608 | 11990 | Approver | Approve transactions such as requisitions, purchase orders, solicitations, and journal entries. | Assigned Agency | Lvl 1 Arvin Deleon Guerrero, Lynn Christian or Genny Casiano Lvl 2 Genny Casiano or Kim Rau | arvin.deleon-guerrero@adm.idaho.gov lynn.christian@adm.idaho.gov genny.casiano@adm.idaho.gov kim.rau@adm.idaho.gov |  | MF-070-056 Invoice Approval Process | 2022-02-01 | 2:30-3PM
20 | Match Invoice | 11609 | 11994 | Payables Manager | Void & cancel payments. Reissue & mail warrants. Process period close. | Assigned Agency | Lynn Christian | Lynn.christian@adm.idaho.gov |  | MF-070-070 Match Invoices | 2022-02-01 | 3-3:30PM
21 | Process Payment for Invoice | 11442 | 11981 | Payables Manager | Void & cancel payments. Reissue & mail warrants. Process period close. | Assigned Agency | Lynn Christian | Lynn.christian@adm.idaho.gov |  | MF-070-100 Process Invoice Payments | 2022-02-01 | 3-3:30PM
22 | Journalize | 11440 | 11980 | Payables Manager | Void & cancel payments. Reissue & mail warrants. Process period close. |  | Lynn Christian | Lynn.christian@adm.idaho.gov |  | MF-070-110 Journalize AP Distributions | 2022-02-01 | 3-3:30PM
23 | Renew/Addendum Statewide Contract | 2773 | 11986 | Contract Manager | Compile contract file, including entering contract line-item details, terms & conditions, and pricing, and amends and renews contracts. | DOP | Bob Morlan, Chelsea Robillard, Forrest Benedict, Joseph Nelson, Laura Gallivan, Mike Gwinn, Patrick Murphy, Quinn Shea, or Thayne Pearson, | bob.morlan@adm.idaho.gov, chelsea.robillard@adm.idaho.gov, forrest.benedict@adm.idaho.gov, joseph.nelson@adm.idaho.gov, laura.gallivan@adm.idaho.gov, mike.gwinn@adm.idaho.gov, patrick.murphy@adm.idaho.gov, quinn.shea@adm.idaho.gov, thayne.pearson@adm.idaho.gov |  | PR-050-010 | 2022-02-02 | 8:45-9:30 AM
24 | Load Rebate Invoices | New | 11999 | Supply Management Admin or Processor |  | Assigned Agency |  |  |  | PR-050-010 | 2022-02-02 | 9:30-10AM
25 | Calculate Rebate Amounts Due for a Contract | New | 12000 | Supply Management Admin or Processor | [5 empty] | PR-050-010 | 2022-02-02 | 10-11AM
26 | Review Rebate Due Information | New | 12001 | Contract Manager | Compile contract file, including entering contract line-item details, terms & conditions, and pricing, and amends and renews contracts. | Assigned Agency | Bob Morlan, Chelsea Robillard, Forrest Benedict, Joseph Nelson, Laura Gallivan, Mike Gwinn, Patrick Murphy, Quinn Shea, or Thayne Pearson, | bob.morlan@adm.idaho.gov, chelsea.robillard@adm.idaho.gov, forrest.benedict@adm.idaho.gov, joseph.nelson@adm.idaho.gov, laura.gallivan@adm.idaho.gov, mike.gwinn@adm.idaho.gov, patrick.murphy@adm.idaho.gov, quinn.shea@adm.idaho.gov, thayne.pearson@adm.idaho.gov |  | PR-050-010 | 2022-02-02 | 1-1:30PM
27 | Apply Rebate (Enter a Rebate Invoice in Payables | New | 12002 | Payables Manager | Void & cancel payments. Reissue & mail warrants. Process period close. |  | Lynn Christian | Lynn.christian@adm.idaho.gov | There isn't an invoice type of Rebate Invoice???? | MF-260-070ZZ | 2022-02-03 | 8:45-9:30 AM
28 | Review Rebate Information | New | 12003 | Contract Manager | Compile contract file, including entering contract line-item details, terms & conditions, and pricing, and amends and renews contracts. |  | Bob Morlan, Chelsea Robillard, Forrest Benedict, Joseph Nelson, Laura Gallivan, Mike Gwinn, Patrick Murphy, Quinn Shea, or Thayne Pearson, | bob.morlan@adm.idaho.gov, chelsea.robillard@adm.idaho.gov, forrest.benedict@adm.idaho.gov, joseph.nelson@adm.idaho.gov, laura.gallivan@adm.idaho.gov, mike.gwinn@adm.idaho.gov, patrick.murphy@adm.idaho.gov, quinn.shea@adm.idaho.gov, thayne.pearson@adm.idaho.gov |  | PR-050-010 | 2022-02-03 | 9:30-10AM
29 | Verify Rebates posted in Cash Account |  |  | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Arvin Deleon-Guerrero or Sheri Jones | arvin.deleon-guerrero@adm.idaho.gov & sheri.jones@adm.idaho.gov |  | MF-260-070ZZ | 2022-02-03 | 10-11 AM
Note on J5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard

## AR Credit Monitoring
SIT 3 Scenario - AR Credit Monitoring
Agency:
SIT Week - Week 6 - 2/7 - 2/11
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | ALM SIT 3 Test ID# | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution Date | Window to Complete Script
1 | Finance Charge Code Setup | 2845 | 12021 | Receivables Manager | Reconcile accounts receivables & collections and assess late fees. | Assigned Agency | Genny Casiano | genny.casiano@adm.idaho.gov |  | MF-260-010 | 2022-02-07 | 8:45-10 AM
2 | Finance Charge Text Code Setup | 2846 | 12022 | Receivables Manager | Reconcile accounts receivables & collections and assess late fees. | Assigned Agency | Genny Casiano | genny.casiano@adm.idaho.gov |  | MF-260-010 | 2022-02-07 | 8:45-10 AM
3 | Run Finance Charge Initiation | 8680 | 12018 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Arvin Deleon-Gerrero or Sheri Jones | arvin.deleon-guerrero@adm.idaho.gov & sheri.jones@adm.idaho.gov |  | MF-260-030 | 2022-02-07 | 10 AM-2 PM
4 | Run Finance Charge Late Payment | 8681 | 12020 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Arvin Deleon-Gerrero or Sheri Jones | arvin.deleon-guerrero@adm.idaho.gov & sheri.jones@adm.idaho.gov |  | MF-260-120 | 2022-02-07 | 10 AM-2 PM
5 | Create an Invoice Write Off | 10995 | 12019 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Arvin Deleon-Gerrero or Sheri Jones | arvin.deleon-guerrero@adm.idaho.gov & sheri.jones@adm.idaho.gov |  | MF-260-120 | 2022-02-07 | 10 AM-2 PM
6 | Run Customer Statements | 10986 | 12023 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Arvin Deleon-Gerrero or Sheri Jones | arvin.deleon-guerrero@adm.idaho.gov & sheri.jones@adm.idaho.gov |  | MF-260-060 | 2022-02-08 | 8:45 - 11 AM
7 | Run Advanced Dunning Letter Selection | 11409 | 12024 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Arvin Deleon-Gerrero or Sheri Jones | arvin.deleon-guerrero@adm.idaho.gov & sheri.jones@adm.idaho.gov |  | MF-260-120 | 2022-02-08 | 8:45 - 11 AM
8 | Run Advanced Dunning Letter File Generation | 11410 | 12025 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Arvin Deleon-Gerrero or Sheri Jones | arvin.deleon-guerrero@adm.idaho.gov & sheri.jones@adm.idaho.gov |  | MF-260-120 | 2022-02-08 | 8:45 - 11 AM
9 | Run Company Aging Report | 11898 | 12027 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Arvin Deleon-Gerrero or Sheri Jones | arvin.deleon-guerrero@adm.idaho.gov & sheri.jones@adm.idaho.gov |  | MF-260-110 | 2022-02-08 | 8:45 - 11 AM
10 | Run Customer Aging Report | 11899 | 12028 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Arvin Deleon-Gerrero or Sheri Jones | arvin.deleon-guerrero@adm.idaho.gov & sheri.jones@adm.idaho.gov |  | MF-260-110 | 2022-02-08 | 1- 2PM
11 | Review Invoices Paid Late | 11896 | 12026 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Arvin Deleon-Gerrero or Sheri Jones | arvin.deleon-guerrero@adm.idaho.gov & sheri.jones@adm.idaho.gov |  | MF-260-110 | 2022-02-08 | 1- 2PM
Note on J5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard

## Svc Cntract Interagency Billing
SIT 3 Scenario - Service Contract Procure to Pay Interagency Billing
Agency:
SIT Week - Week 6 - 2/7 - 2/11
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Create Requisition for Service | 8323 | 11936 | Requester | Determines requirements & cost estimates for purchase of goods & services. Submits purchase requisition. | Assigned Agency | Laura Gallivan or Linda Edkins | linda.edkins@adm.idaho.gov or laura.gallivan@adm.idaho.gov |  | PR-020-010 | 2022-02-08 | 8:45-9:30 AM
2 | Approve Requisition | 8539 | 11929 | Approver | Approve transactions such as requisitions, purchase orders, solicitations, and journal entries. | Assigned Agency | Lvl 1 Chelsea Robillard Lvl 2 Lynn Christian Lvl 3 Genny Casiano | chelsea.robillard@adm.idaho.gov lynn.christian@adm.idaho.gov genny.casiano@adm.idaho.gov |  | PR-020-020 | 2022-02-08 | 9:30-10AM
3 | Identify Requistions to send to Sourcing Event | 2896 | 11934 | Buyer | Review requisitions & create purchase orders. Conduct market research & monitor vendor commitments. Approve vendor returns. | Assigned Agency | Laura Gallivan or Linda Edkins | linda.edkins@adm.idaho.gov or laura.gallivan@adm.idaho.gov |  | PR-020-020 | 2022-02-08 | 10-11AM
4 | Create Sourcing Event RFP | 7186 | 11949 | Sourcing Manager | Create souring events, evaluate supplier responses, and oversee selection & award of sourcing events. | Assigned Agency | Bob Morlan, Chelsea Robillard, Forrest Benedict, Joseph Nelson, Laura Gallivan, Mike Gwinn, Patrick Murphy, Quinn Shea, Thayne Pearson, or Valierie Bollinger | bob.morlan@adm.idaho.gov, chelsea.robillard@adm.idaho.gov, forrest.benedict@adm.idaho.gov, joseph.nelson@adm.idaho.gov, laura.gallivan@adm.idaho.gov, mike.gwinn@adm.idaho.gov, patrick.murphy@adm.idaho.gov, quinn.shea@adm.idaho.gov, thayne.pearson@adm.idaho.gov, valerie.bollinger@adm.idaho.gov |  | PR-030-020 | 2022-02-08 | 1-1:30PM
5 | Approve Sourcing Event to Post | 7191 | 11941 | Approver | Approve transactions such as requisitions, purchase orders, solicitations, and journal entries. | Assigned Agency | 0-99,999.99 Mike Gwinn, Chelsea Robillard, Valerie Bollinger 100,000.00-249,999.99 Mike Gwinn, Chelsea Robillard, Valerie Bollinger 250,000.00-9,999,999,999.99 Mike Gwinn, Chelsea Robillard, Valerie Bollinger | mike.gwinn@adm.idaho.gov chelsea.robillard@adm.idaho.gov valierie.bollinger@adm.idaho.gov |  | PR-030-010 | 2022-02-08 | 1:30-2PM
6 | Supplier Responds to Event | 1249 | 11944 | Supplier (Luma Team Member) |  | DOP | 0-99,999.99 Mike Gwinn, Chelsea Robillard, Valerie Bollinger 100,000.00-249,999.99 Mike Gwinn, Chelsea Robillard, Valerie Bollinger 250,000.00-9,999,999,999.99 Mike Gwinn, Chelsea Robillard, Valerie Bollinger | mike.gwinn@adm.idaho.gov chelsea.robillard@adm.idaho.gov valierie.bollinger@adm.idaho.gov |  | PR-030-020 | 2022-02-08 | 2-2:30PM
7 | Analyze and Award Suppler Responses | Refer to upload Template | 11952 | Sourcing Manager | Create souring events, evaluate supplier responses, and oversee selection & award of sourcing events. | Assigned Agency | Bob Morlan, Chelsea Robillard, Forrest Benedict, Joseph Nelson, Laura Gallivan, Mike Gwinn, Patrick Murphy, Quinn Shea, Thayne Pearson, or Valierie Bollinger | bob.morlan@adm.idaho.gov, chelsea.robillard@adm.idaho.gov, forrest.benedict@adm.idaho.gov, joseph.nelson@adm.idaho.gov, laura.gallivan@adm.idaho.gov, mike.gwinn@adm.idaho.gov, patrick.murphy@adm.idaho.gov, quinn.shea@adm.idaho.gov, thayne.pearson@adm.idaho.gov, valerie.bollinger@adm.idaho.gov |  | PR-030-050 | 2022-02-08 | 2:30-3PM
8 | Sourcing Event Award Approval | 7191 | 11947 | Approver | Approve transactions such as requisitions, purchase orders, solicitations, and journal entries. | Assigned Agency | 0-99,999.99 Mike Gwinn, Chelsea Robillard, Valerie Bollinger 100,000.00-249,999.99 Mike Gwinn, Chelsea Robillard, Valerie Bollinger 250,000.00-9,999,999,999.99 Mike Gwinn, Chelsea Robillard, Valerie Bollinger | mike.gwinn@adm.idaho.gov chelsea.robillard@adm.idaho.gov valierie.bollinger@adm.idaho.gov |  | PR-030-040 | 2022-02-08 | 3-3:30PM
9 | Create Contract - Create a Contract - Contract Tab | 7219 | 11942 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | Assigned Agency/DOP | Bob Morlan, Chelsea Robillard, Forrest Benedict, Joseph Nelson, Laura Gallivan, Mike Gwinn, Patrick Murphy, Quinn Shea, or Thayne Pearson, | bob.morlan@adm.idaho.gov, chelsea.robillard@adm.idaho.gov, forrest.benedict@adm.idaho.gov, joseph.nelson@adm.idaho.gov, laura.gallivan@adm.idaho.gov, mike.gwinn@adm.idaho.gov, patrick.murphy@adm.idaho.gov, quinn.shea@adm.idaho.gov, thayne.pearson@adm.idaho.gov |  | PR-040-010 | 2022-02-09 | 8:45 - 10:30AM
10 | Create Contract - Contract Draft - Articles Tab | 7204 | 11951 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | Assigned Agency/DOP | Bob Morlan, Chelsea Robillard, Forrest Benedict, Joseph Nelson, Laura Gallivan, Mike Gwinn, Patrick Murphy, Quinn Shea, or Thayne Pearson, | bob.morlan@adm.idaho.gov, chelsea.robillard@adm.idaho.gov, forrest.benedict@adm.idaho.gov, joseph.nelson@adm.idaho.gov, laura.gallivan@adm.idaho.gov, mike.gwinn@adm.idaho.gov, patrick.murphy@adm.idaho.gov, quinn.shea@adm.idaho.gov, thayne.pearson@adm.idaho.gov |  | PR-040-010 | 2022-02-09 | 8:45 - 10:30AM
11 | Create Contract - Contract Draft - Participants Tab | 2667 | 11950 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | Assigned Agency/DOP | Bob Morlan, Chelsea Robillard, Forrest Benedict, Joseph Nelson, Laura Gallivan, Mike Gwinn, Patrick Murphy, Quinn Shea, or Thayne Pearson, | bob.morlan@adm.idaho.gov, chelsea.robillard@adm.idaho.gov, forrest.benedict@adm.idaho.gov, joseph.nelson@adm.idaho.gov, laura.gallivan@adm.idaho.gov, mike.gwinn@adm.idaho.gov, patrick.murphy@adm.idaho.gov, quinn.shea@adm.idaho.gov, thayne.pearson@adm.idaho.gov |  | PR-040-010 | 2022-02-09 | 8:45 - 10:30AM
12 | Create Contract - Contract Draft - Lines Tab - Service | 3375 | 11948 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | Assigned Agency/DOP | Bob Morlan, Chelsea Robillard, Forrest Benedict, Joseph Nelson, Laura Gallivan, Mike Gwinn, Patrick Murphy, Quinn Shea, or Thayne Pearson, | bob.morlan@adm.idaho.gov, chelsea.robillard@adm.idaho.gov, forrest.benedict@adm.idaho.gov, joseph.nelson@adm.idaho.gov, laura.gallivan@adm.idaho.gov, mike.gwinn@adm.idaho.gov, patrick.murphy@adm.idaho.gov, quinn.shea@adm.idaho.gov, thayne.pearson@adm.idaho.gov |  | PR-040-010 | 2022-02-09 | 8:45 - 10:30AM
13 | Create Contract - Contract Draft - Contacts Tab | 3335 | 11940 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | Assigned Agency/DOP | Bob Morlan, Chelsea Robillard, Forrest Benedict, Joseph Nelson, Laura Gallivan, Mike Gwinn, Patrick Murphy, Quinn Shea, or Thayne Pearson, | bob.morlan@adm.idaho.gov, chelsea.robillard@adm.idaho.gov, forrest.benedict@adm.idaho.gov, joseph.nelson@adm.idaho.gov, laura.gallivan@adm.idaho.gov, mike.gwinn@adm.idaho.gov, patrick.murphy@adm.idaho.gov, quinn.shea@adm.idaho.gov, thayne.pearson@adm.idaho.gov |  | PR-040-010 | 2022-02-09 | 8:45 - 10:30AM
14 | Create Contract - Contract Draft - Releasing a Contract | 7203 | 11930 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | Assigned Agency/DOP | Bob Morlan, Chelsea Robillard, Forrest Benedict, Joseph Nelson, Laura Gallivan, Mike Gwinn, Patrick Murphy, Quinn Shea, or Thayne Pearson, | bob.morlan@adm.idaho.gov, chelsea.robillard@adm.idaho.gov, forrest.benedict@adm.idaho.gov, joseph.nelson@adm.idaho.gov, laura.gallivan@adm.idaho.gov, mike.gwinn@adm.idaho.gov, patrick.murphy@adm.idaho.gov, quinn.shea@adm.idaho.gov, thayne.pearson@adm.idaho.gov |  | PR-040-010 | 2022-02-09 | 8:45 - 10:30AM
16 | Contract Approval | 8353 | 11939 | Approver | Approve transactions such as requisitions, purchase orders, solicitations, and journal entries. | Assigned Agency | 0-99,999.99 Mike Gwinn, Chelsea Robillard, Valerie Bollinger 100,000.00-249,999.99 Mike Gwinn, Chelsea Robillard, Valerie Bollinger 250,000.00-9,999,999,999.99 Mike Gwinn, Chelsea Robillard, Valerie Bollinger | mike.gwinn@adm.idaho.gov chelsea.robillard@adm.idaho.gov valierie.bollinger@adm.idaho.gov |  | PR-040-010 | 2022-02-09 | 10:30-11AM
15 | Create Contract - Contract Draft - Activating a Contract | 7202 | 11931 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | Assigned Agency/DOP | Bob Morlan, Chelsea Robillard, Forrest Benedict, Joseph Nelson, Laura Gallivan, Mike Gwinn, Patrick Murphy, Quinn Shea, or Thayne Pearson, | bob.morlan@adm.idaho.gov, chelsea.robillard@adm.idaho.gov, forrest.benedict@adm.idaho.gov, joseph.nelson@adm.idaho.gov, laura.gallivan@adm.idaho.gov, mike.gwinn@adm.idaho.gov, patrick.murphy@adm.idaho.gov, quinn.shea@adm.idaho.gov, thayne.pearson@adm.idaho.gov |  | PR-040-010 | 2022-02-09 | 8:45 - 10:30AM
17 | Create Contract Invoice | 11459 | 11933 | Payables Invoice Processor | Process interface and XM files. Match payables invoices, and vendor list. Process payables payments. Generate 1099. | Assigned Agency | Sheri Jones | sheri.jones@adm.idaho.gov |  | MF-070-050 Enter a PO Invoice | 2022-02-09 | 1 - 1:30PM
18 | Approve Invoice | 11460 | 11938 | Payables Manager | Void & cancel payments. Reissue & mail warrants. Process period close. | Assigned Agency | Lynn Christian | Lynn.christian@adm.idaho.gov |  | MF-070-056 Invoice Approval Process | 2022-02-09 | 1:30 -3:30 PM
19 | Match Invoice | 11462 | 11946 | Payables Manager | Void & cancel payments. Reissue & mail warrants. Process period close. | Assigned Agency | Lynn Christian | Lynn.christian@adm.idaho.gov |  | MF-070-070 Match Invoices | 2022-02-09 | 1:30 -3:30 PM
20 | Process Payment for Invoice | 11442 | 11932 | Payables Manager | Void & cancel payments. Reissue & mail warrants. Process period close. | Assigned Agency | Lynn Christian | Lynn.christian@adm.idaho.gov |  | MF-070-100 Process Invoice Payments | 2022-02-09 | 1:30 -3:30 PM
21 | Create Interagency Billing - Basic | 8795 | 11945 | Intercompany Billing Specialist | Handle setup and processing of intercompany billing. | Assigned Agency | Arvin Deleon-Gerrero or Lynn Christian | arvin.deleon-guerrero@adm.idaho.gov & Lynn.christian@adm.idaho.gov |  | MF-260-030ZZ | 2022-02-10 | 8:45-9:30 AM
22 | Identify Unpaid Interagency Billings | 11536 | 11937 | Payables Invoice Processor | Process interface and XM files. Match payables invoices, and vendor list. Process payables payments. Generate 1099. | Assigned Agency | Sheri Jones | sheri.jones@adm.idaho.gov |  | MF-070-050 Enter a PO Invoice | 2022-02-10 | 9:30-10AM
23 | Reclassify Interagency Expenditure Coding (AP110 Distribution Changes on Paid Invoice) | 11624 | 11935 | Payables Invoice Processor | Process interface and XM files. Match payables invoices, and vendor list. Process payables payments. Generate 1099. | Assigned Agency | Sheri Jones | sheri.jones@adm.idaho.gov |  | MF-070-050 Enter a PO Invoice | 2022-02-10 | 10-11AM
24 | Settle an Interagency Billing | 8794 | 11943 | Intercompany Billing Specialist | Handle setup and processing of intercompany billing. | Assigned Agency | Arvin Deleon-Gerrero or Lynn Christian | arvin.deleon-guerrero@adm.idaho.gov & Lynn.christian@adm.idaho.gov |  | MF-260-030ZZ | 2022-02-10 | 1-1:30PM
Note on J5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard

## Cash Ledger Payment
SIT 3 Scenario - Cash Ledger Payment
Agency:
SIT Week - Week 7 - 2/14 -2/18
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Enter Cash Payment | Cash Payment Entry.xlsx | 12075 | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Arvin Deleon-Guerrero or Sheri Jones | arvin.deleon-guerrero@adm.idaho.gov & sheri.jones@adm.idaho.gov | Rotary/Site Draft, L Warrants |  | 2022-02-14 | 8:45 - 10 AM
1A | Record Cash Payment |  | 12525 | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Arvin Deleon-Guerrero or Sheri Jones | arvin.deleon-guerrero@adm.idaho.gov & sheri.jones@adm.idaho.gov |  |  | 2022-02-14 | 8:45 - 10 AM
2 | Approve Cash Payment | Cash Approve Cash Payment.xlsx | 12076 | Cash Manager | Manage all cash transactions. Review and update cash management policy as needed. | Assigned Agency | Genny Casiano or Kim Rau | genny.casiano@adm.idaho.gov or kim.rau@adm.idaho.gov |  |  | 2022-02-14 | 10 - 11:30 AM
3 | Cash Requirements | Cash Requirements.xlsx | 12077 | Payables Payment Processor | Perform Cash Requirements, Schedule Payments, Complete Payment Cycle | Assigned Agency | Arvin Deleon-Gerrero or Lynn Christian | arvin.deleon-guerrero@adm.idaho.gov & Lynn.christian@adm.idaho.gov |  | MF-070-100 Process Invoice Payments | 2022-02-14 | 1 - 2:30 PM
4 | Review Check in Cash | Cash Review Check in Cash Management.xlsx | 12078 | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Arvin Deleon-Guerrero or Sheri Jones | arvin.deleon-guerrero@adm.idaho.gov & sheri.jones@adm.idaho.gov | Redeem or Void then Review again |  | 2022-02-14 | 2:30 - 4 PM
5 | Journalize Distributions | Cash Journalize Cash Transaction.xlsx | 12079 | Cash Manager | Manage all cash transactions. Review and update cash management policy as needed. | Assigned Agency | Genny Casiano or Kim Rau | genny.casiano@adm.idaho.gov or kim.rau@adm.idaho.gov |  |  | 2022-02-15 | 8:45 - 10 AM
6 | Verify Results in Global Ledger Account Analysis |  | 12082 | Staff Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Lynn Christian or Sheri Jones | lynn.christian@adm.idaho.gov or sheri.jones@adm.idaho.gov |  |  | 2022-02-15 | 10 - 11:30 AM
7 | Optional Void Cash Payment for Status Updates | Cash Void Cash Payment.xlsx | 12080 | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Arvin Deleon-Guerrero or Sheri Jones | arvin.deleon-guerrero@adm.idaho.gov & sheri.jones@adm.idaho.gov |  |  | 2022-02-15 | 1 - 2:30 PM
8 | Optional Void Cash Payment: Payment Void Stop Pay Update | 12161 | 12161 | Payables Payment Processor | Perform Cash Requirements, Schedule Payments, Complete Payment Cycle | Assigned Agency | Arvin Deleon-Gerrero or Lynn Christian | arvin.deleon-guerrero@adm.idaho.gov & Lynn.christian@adm.idaho.gov |  |  | 2022-02-15 | 1 - 2:30 PM
9 | Optional Redeem Warrant for Status Updates | Cash Redeem Warrant.xlsx | 12081 | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Arvin Deleon-Guerrero or Sheri Jones | arvin.deleon-guerrero@adm.idaho.gov & sheri.jones@adm.idaho.gov |  |  | 2022-02-15 | 2:30 - 4 PM
Note on I4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard
Note on K5: Glenda Smith: Cash BPR's are not correct, do not reference.

## Interagency Billing to Settleme
SIT 3 Scenario - Interagency Billing to Settlement
Agency:
SIT Week - Week 7 - 2/14 -2/18
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Create Interagency Billing - Basic | 8795 | 11909 | Intercompany Billing Specialist | Handle setup and processing of intercompany billing. | Assigned Agency | Arvin Deleon-Gerrero or Lynn Christian | arvin.deleon-guerrero@adm.idaho.gov & Lynn.christian@adm.idaho.gov |  | MF-260-030ZZ | 2022-02-14 | 8:45-9:30 AM
2 | Identify Unpaid Interagency Billings | 11536 | 11907 | Payables Invoice Processor | Process interface and XM files. Match payables invoices, and vendor list. Process payables payments. Generate 1099. | Assigned Agency | Sheri Jones | sheri.jones@adm.idaho.gov |  | MF-070-050 Enter a PO Invoice | 2022-02-14 | 9:30 - 10:30 AM
3 | Reclassify Interagency Expenditure Coding (AP110 Distribution Changes on Paid Invoice) | 11624 | 11906 | Payables Invoice Processor | Process interface and XM files. Match payables invoices, and vendor list. Process payables payments. Generate 1099. | Assigned Agency | Sheri Jones | sheri.jones@adm.idaho.gov |  | MF-070-050 Enter a PO Invoice | 2022-02-14 | 10:30 -11:30 AM
4 | Settle an Interagency Billing | 8794 | 11908 | Intercompany Billing Specialist | Handle setup and processing of intercompany billing. | Assigned Agency | Arvin Deleon-Gerrero or Lynn Christian | arvin.deleon-guerrero@adm.idaho.gov & Lynn.christian@adm.idaho.gov |  | MF-260-030ZZ | 2022-02-14 | 1-1:30PM
Note on J5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard

## Nonstate Billing
SIT 3 Scenario - Non-State Billing_Master
Agency:
SIT Week - Week 7 - 2/14 -2/18
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 TEST ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Create Manual Batch Header | 10963 | 12456 | Billing Manager | Create and maintain bills for Accounts Receivable. | Assigned Agency | Arvin Deleon-Guerrero or Lynn Christian | arvin.deleon-guerrero@adm.idaho.gov & Lynn.christian@adm.idaho.gov | Interfaced Invoices, Recurring Invoices | MF-260-030 | 2022-02-14 | 8:45-9:30 AM
2 | Create Billing Invoice | 10962 | 12449 | Billing Manager | Create and maintain bills for Accounts Receivable. | Assigned Agency | Arvin Deleon-Guerrero or Lynn Christian | arvin.deleon-guerrero@adm.idaho.gov & Lynn.christian@adm.idaho.gov |  | MF-260-030 | 2022-02-14 | 9:30-10AM
3 | Create Credit Memo | 11562 | 12446 | Billing Manager | Create and maintain bills for Accounts Receivable. | Assigned Agency | Arvin Deleon-Guerrero or Lynn Christian | arvin.deleon-guerrero@adm.idaho.gov & Lynn.christian@adm.idaho.gov | Debit Memo | MF-260-100 | 2022-02-14 | 10-10:30 AM
4 | Approve Invoice Batch | 11603 | 12452 | Billing Manager | Create and maintain bills for Accounts Receivable. | Assigned Agency | Arvin Deleon-Guerrero or Lynn Christian | arvin.deleon-guerrero@adm.idaho.gov & Lynn.christian@adm.idaho.gov |  | MF-260-060 | 2022-02-14 | 10:30 - 11 AM
5 | Run Invoice Batch Release | 10966 | 12465 | Billing Manager | Create and maintain bills for Accounts Receivable. | Assigned Agency | Arvin Deleon-Guerrero or Lynn Christian | arvin.deleon-guerrero@adm.idaho.gov & Lynn.christian@adm.idaho.gov |  | MF-260-060 | 2022-02-14 | 1-1:30PM
6 | Run Invoice Register and Print | 3511 | 12459 | Billing Manager | Create and maintain bills for Accounts Receivable. | Assigned Agency | Arvin Deleon-Guerrero or Lynn Christian | arvin.deleon-guerrero@adm.idaho.gov & Lynn.christian@adm.idaho.gov |  | MF-260-060 | 2022-02-14 | 1:30-2PM
7 | Run Sub System Update (Interface Invoices to AR and Journalize) | 10965 | 12463 | Billing Manager | Create and maintain bills for Accounts Receivable. | Assigned Agency | Arvin Deleon-Guerrero or Lynn Christian | arvin.deleon-guerrero@adm.idaho.gov & Lynn.christian@adm.idaho.gov |  | MF-260-090 | 2022-02-14 | 2-2:30PM
8 | Create Invoice Batch in AR | 8661 | 12458 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Arvin Deleon-Gerrero or Sheri Jones | arvin.deleon-guerrero@adm.idaho.gov & sheri.jones@adm.idaho.gov |  | MF-260-060 | 2022-02-14 | 2:30-3PM
9 | Create Invoice in AR | 8660 | 12447 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Arvin Deleon-Gerrero or Sheri Jones | arvin.deleon-guerrero@adm.idaho.gov & sheri.jones@adm.idaho.gov | Interfaced Invoices | MF-260-030 | 2022-02-14 | 3 - 3:30 PM
10 | Create Credit Memo in AR | 2812 | 12451 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Arvin Deleon-Gerrero or Sheri Jones | arvin.deleon-guerrero@adm.idaho.gov & sheri.jones@adm.idaho.gov | Debit Memo | MF-260-050 | 2022-02-14 | 3:30 - 4 PM
11 | Approve AR Invoice (if not interfaced from BL) | 11603 | 12472 | Receivables Manager | Reconcile accounts receivables & collections and assess late fees. | Assigned Agency | Genny Casiano | genny.casiano@adm.idaho.gov |  | MF-260-ZZ | 2022-02-15 | 8:45-9:30 AM
12 | Run Journalize Preview | 8662 | 12466 | Receivables Manager | Reconcile accounts receivables & collections and assess late fees. | Assigned Agency | Genny Casiano | genny.casiano@adm.idaho.gov |  | MF-260-090 | 2022-02-15 | 9:30-10AM
13 | Run Journalize Distributions |  | 12464 | Receivables Manager | Reconcile accounts receivables & collections and assess late fees. | Assigned Agency | Genny Casiano | genny.casiano@adm.idaho.gov |  | MF-260-090 | 2022-02-15 | 10-10:30 AM
14 | Create Payment Batch | 8668 | 12457 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Arvin Deleon-Gerrero or Sheri Jones | arvin.deleon-guerrero@adm.idaho.gov & sheri.jones@adm.idaho.gov | Interfaced Payments | MF-260-070 | 2022-02-15 | 10:30 - 11 AM
15 | Create Customer Payment | 8666 | 12448 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Arvin Deleon-Gerrero or Sheri Jones | arvin.deleon-guerrero@adm.idaho.gov & sheri.jones@adm.idaho.gov | Interfaced Payments | MF-260-070 | 2022-02-15 | 1-1:30PM
16 | Create Payment Remittance | 11895 | 12470 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Arvin Deleon-Gerrero or Sheri Jones | arvin.deleon-guerrero@adm.idaho.gov & sheri.jones@adm.idaho.gov |  | MF-260-070 | 2022-02-15 | 1:30-2PM
17 | Create Non AR Cash Payment | 8673 | 12468 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Arvin Deleon-Gerrero or Sheri Jones | arvin.deleon-guerrero@adm.idaho.gov & sheri.jones@adm.idaho.gov | Interfaced Payments | MF-260-070 | 2022-02-15 | 2-2:30PM
18 | Apply Payment to Invoice | 8669 | 12460 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Arvin Deleon-Gerrero or Sheri Jones | arvin.deleon-guerrero@adm.idaho.gov & sheri.jones@adm.idaho.gov | Automatic Cash Application | MF-260-080 | 2022-02-15 | 2:30-3PM
19 | Apply Credit Memo to Invoice | 2513 | 12469 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Arvin Deleon-Gerrero or Sheri Jones | arvin.deleon-guerrero@adm.idaho.gov & sheri.jones@adm.idaho.gov | Automatic Memo Application | MF-260-100 | 2022-02-15 | 3 - 3:30 PM
20 | Approve Payment Batch | 11603 | 12473 | Receivables Manager | Reconcile accounts receivables & collections and assess late fees. | Treasury | Genny Casiano | genny.casiano@adm.idaho.gov |  | MF-260-ZZ | 2022-02-15 | 3:30 - 4 PM
21 | Create Payment Application Reversal | 11064 | 12450 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Arvin Deleon-Gerrero or Sheri Jones | arvin.deleon-guerrero@adm.idaho.gov & sheri.jones@adm.idaho.gov |  | MF-260-ZZ | 2022-02-16 | 8:45-9:30 AM
22 | Run Application Reversal Creation | 11065 | 12455 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Arvin Deleon-Gerrero or Sheri Jones | arvin.deleon-guerrero@adm.idaho.gov & sheri.jones@adm.idaho.gov |  | MF-260-ZZ | 2022-02-16 | 9:30-10AM
23 | Application Close | 8670 | 12462 | Receivables Manager | Reconcile accounts receivables & collections and assess late fees. | Assigned Agency | Genny Casiano | genny.casiano@adm.idaho.gov |  | MF-260-130 | 2022-02-16 | 10-10:30 AM
24 | Run Journalize Preview | 8671 | 12467 | Receivables Manager | Reconcile accounts receivables & collections and assess late fees. | Assigned Agency | Genny Casiano | genny.casiano@adm.idaho.gov |  | MF-260-090 | 2022-02-16 | 10:30 - 11 AM
25 | Run Journalize Distributions | 8672 | 12474 | Receivables Manager | Reconcile accounts receivables & collections and assess late fees. | Assigned Agency | Genny Casiano | genny.casiano@adm.idaho.gov |  | MF-260-090 | 2022-02-16 | 1-1:30PM
26 | Reconcile AR module to GL balance (Account Analysis/Reports) | 11672 | 12453 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate, and update allocations. | Assigned Agency | Lynn Christian or Sheri Jones | lynn.christian@adm.idaho.gov or sheri.jones@adm.idaho.gov |  | MF-260-090 | 2022-02-16 | 1:30-2PM
27 | View Cash Fund Balance | Cash Fund Balance.lxsx - maybe in ALM already |  | Financial Viewer | View-only access to key financial workstreams and structures, such as Chart of Accounts, financial reports, and financial transaction data. | Assigned Agency | Genny Casiano | genny.casiano@adm.idaho.gov |  | MF-260-090 | 2022-02-16 | 2-2:30PM
28 | Create Return to Maker Payment | 11120 | 12454 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Arvin Deleon-Gerrero or Sheri Jones | arvin.deleon-guerrero@adm.idaho.gov & sheri.jones@adm.idaho.gov |  | MF-260-ZZ | 2022-02-16 | 2:30-3PM
29 | Release Return to Maker Payment | 11124 | 12461 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Arvin Deleon-Gerrero or Sheri Jones | arvin.deleon-guerrero@adm.idaho.gov & sheri.jones@adm.idaho.gov |  | MF-260-ZZ | 2022-02-16 | 3 - 3:30 PM
30 | Create Payment Reversal | 11064 | 12475 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Arvin Deleon-Gerrero or Sheri Jones | arvin.deleon-guerrero@adm.idaho.gov & sheri.jones@adm.idaho.gov |  | MF-260-ZZ | 2022-02-16 | 3:30 - 4 PM
31 | Run Application Reversal Creation | 11065 | 12476 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Arvin Deleon-Gerrero or Sheri Jones | arvin.deleon-guerrero@adm.idaho.gov & sheri.jones@adm.idaho.gov |  | MF-260-ZZ | 2022-02-17 | 8:45-9:30 AM
Note on J5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard

## Procure to Pay Vendor Mgt Voids
SIT 3 Scenario - Procure to Pay with Void and Vendor Update
Agency:
SIT Week - Week 7 - 2/14 -2/18
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | Luma Role (role switcher) | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Create Requisition - Special | 8324 | Requester | Assigned Agency | Laura Gallivan or Linda Edkins | linda.edkins@adm.idaho.gov or laura.gallivan@adm.idaho.gov |  | PR-020-010 | 2022-02-14 | 8:45-9:30 AM
2 | Approve Requisition | 8539 | Approver | Assigned Agency | Lvl 1 Chelsea Robillard Lvl 2 Lynn Christian Lvl 3 Genny Casiano | chelsea.robillard@adm.idaho.gov lynn.christian@adm.idaho.gov genny.casiano@adm.idaho.gov | Requisition not approved | PR-010-060 | 2022-02-14 | 9:30-10AM
3 | Create Purchase Order | 8170 | Buyer | Assigned Agency | Laura Gallivan or Linda Edkins | linda.edkins@adm.idaho.gov or laura.gallivan@adm.idaho.gov |  | PR-050-040 | 2022-02-14 | 10-10:30 AM
4 | Receive Purchase Order | 4587 | Receiver | Assigned Agency | Laura Gallivan or Linda Edkins | linda.edkins@adm.idaho.gov or laura.gallivan@adm.idaho.gov |  | PR-050-070 | 2022-02-14 | 10:30 - 11 AM
5 | Create Invoice | 11519 | Payables Invoice Processor | Assigned Agency | Sheri Jones | sheri.jones@adm.idaho.gov |  | MF-070-050 Enter a PO Invoice | 2022-02-14 | 1-1:30PM
6 | Approve Invoice | 11520 | Approver | Assigned Agency | Lvl 1 Arvin Deleon Guerrero, Lynn Christian or Genny Casiano Lvl 2 Genny Casiano or Kim Rau | arvin.deleon-guerrero@adm.idaho.gov lynn.christian@adm.idaho.gov genny.casiano@adm.idaho.gov kim.rau@adm.idaho.gov |  | MF-070-056 Invoice Approval Process | 2022-02-14 | 1:30-2PM
7 | Match Invoice | 11458 | Payables Manager | Assigned Agency | Lynn Christian | Lynn.christian@adm.idaho.gov |  | MF-070-070 Match Invoices | 2022-02-14 | 2-2:30PM
8 | Process Payment for Invoice | 11442 | Payables Manager | Assigned Agency | Lynn Christian | Lynn.christian@adm.idaho.gov |  | MF-070-100 Process Invoice Payments | 2022-02-14 | 2:30-3PM
9 | Journalize | 11440 | Payables Manager |  | Lynn Christian | Lynn.christian@adm.idaho.gov |  | MF-070-110 Journalize AP Distributions | 2022-02-14 | 3 - 3:30 PM
10 | Void Payment | 12080 | Cash Accountant | SCO | Arvin Deleon-Guerrero or Sheri Jones | arvin.deleon-guerrero@adm.idaho.gov & sheri.jones@adm.idaho.gov |  | MF-200-060 Void Cash Transactions | 2022-02-14 | 3:30 - 4 PM
11 | Cancel Invoice | 11523 | Payables Manager | Assigned Agency | Lynn Christian | Lynn.christian@adm.idaho.gov |  | MF-070-050 Enter a PO Invoice | 2022-02-15 | 8:45-9:30 AM
12 | Request a new vendor | 11524 | Payables Invoice Processor | Assigned Agency | Sheri Jones | sheri.jones@adm.idaho.gov |  | PR-040-030 Create and Maintain Vendor | 2022-02-15 | 9:30-10AM
13 | Approve and setup new vendor | 11525 - Only SCO staff can do this | Approver | SCO | Lvl 1 Arvin Deleon Guerrero, Lynn Christian or Genny Casiano Lvl 2 Genny Casiano or Kim Rau | arvin.deleon-guerrero@adm.idaho.gov lynn.christian@adm.idaho.gov genny.casiano@adm.idaho.gov kim.rau@adm.idaho.gov | Disapprove vendor | PR-040-030 Create and Maintain Vendor | 2022-02-15 | 10-10:30 AM
14 | Create Invoice | 11519 | Payables Invoice Processor | Assigned Agency | Sheri Jones | sheri.jones@adm.idaho.gov |  | MF-070-050 Enter a PO Invoice | 2022-02-15 | 10:30 - 11 AM
15 | Approve Invoice | 11520 | Approver | Assigned Agency | Lvl 1 Arvin Deleon Guerrero, Lynn Christian or Genny Casiano Lvl 2 Genny Casiano or Kim Rau | arvin.deleon-guerrero@adm.idaho.gov lynn.christian@adm.idaho.gov genny.casiano@adm.idaho.gov kim.rau@adm.idaho.gov |  | MF-070-056 Invoice Approval Process | 2022-02-15 | 1-1:30PM
16 | Match Invoice | 11522 | Payables Invoice Processor | Assigned Agency | Sheri Jones | sheri.jones@adm.idaho.gov |  | MF-070-070 Match Invoices | 2022-02-15 | 1:30-2PM
17 | Process Payment for Invoice | 11442 | Payables Manager | Assigned Agency | Lynn Christian | Lynn.christian@adm.idaho.gov |  | MF-070-100 Process Invoice Payments | 2022-02-15 | 2-2:30PM
18 | Post Transactions - Journalize | 11440 | Payables Manager | Assigned Agency | Lynn Christian | Lynn.christian@adm.idaho.gov |  | MF-070-110 Journalize AP Distributions | 2022-02-15 | 2:30-3PM
19 | Cash Ledger Journalize | 12079 | Cash Manager | Assigned Agency | Genny Casiano & Kim Rau | genny.casiano@adm.idaho.gov or kim.rau@adm.idaho.gov |  | MF-200-050 Reconcile Payments Payables and Disbursements | 2022-02-15 | 3 - 3:30 PM
20 | Verify Voided Payables Checks | 12153 | Cash Accountant | Assigned Agency | Arvin Deleon-Guerrero or Sheri Jones | arvin.deleon-guerrero@adm.idaho.gov & sheri.jones@adm.idaho.gov |  | MF-200-060 Void Cash Transactions | 2022-02-15 | 3:30 - 4 PM
21 | View Fund Balance | Cash Fund Balance.xlsx (in ALM?)(in Cash Deposit to Revenue Scenario) | Cash Accountant | Assigned Agency | Arvin Deleon-Guerrero or Sheri Jones | arvin.deleon-guerrero@adm.idaho.gov & sheri.jones@adm.idaho.gov |  | MF-200-050 Reconcile Payments Payables and Disbursements | 2022-02-16 | 8:45-9:30 AM
22 | Comparative report from Birst |  | Cash Accountant | Assigned Agency | Arvin Deleon-Guerrero or Sheri Jones | arvin.deleon-guerrero@adm.idaho.gov & sheri.jones@adm.idaho.gov |  | MF-200-ZZ | 2022-02-16 | 9:30-10AM
23 | Cash Revenue Daily Report - Birst |  | Cash Manager | Assigned Agency | Genny Casiano & Kim Rau | genny.casiano@adm.idaho.gov or kim.rau@adm.idaho.gov |  | MF-200-ZZ | 2022-02-16 | 10-10:30 AM
Note on H5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard

## Vendor Refund
SIT 3 Scenario - Vendor Refund
Agency:
SIT 3 Week - Week 7 - 2/14 - 2/18
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Invoice Entry - Non-PO | 12444 | 12444 | Payables Invoice Processor |  |  | Sheri Jones | sheri.jones@adm.idaho.gov |  | MF-070-060 Enter Non-PO Invoice | 2022-02-15 | 8:45-9:30 AM
2 | Invoice Approver | 12445 | 12445 | Approver |  |  | Lvl 1 Arvin Deleon Guerrero, Lynn Christian or Genny Casiano Lvl 2 Genny Casiano or Kim Rau | arvin.deleon-guerrero@adm.idaho.gov lynn.christian@adm.idaho.gov genny.casiano@adm.idaho.gov kim.rau@adm.idaho.gov |  | MF-070-056 Invoice Approval Process | 2022-02-15 | 9:30-10AM
3 | Cash Requirements | 12442 | 12442 | Payables Manager |  |  | Lynn Christian | Lynn.christian@adm.idaho.gov |  | MF-070-100 Process Invoice Payments | 2022-02-15 | 10-10:30 AM
4 | Journalize | 12443 | 12443 | Payables Manager |  |  | Lynn Christian | Lynn.christian@adm.idaho.gov |  | MF-070-110 Journalize AP Distributions | 2022-02-15 | 10:30 - 11 AM
5 | Create Cash Receipts |  | TBD | Cash Accountant |  |  | Arvin Deleon-Guerrero or Sheri Jones | arvin.deleon-guerrero@adm.idaho.gov & sheri.jones@adm.idaho.gov |  |  | 2022-02-15 | 1-1:30PM
6 | Approve Cash Receipt |  | TBD | Approver |  |  | Lvl 1 Arvin Deleon Guerrero, Lynn Christian or Genny Casiano Lvl 2 Genny Casiano or Kim Rau | arvin.deleon-guerrero@adm.idaho.gov lynn.christian@adm.idaho.gov genny.casiano@adm.idaho.gov kim.rau@adm.idaho.gov |  |  | 2022-02-15 | 1:30-2PM
7 | Cash Receipt Final Release |  | TBD | Cash Manager |  |  | Genny Casiano & Kim Rau | genny.casiano@adm.idaho.gov or kim.rau@adm.idaho.gov |  |  | 2022-02-15 | 2-2:30PM
8 | Jornalize Cash Transactions |  | TBD | Staff Accountant |  |  | Lynn Christian or Sheri Jones | lynn.christian@adm.idaho.gov or sheri.jones@adm.idaho.gov |  |  | 2022-02-15 | 2:30-3PM
9 | Post GL Journals |  | TBD | Staff Accountant |  |  | Lynn Christian or Sheri Jones | lynn.christian@adm.idaho.gov or sheri.jones@adm.idaho.gov |  |  | 2022-02-15 | 3 - 3:30 PM
10 | Adjust Reportable Income | 11837 | 12047 | Payables Manager | Void & cancel payments. Reissue & mail warrants. Process period close. | Assigned Agency | Lynn Christian | Lynn.christian@adm.idaho.gov |  | MF-070-020 Maintain Invoice | 2022-02-15 | 3:30 - 4 PM
Note on J5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard

## Cash Managem Deposit to Revenue
SIT 3 Scenario - Deposit to Revenue
Agency:
SIT Week - Week 8 - 2/21/ - 2/25
Sequence | Script ID | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 BPR PROCESSES | Execution date | Window to Complete Script
1 | Cash Fund Balance - Before Processing Transactions | TBD | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Arvin Deleon-Guerrero or Sheri Jones | arvin.deleon-guerrero@adm.idaho.gov & sheri.jones@adm.idaho.gov |  |  | 2022-02-22 | 8:45-9:30 AM
2 | Create Cash Receipt | TBD | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Arvin Deleon-Guerrero or Sheri Jones | arvin.deleon-guerrero@adm.idaho.gov & sheri.jones@adm.idaho.gov |  |  | 2022-02-22 | 9:30-10AM
3 | Approve Cash Receipt (Approve Cash Transactions in InBasket) | TBD | Cash Manager | Manage all cash transactions. Review and update cash management policy as needed. | Assigned Agency | Genny Casiano & Kim Rau | genny.casiano@adm.idaho.gov or kim.rau@adm.idaho.gov |  |  | 2022-02-22 | 10-11AM
4 | Cash Receipt Final Release (Approve Cash Transactions in InBasket) | TBD | Cash Manager | Manage all cash transactions. Review and update cash management policy as needed. | 150 | Genny Casiano & Kim Rau | genny.casiano@adm.idaho.gov or kim.rau@adm.idaho.gov |  |  | 2022-02-22 | 1-1:30PM
5 | Process NSF | TBD | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Arvin Deleon-Guerrero or Sheri Jones | arvin.deleon-guerrero@adm.idaho.gov & sheri.jones@adm.idaho.gov |  |  | 2022-02-22 | 1:30-2PM
6 | Approve NSF (Approve Cash Transactions in InBasket) | TBD | Cash Manager | Manage all cash transactions. Review and update cash management policy as needed. | Assigned Agency | Genny Casiano & Kim Rau | genny.casiano@adm.idaho.gov or kim.rau@adm.idaho.gov |  |  | 2022-02-22 | 2-2:30PM
7 | NSF Final Release (Approve Cash Transactions in InBasket) | TBD | Cash Manager | Manage all cash transactions. Review and update cash management policy as needed. | 150 | Genny Casiano & Kim Rau | genny.casiano@adm.idaho.gov or kim.rau@adm.idaho.gov |  |  | 2022-02-22 | 2:30-3PM
8 | Reclass From Suspense: No Customer (Cash Receipt Transfer) | TBD | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Arvin Deleon-Guerrero or Sheri Jones | arvin.deleon-guerrero@adm.idaho.gov & sheri.jones@adm.idaho.gov |  |  | 2022-02-22 | 3-3:30PM
9 | Reclass From Suspense Customer (Go to AR Scenario) | TBD | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Arvin Deleon-Gerrero or Sheri Jones | arvin.deleon-guerrero@adm.idaho.gov & sheri.jones@adm.idaho.gov | Process under development. |  | 2022-02-23 | 8:45-9:30 AM
10 | Operating Transfer (Cash Ledger Transaction Transfer) | TBD | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Arvin Deleon-Guerrero or Sheri Jones | arvin.deleon-guerrero@adm.idaho.gov & sheri.jones@adm.idaho.gov |  |  | 2022-02-23 | 9:30-10AM
11 | Statutory Transfer (Cash Ledger Transaction Transfer) | TBD | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Arvin Deleon-Guerrero or Sheri Jones | arvin.deleon-guerrero@adm.idaho.gov & sheri.jones@adm.idaho.gov |  |  | 2022-02-23 | 10-11AM
12 | Approve Cash Transfer (Approve Cash Transactions in InBasket) | TBD | Cash Manager | Manage all cash transactions. Review and update cash management policy as needed. | Assigned Agency | Genny Casiano & Kim Rau | genny.casiano@adm.idaho.gov or kim.rau@adm.idaho.gov |  |  | 2022-02-23 | 1-1:30PM
13 | Cash Fund Balance - After Processing Transactions | TBD | Cash Manager | Manage all cash transactions. Review and update cash management policy as needed. | Assigned Agency | Genny Casiano & Kim Rau | genny.casiano@adm.idaho.gov or kim.rau@adm.idaho.gov |  |  | 2022-02-23 | 1:30-2PM
14 | Journalize Cash Transactions | TBD | Cash Manager | Manage all cash transactions. Review and update cash management policy as needed. | Assigned Agency | Genny Casiano & Kim Rau | genny.casiano@adm.idaho.gov or kim.rau@adm.idaho.gov |  |  | 2022-02-23 | 2-2:30PM
15 | Post GL Journals | TBD | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate, and update allocations. | Assigned Agency | Lynn Christian or Sheri Jones | lynn.christian@adm.idaho.gov or sheri.jones@adm.idaho.gov | Check for autopost |  | 2022-02-23 | 2:30-3PM
16 | Review Global Ledger for Transactions Processed | TBD | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate, and update allocations. | Assigned Agency | Lynn Christian or Sheri Jones | lynn.christian@adm.idaho.gov or sheri.jones@adm.idaho.gov |  |  | 2022-02-23 | 3-3:30PM
Note on I5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard

## Global Ledger Entries and Analy
SIT 3 Scenario - Global Legder Processing and Analysis
Agency:
SIT Week - Week 8 - 2/21/ - 2/25
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Create a Front-End Split Journal Entry (Front End Split Projects Only) | Refer to Upload Template | 12154 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Lynn Christian or Sheri Jones | lynn.christian@adm.idaho.gov or sheri.jones@adm.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-010 | 2022-02-23 | 8:45-9:30 AM
2 | Create a Journal Entry | Refer to Upload Template | 11668 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Lynn Christian or Sheri Jones | lynn.christian@adm.idaho.gov or sheri.jones@adm.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-010 | 2022-02-23 | 9:30-10AM
3 | Approve a Journal Entry | Refer to Upload Template | 11669 | Approver | Approve transactions such as requisitions, purchase orders, solicitation & journal entries. | Assigned Agency | Lvl 1 Arvin Deleon Guerrero, Lynn Christian or Genny Casiano Lvl 2 Genny Casiano or Kim Rau | arvin.deleon-guerrero@adm.idaho.gov lynn.christian@adm.idaho.gov genny.casiano@adm.idaho.gov kim.rau@adm.idaho.gov |  | MF-025-060 | 2022-02-23 | 10-11AM
4 | Create a Journal Entry from an Existing Journal | Refer to Upload Template | 11671 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Lynn Christian or Sheri Jones | lynn.christian@adm.idaho.gov or sheri.jones@adm.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-010 | 2022-02-23 | 1-1:30PM
5 | Create a Journal Entry from a Template | Refer to Upload Template | 11670 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Lynn Christian or Sheri Jones | lynn.christian@adm.idaho.gov or sheri.jones@adm.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-010 | 2022-02-23 | 1:30-2PM
6 | Create a Recurring Journal | Refer to Upload Template | 11673 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Lynn Christian or Sheri Jones | lynn.christian@adm.idaho.gov or sheri.jones@adm.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-020 | 2022-02-23 | 2-2:30PM
7 | Journalize a Recurring Journal Entry | Refer to Upload Template | 12155 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Lynn Christian or Sheri Jones | lynn.christian@adm.idaho.gov or sheri.jones@adm.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-030 | 2022-02-23 | 2:30-3PM
8 | Post Multiple Journal Entries | Refer to Upload Template | 12156 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Lynn Christian or Sheri Jones | lynn.christian@adm.idaho.gov or sheri.jones@adm.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-23 | 3-3:30PM
9 | Post Journals from Subsystems | Refer to Upload Template | 12157 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Lynn Christian or Sheri Jones | lynn.christian@adm.idaho.gov or sheri.jones@adm.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-050 | 2022-02-24 | 8:45-9:30 AM
10 | Validate (here) Reconcile (close) Subsystems to the General Ledger | Bill will put these scripts here and in close scenario | TBD | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Lynn Christian or Sheri Jones | lynn.christian@adm.idaho.gov or sheri.jones@adm.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-24 | 9:30-10AM
11 | Analyze Global Ledger Totals | Refer to Upload Template | 12158 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Lynn Christian or Sheri Jones | lynn.christian@adm.idaho.gov or sheri.jones@adm.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-24 | 10-11AM
12 | Perform Account Analysis | Refer to Upload Template | 11672 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Lynn Christian or Sheri Jones | lynn.christian@adm.idaho.gov or sheri.jones@adm.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-24 | 1-1:30PM
13 | Perform Fund Analysis | Refer to Upload Template | 12159 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Lynn Christian or Sheri Jones | lynn.christian@adm.idaho.gov or sheri.jones@adm.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-24 | 1:30-2PM
14 | Perform Organizational Unit Analysis | Refer to Upload Template | 12160 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Lynn Christian or Sheri Jones | lynn.christian@adm.idaho.gov or sheri.jones@adm.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-24 | 2-2:30PM
15 | View Transactions by Entity-Account | Refer to Upload Template | 11674 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Lynn Christian or Sheri Jones | lynn.christian@adm.idaho.gov or sheri.jones@adm.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-25 | 9- 9:30 AM
16 | BIRST/BI/CSF Analytic Reporting |  | TBD | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Lynn Christian or Sheri Jones | lynn.christian@adm.idaho.gov or sheri.jones@adm.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-25 | 9:30 - 10 AM
17 | Evaluate Encumbrances | Placeholder - Judy and Bill (and Eileen/Cathy) are working on script for this; will have this week (12/23/21) | TBD | Staff Accountant |  | Assigned Agency | Lynn Christian or Sheri Jones | lynn.christian@adm.idaho.gov or sheri.jones@adm.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-25 | 10 - 11 AM
Note on J5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard

## Punchout Request to Payment
SIT 3 Scenario - Punchout Request to Payment
Agency:
SIT Week - Week 8 - 2/21 - 2/25
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Create Punchout Requisition using RSS | 3501 | 11924 | Requester | Determines requirements & cost estimates for purchase of goods & services. Submits purchase requisition. | Assigned Agency | Laura Gallivan or Linda Edkins | linda.edkins@adm.idaho.gov or laura.gallivan@adm.idaho.gov |  | PR-020-010 | 2022-02-22 | 8:45-9:30 AM
2 | Approve Requisition | 8539 | 11925 | Approver | Approve transactions such as requisitions, purchase orders, solicitation & journal entries. | Assigned Agency | Lvl 1 Chelsea Robillard Lvl 2 Lynn Christian Lvl 3 Genny Casiano | chelsea.robillard@adm.idaho.gov lynn.christian@adm.idaho.gov genny.casiano@adm.idaho.gov | Deny Requisition - add note - need more information Approve Requisition | PR-010-060 | 2022-02-22 | 9:30-10AM
3 | Locate Punchout PO | Refer to Upload template | 12034 | Requester |  |  | Laura Gallivan or Linda Edkins | linda.edkins@adm.idaho.gov or laura.gallivan@adm.idaho.gov |  | PR-050-040 | 2022-02-22 | 10-11AM
4 | Review Punchout PO | Refer to Upload template | 11927 | Buyer | Review requisitions & create purchase orders. Conduct market research & monitor vendor commitments. Approve vendor returns. | Assigned Agency | Laura Gallivan or Linda Edkins | linda.edkins@adm.idaho.gov or laura.gallivan@adm.idaho.gov | This will be a review of schedule job creating PO. Other variations would be manual creation, or Job run creation submitted as needed. | PR-050-040 | 2022-02-22 | 1-1:30PM
5 | Review Punchout Receipt | Refer to Upload template | 11928 | Receiver | Receive and inspect incoming goods. Pick items for shipment/transfer. Dispose of items. Vendor returns. Document variances. | Assigned Agency | Laura Gallivan or Linda Edkins | linda.edkins@adm.idaho.gov or laura.gallivan@adm.idaho.gov | Manual release of receipt vs. auto release | PR-050-070 | 2022-02-22 | 1:30-2PM
6 | Review Punchout Invoice | 11610 | 11922 | Payables Invoice Processor | Processes interface and XM files. Match Payables invoices. Manages vendor list. Processes Payables payments. Generates 1099. | Assigned Agency | Sheri Jones | sheri.jones@adm.idaho.gov |  | MF-070-050 Enter a PO Invoice | 2022-02-22 | 2-2:30PM
7 | Approve Invoice | 11611 | 11923 | Approver |  |  | Lvl 1 Arvin Deleon Guerrero, Lynn Christian or Genny Casiano Lvl 2 Genny Casiano or Kim Rau | arvin.deleon-guerrero@adm.idaho.gov lynn.christian@adm.idaho.gov genny.casiano@adm.idaho.gov kim.rau@adm.idaho.gov |  | MF-070-056 Invoice Approval Process | 2022-02-22 | 2:30-3PM
8 | Match Invoice | 11613 | 11926 | Payables Manager | Void & cancel payments, reissue & mail warrants. Process period close. | Assigned Agency | Lynn Christian | Lynn.christian@adm.idaho.gov |  | MF-070-070 Match Invoices | 2022-02-22 | 3-3:30PM
9 | Process Invoice for Payment | 11442 | 11921 | Payables Manager | Void & cancel payments, reissue & mail warrants. Process period close. | Assigned Agency | Lynn Christian | Lynn.christian@adm.idaho.gov |  | MF-070-100 Process Invoice Payments | 2022-02-22 | 3:30 - 4 PM
Note on J5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard

## Month End
NOTE: The Month End Close Process Scenario testing will be coordinated with the assigned Agencies and executed one time during UAT.
SIT 3 Scenario - Month End Close Process
Agency:
SIT Week - (dates)
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Close Purchasing: Resolve all Buyer & Invoice Messages | Refer to Upload Template | 12140 | Purchasing Manager | Review requisitions & sourcing event requests. Review purchase requirement. Assign buyers and approve method of purchase. | Assigned Agency | Lynn Christian | Lynn.christian@adm.idaho.gov |  | PR-050-090 Determine Inventory Strategy and Approach | 2022-03-01 | All Day Testing
2 | Close Purchasing: Received Not Invoiced Report | 3005 |  | Purchasing Manager | Review requisitions & sourcing event requests. Review purchase requirement. Assign buyers and approve method of purchase. | Assigned Agency | Lynn Christian | Lynn.christian@adm.idaho.gov |  | PR-050-090 Determine Inventory Strategy and Approach | 2022-03-01 | All Day Testing
3 | Close Purchasing: Matched, Not Received Report | 3003 |  | Purchasing Manager | Review requisitions & sourcing event requests. Review purchase requirement. Assign buyers and approve method of purchase. | Assigned Agency | Lynn Christian | Lynn.christian@adm.idaho.gov |  | PR-050-090 Determine Inventory Strategy and Approach | 2022-03-01 | All Day Testing
4 | Close Purchasing: Invoiced, Not Received Closing | 3002 |  | Purchasing Manager | Review requisitions & sourcing event requests. Review purchase requirement. Assign buyers and approve method of purchase. | Assigned Agency | Lynn Christian | Lynn.christian@adm.idaho.gov |  | PR-050-090 Determine Inventory Strategy and Approach | 2022-03-01 | All Day Testing
5 | Close Purchasing: Close Purchase Order Header | 3001 |  | Purchasing Manager | Review requisitions & sourcing event requests. Review purchase requirement. Assign buyers and approve method of purchase. | LUMA | Lynn Christian | Lynn.christian@adm.idaho.gov |  | MF-030-050 Close Purchase Order | 2022-03-01 | All Day Testing
6 | Close Purchasing: Purchase System Close | 3004 |  | Purchasing Manager | Review requisitions & sourcing event requests. Review purchase requirement. Assign buyers and approve method of purchase. | LUMA | Lynn Christian | Lynn.christian@adm.idaho.gov |  | MF-030-050 Close Purchase Order | 2022-03-01 | All Day Testing
7 | Close Payables | 11441 - just the close steps not all the reports leading up to this |  | Payables Manager | Void & cancel payments. Reissue & mail warrants. Process period close. | Assigned Agency | Lynn Christian | Lynn.christian@adm.idaho.gov |  | MF-070-120 Perform AP Period End Close / MF-030-070 Close Payables | 2022-03-01 | All Day Testing
8 | Close Biling - Recurring Invoice Creation | Billing > RunProcesses > Create RecurringInvoices |  | Billing Manager | Create and maintain bills for Accounts Receivable. | Assigned Agency | Arvin Deleon-Guerrero or Lynn Christian | arvin.deleon-guerrero@adm.idaho.gov & Lynn.christian@adm.idaho.gov |  | MF-030-080 Close Billing | 2022-03-01 | All Day Testing
9 | Close Billing - Invoice Batch Release | Billing Manager > Processing > Create Billing Processes > Invoice Batch Release |  | Billing Manager | Create and maintain bills for Accounts Receivable. | Assigned Agency | Arvin Deleon-Guerrero or Lynn Christian | arvin.deleon-guerrero@adm.idaho.gov & Lynn.christian@adm.idaho.gov |  |  | 2022-03-01 | All Day Testing
10 | Close Billing - Invoice Verification Report | Billing > RunProcesses > Create BillingProcess > Invoice VerificationReport |  | Billing Manager | Create and maintain bills for Accounts Receivable. | Assigned Agency | Arvin Deleon-Guerrero or Lynn Christian | arvin.deleon-guerrero@adm.idaho.gov & Lynn.christian@adm.idaho.gov |  |  | 2022-03-01 | All Day Testing
11 | Close Billing - Invoice and Register Print | Billing > RunProcesses > Create BillingProcess > Invoice and Register Print |  | Billing Manager | Create and maintain bills for Accounts Receivable. | Assigned Agency | Arvin Deleon-Guerrero or Lynn Christian | arvin.deleon-guerrero@adm.idaho.gov & Lynn.christian@adm.idaho.gov |  |  | 2022-03-01 | All Day Testing
12 | Close Billig - Sub-system Update | Billing > RunProcesses > Create BillingProcess > Sub System Up-date |  | Billing Manager | Create and maintain bills for Accounts Receivable. | Assigned Agency | Arvin Deleon-Guerrero or Lynn Christian | arvin.deleon-guerrero@adm.idaho.gov & Lynn.christian@adm.idaho.gov |  |  | 2022-03-01 | All Day Testing
13 | Close Billing - Billing Invoice | Billing Manager > Manage Processing > Invoice |  | Billing Manager | Create and maintain bills for Accounts Receivable. | Assigned Agency | Arvin Deleon-Guerrero or Lynn Christian | arvin.deleon-guerrero@adm.idaho.gov & Lynn.christian@adm.idaho.gov |  |  | 2022-03-01 | All Day Testing
14 | Billing System Period Close | Billing Manager > Manage Processing > Billing System Period Close |  | Billing Manager | Create and maintain bills for Accounts Receivable. | Assigned Agency | Arvin Deleon-Guerrero or Lynn Christian | arvin.deleon-guerrero@adm.idaho.gov & Lynn.christian@adm.idaho.gov |  |  | 2022-03-01 | All Day Testing
15 | Close Inventory Control - Unreleased Documents | 2579 |  | Inventory Manager | Manage/monitor: reconciliation of counts, item master, forecast methods & replenishment, reorder & disposal policy compliance. | Assigned Agency |  |  |  | MF-030-090 Close Inventory Control | 2022-03-01 | All Day Testing
16 | Close Inventory Control - Journalize | 2577 |  | Inventory Manager | Manage/monitor: reconciliation of counts, item master, forecast methods & replenishment, reorder & disposal policy compliance. | LUMA |  |  |  | MF-030-090 Close Inventory Control | 2022-03-01 | All Day Testing
17 | Close Inventory Control - Inventory Period Close | 2575 |  | Inventory Manager | Manage/monitor: reconciliation of counts, item master, forecast methods & replenishment, reorder & disposal policy compliance. | LUMA |  |  |  | MF-030-090 Close Inventory Control | 2022-03-01 | All Day Testing
18 | Close Inventory Control - Close Inventory Control | 2574 |  | Inventory Manager | Manage/monitor: reconciliation of counts, item master, forecast methods & replenishment, reorder & disposal policy compliance. | LUMA |  |  |  | MF-030-090 Close Inventory Control | 2022-03-01 | All Day Testing
19 | Close Inventory Control - Inventory Valuation (Report) | 2576 |  | Inventory Manager | Manage/monitor: reconciliation of counts, item master, forecast methods & replenishment, reorder & disposal policy compliance. | Assigned Agency |  |  |  | MF-030-090 Close Inventory Control | 2022-03-01 | All Day Testing
20 | Close Inventory Control - Period End Valuation (Report) | 2578 |  | Inventory Manager | Manage/monitor: reconciliation of counts, item master, forecast methods & replenishment, reorder & disposal policy compliance. | Assigned Agency |  |  |  | MF-030-090 Close Inventory Control | 2022-03-01 | All Day Testing
21 | Receivables - Cash Batch Exception | Receivables Manager > Processing > Payments > Cash Batch Exception tab > CashBatch Exception Payments |  | Receivables Manager | Reconcile accounts receivables & collections and assess late fees. |  | Genny Casiano | genny.casiano@adm.idaho.gov |  | MF-030-100 Close Receivables | 2022-03-01 | All Day Testing
22 | Receivables - Application Audit | Receivables Manager > Processing > Run ReceivablesProcesses > Application Audit |  | Receivables Manager | Reconcile accounts receivables & collections and assess late fees. |  | Genny Casiano | genny.casiano@adm.idaho.gov |  |  | 2022-03-01 | All Day Testing
23 | Receivables - AR Statement Print | Receivables Manager > Processing > Credit And Collection > Statement Print |  | Receivables Manager | Reconcile accounts receivables & collections and assess late fees. |  | Genny Casiano | genny.casiano@adm.idaho.gov |  |  | 2022-03-01 | All Day Testing
24 | Receivables - Application Close | Receivables Manager > Processing > Run ReceivablesProcesses > ReceivablesClose Menu > Application Close Receivables Manager > Processing > Run ReceivablesProcesses > ReceivablesClose Menu > Application Close Results |  | Receivables Manager | Reconcile accounts receivables & collections and assess late fees. |  | Genny Casiano | genny.casiano@adm.idaho.gov |  |  | 2022-03-01 | All Day Testing
25 | Receivables - Unrealized Gain Loss Report | Receivables Manager > Processing > Run ReceivablesProcesses > Unrealized GainLoss Report |  | Receivables Manager | Reconcile accounts receivables & collections and assess late fees. |  | Genny Casiano | genny.casiano@adm.idaho.gov |  |  | 2022-03-01 | All Day Testing
26 | Receivables - Journalize | Receivables Manager > Processing > > Run ReceivablesProcesses > Receivables CloseMenu > Journalize |  | Receivables Manager | Reconcile accounts receivables & collections and assess late fees. |  | Genny Casiano | genny.casiano@adm.idaho.gov |  |  | 2022-03-01 | All Day Testing
27 | Receivables - Receivable Tie Back Report | Receivables Manager > Processing > Run ReceivablesListing > Receivables TieBack Report |  | Receivables Manager | Reconcile accounts receivables & collections and assess late fees. |  | Genny Casiano | genny.casiano@adm.idaho.gov |  |  | 2022-03-01 | All Day Testing
28 | Receivable Activity Summary | Receivables Manager > Processing > Run ReceivablesProcesses > ReceivablesClose Menu > Receivable Activity Summary |  | Receivables Manager | Reconcile accounts receivables & collections and assess late fees. |  | Genny Casiano | genny.casiano@adm.idaho.gov |  |  | 2022-03-01 | All Day Testing
29 | Receivables - Period Close Report | Receivables Manager > Processing > Run ReceivablesProcesses > ReceivablesClose Menu > Period CloseReport |  | Receivables Manager | Reconcile accounts receivables & collections and assess late fees. |  | Genny Casiano | genny.casiano@adm.idaho.gov |  |  | 2022-03-01 | All Day Testing
30 | Cash -Manage Cash Ledger Transaction | CashManager > Manage Cash Ledger Transaction |  | Cash Manager | Manage all cash transactions. Review and update cash management policy as needed. |  | Genny Casiano & Kim Rau | genny.casiano@adm.idaho.gov or kim.rau@adm.idaho.gov |  |  | 2022-03-01 | All Day Testing
31 | Cash - Journalize Preview Cash Ledger GL Distribution | Cash Manager > Journalize Preview > <Distribution Type> |  | Cash Manager | Manage all cash transactions. Review and update cash management policy as needed. |  | Genny Casiano & Kim Rau | genny.casiano@adm.idaho.gov or kim.rau@adm.idaho.gov |  |  | 2022-03-01 | All Day Testing
32 | Cash - Journalize Cash Ledger GL Distribution | Cash Manager > Journalize Preview > <Distribution Type> > Click Journalize Distribution Button > Cash Management Group <HE> > Cash Code or Cash Code Group > Company or Company Group > Post Thru Date <Month End Date> > Click OK |  | Cash Manager | Manage all cash transactions. Review and update cash management policy as needed. |  | Genny Casiano & Kim Rau | genny.casiano@adm.idaho.gov or kim.rau@adm.idaho.gov |  |  | 2022-03-01 | All Day Testing
33 | Cash - Close Cash Management Period | Cash Accountant > Process Month End > Bank Company Period Close Company or Company Group > Detail Report <yes> > Update <yes> > Bank Company Period Close Report <report receivers> > Error Report <report receivers> > Click Ok |  | Cash Manager | Manage all cash transactions. Review and update cash management policy as needed. |  | Genny Casiano & Kim Rau | genny.casiano@adm.idaho.gov or kim.rau@adm.idaho.gov |  |  | 2022-03-01 | All Day Testing
34 | Close Asset Management: Run Release Assets | 11424 |  | Asset Manager | Manage the process to tract fixed asset activity: create, transfer, and retire fixed assets. | Assigned Agency | Genny Casiano or Steven Bailey | genny.casiano@adm.daho.gov or steven.bailey@adm.idaho.gov |  | MF-040-070-870 | 2022-03-01 | All Day Testing
35 | Close Asset Management: Generate Asset Depreciation Calculation and List | 11425 |  | Asset Manager | Manage the process to tract fixed asset activity: create, transfer, and retire fixed assets. | Assigned Agency | Genny Casiano or Steven Bailey | genny.casiano@adm.daho.gov or steven.bailey@adm.idaho.gov |  | MF-040-070-020 | 2022-03-01 | All Day Testing
36 | Close Asset Management: Generate Asset Report | 11430 |  | Asset Manager | Manage the process to tract fixed asset activity: create, transfer, and retire fixed assets. | Assigned Agency | Genny Casiano or Steven Bailey | genny.casiano@adm.daho.gov or steven.bailey@adm.idaho.gov |  | MF-040-070-880 | 2022-03-01 | All Day Testing
37 | Close Asset Management: Perform Asset Period Close | 11426 |  | Asset Manager | Manage the process to tract fixed asset activity: create, transfer, and retire fixed assets. | Assigned Agency | Genny Casiano or Steven Bailey | genny.casiano@adm.daho.gov or steven.bailey@adm.idaho.gov |  | MF-040-080-020 Perform Asset Period Close | 2022-03-01 | All Day Testing
38 | Process Recurring Journal Entries | Financial Business Analyst > Processing > Journal > Recurring Journal Actions > Journalize |  | Financial Business Analyst | Set up Global Ledger/Budget, monitor allocation & interfacing GL transactions, and maintain journal controls. | Assigned Agency | Lynn Christian | Lynn.christian@adm.idaho.gov |  | MF-030-140 Close Recurring Journals | 2022-03-01 | All Day Testing
39 | GL - Reconcile accounts | Verify that all accounts that need to be reconciled, are reconciled. |  | Financial Business Analyst | Set up Global Ledger/Budget, monitor allocation & interfacing GL transactions, and maintain journal controls. | Assigned Agency | Lynn Christian | Lynn.christian@adm.idaho.gov |  | MF-030-260 Process Year-end Adjustments and Accruals | 2022-03-01 | All Day Testing
40 | GL - Journal Posting | Create Jouranl Entry to reverse all AP Accruals if needed by Agency |  | Financial Business Analyst | Set up Global Ledger/Budget, monitor allocation & interfacing GL transactions, and maintain journal controls. |  | Lynn Christian | Lynn.christian@adm.idaho.gov |  |  | 2022-03-01 | All Day Testing
41 | AR Accruals | Create Jouranl Entry to reverse all AR Accruals if needed by Agency |  | Financial Business Analyst | Set up Global Ledger/Budget, monitor allocation & interfacing GL transactions, and maintain journal controls. |  | Lynn Christian | Lynn.christian@adm.idaho.gov |  |  | 2022-03-01 | All Day Testing
42 | PO/IC Accruals | Create Jouranl Entry to reverse all PO/IC Accruals if needed by Agency |  | Financial Business Analyst | Set up Global Ledger/Budget, monitor allocation & interfacing GL transactions, and maintain journal controls. |  | Lynn Christian | Lynn.christian@adm.idaho.gov |  |  | 2022-03-01 | All Day Testing
43 | Journal Posting | Post all journal entries |  | Financial Business Analyst | Set up Global Ledger/Budget, monitor allocation & interfacing GL transactions, and maintain journal controls. |  | Lynn Christian | Lynn.christian@adm.idaho.gov |  |  | 2022-03-01 | All Day Testing
44 | Allocations | Verify that all allocatins have been processed for period |  | Financial Business Analyst | Set up Global Ledger/Budget, monitor allocation & interfacing GL transactions, and maintain journal controls. |  | Lynn Christian | Lynn.christian@adm.idaho.gov |  |  | 2022-03-01 | All Day Testing
45 | CAM ? |  |  | Financial Business Analyst | Set up Global Ledger/Budget, monitor allocation & interfacing GL transactions, and maintain journal controls. |  | Lynn Christian | Lynn.christian@adm.idaho.gov |  |  | 2022-03-01 | All Day Testing
46 | Period Closing | Financial Business Analyst > Processing > Period Close > Close Period for Entity Select Entity, Year, Period > Actions > Limited Close |  | Financial Business Analyst | Set up Global Ledger/Budget, monitor allocation & interfacing GL transactions, and maintain journal controls. |  | Lynn Christian | Lynn.christian@adm.idaho.gov |  |  | 2022-03-01 | All Day Testing
47 | Final Review of Period Close |  |  | Controller | Monitor financial structure and Chart of Account dimensions for their Agency and recommendations for updates. Manage all financial processes. | Assigned Agency |  |  |  | MF-030-260 Process Year-end Adjustments and Accruals | 2022-03-01 | All Day Testing
48 | Year end Processing |  |  | Controller | Monitor financial structure and Chart of Account dimensions for their Agency and recommendations for updates. Manage all financial processes. | Assigned Agency |  |  |  | MF-030-260 Process Year-end Adjustments and Accruals | 2022-03-01 | All Day Testing
Note on J5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard

## Global Ledger Entries and A (2)
SIT 3 Scenario - Global Legder Processing and Analysis
Agency:
SIT Week - Week 8 - 2/21/ - 2/25
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Create a Front-End Split Journal Entry (Front End Split Projects Only) | Refer to Upload Template | 12154 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Lynn Christian or Sheri Jones | lynn.christian@adm.idaho.gov or sheri.jones@adm.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-010 | 2022-02-23 | 8:45-9:30 AM
2 | Create a Journal Entry | Refer to Upload Template | 11668 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Lynn Christian or Sheri Jones | lynn.christian@adm.idaho.gov or sheri.jones@adm.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-010 | 2022-02-23 | 9:30-10AM
3 | Approve a Journal Entry | Refer to Upload Template | 11669 | Approver | Approve transactions such as requisitions, purchase orders, solicitation & journal entries. | Assigned Agency | Lvl 1 Arvin Deleon Guerrero, Lynn Christian or Genny Casiano Lvl 2 Genny Casiano or Kim Rau | arvin.deleon-guerrero@adm.idaho.gov lynn.christian@adm.idaho.gov genny.casiano@adm.idaho.gov kim.rau@adm.idaho.gov |  | MF-025-060 | 2022-02-23 | 10-11AM
4 | Create a Journal Entry from an Existing Journal | Refer to Upload Template | 11671 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Lynn Christian or Sheri Jones | lynn.christian@adm.idaho.gov or sheri.jones@adm.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-010 | 2022-02-23 | 1-1:30PM
5 | Create a Journal Entry from a Template | Refer to Upload Template | 11670 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Lynn Christian or Sheri Jones | lynn.christian@adm.idaho.gov or sheri.jones@adm.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-010 | 2022-02-23 | 1:30-2PM
6 | Create a Recurring Journal | Refer to Upload Template | 11673 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Lynn Christian or Sheri Jones | lynn.christian@adm.idaho.gov or sheri.jones@adm.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-020 | 2022-02-23 | 2-2:30PM
7 | Journalize a Recurring Journal Entry | Refer to Upload Template | 12155 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Lynn Christian or Sheri Jones | lynn.christian@adm.idaho.gov or sheri.jones@adm.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-030 | 2022-02-23 | 2:30-3PM
8 | Post Multiple Journal Entries | Refer to Upload Template | 12156 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Lynn Christian or Sheri Jones | lynn.christian@adm.idaho.gov or sheri.jones@adm.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-23 | 3-3:30PM
9 | Post Journals from Subsystems | Refer to Upload Template | 12157 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Lynn Christian or Sheri Jones | lynn.christian@adm.idaho.gov or sheri.jones@adm.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-050 | 2022-02-24 | 8:45-9:30 AM
10 | Validate (here) Reconcile (close) Subsystems to the General Ledger | Bill will put these scripts here and in close scenario | TBD | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Lynn Christian or Sheri Jones | lynn.christian@adm.idaho.gov or sheri.jones@adm.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-24 | 9:30-10AM
11 | Analyze Global Ledger Totals | Refer to Upload Template | 12158 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Lynn Christian or Sheri Jones | lynn.christian@adm.idaho.gov or sheri.jones@adm.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-24 | 10-11AM
12 | Perform Account Analysis | Refer to Upload Template | 11672 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Lynn Christian or Sheri Jones | lynn.christian@adm.idaho.gov or sheri.jones@adm.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-24 | 1-1:30PM
13 | Perform Fund Analysis | Refer to Upload Template | 12159 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Lynn Christian or Sheri Jones | lynn.christian@adm.idaho.gov or sheri.jones@adm.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-24 | 1:30-2PM
14 | Perform Organizational Unit Analysis | Refer to Upload Template | 12160 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Lynn Christian or Sheri Jones | lynn.christian@adm.idaho.gov or sheri.jones@adm.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-24 | 2-2:30PM
15 | View Transactions by Entity-Account | Refer to Upload Template | 11674 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Lynn Christian or Sheri Jones | lynn.christian@adm.idaho.gov or sheri.jones@adm.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-25 | 9- 9:30 AM
16 | BIRST/BI/CSF Analytic Reporting |  | TBD | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Lynn Christian or Sheri Jones | lynn.christian@adm.idaho.gov or sheri.jones@adm.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-25 | 9:30 - 10 AM
17 | Evaluate Encumbrances | Placeholder - Judy and Bill (and Eileen/Cathy) are working on script for this; will have this week (12/23/21) | TBD | Staff Accountant |  | Assigned Agency | Lynn Christian or Sheri Jones | lynn.christian@adm.idaho.gov or sheri.jones@adm.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-25 | 10 - 11 AM
Note on J5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard

## Chart of Accounts Maintenance
SIT 3 Scenario - Chart of Accounts Maintenance
Agency:
SIT Week - Week 10 - 3/7 - 3/11
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | View and Validate an Organizational Unit |  | TBD | Staff Accountant |  |  | Lynn Christian or Sheri Jones | lynn.christian@adm.idaho.gov or sheri.jones@adm.idaho.gov |  |  | 2022-03-07 | 8:45-9:30 AM
2 | View and Validate a Project |  | TBD | Staff Accountant |  |  | Lynn Christian or Sheri Jones | lynn.christian@adm.idaho.gov or sheri.jones@adm.idaho.gov |  |  | 2022-03-07 | 9:30-10AM
3 | View and Validate a Program |  | TBD | Staff Accountant |  |  | Lynn Christian or Sheri Jones | lynn.christian@adm.idaho.gov or sheri.jones@adm.idaho.gov |  |  | 2022-03-07 | 10-11AM
4 | View and Validate a Location |  | TBD | Staff Accountant |  |  | Lynn Christian or Sheri Jones | lynn.christian@adm.idaho.gov or sheri.jones@adm.idaho.gov |  |  | 2022-03-07 | 1-1:30PM
5 | View and Validate Additional Reporting |  | TBD | Staff Accountant |  |  | Lynn Christian or Sheri Jones | lynn.christian@adm.idaho.gov or sheri.jones@adm.idaho.gov |  |  | 2022-03-07 | 1:30-2PM
6 | View and Validate Custodial Accounts (CAM) |  | TBD | Staff Accountant |  |  | Lynn Christian or Sheri Jones | lynn.christian@adm.idaho.gov or sheri.jones@adm.idaho.gov |  |  | 2022-03-07 | 2-2:30PM
7 | Request a new account |  | TBD | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Lynn Christian or Sheri Jones | lynn.christian@adm.idaho.gov or sheri.jones@adm.idaho.gov |  |  | 2022-03-07 | 2:30-3PM
8 | Request a new organizational unit |  | TBD | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Lynn Christian or Sheri Jones | lynn.christian@adm.idaho.gov or sheri.jones@adm.idaho.gov |  |  | 2022-03-07 | 3-3:30PM
9 | View and Validate Beginning Balances |  | TBD | Staff Accountant |  |  | Lynn Christian or Sheri Jones | lynn.christian@adm.idaho.gov or sheri.jones@adm.idaho.gov |  |  | 2022-03-08 | 8:45-9:30 AM
10 | Update Summary Conversion Balances to Detail |  | TBD | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. |  | Lynn Christian or Sheri Jones | lynn.christian@adm.idaho.gov or sheri.jones@adm.idaho.gov |  |  | 2022-03-08 | 9:30-10AM
Note on J5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard