## SIT 3 Listing & Schedule
SIT 3 End to End Scenarios | SIT 3 Scheduled Week | 240 - Department of Labor
Inventory Management Cycle | Week 4: 1/24 - 1/28
Pcard End to End Process | Week 4: 1/24 - 1/28
Project Processing (RQ, PO, Contract, INV) | Week 4: 1/24 - 1/28 | X
XM Pcard NO Cash Advance | Week 4: 1/24 - 1/28
XM Pcard WITH Cash Advance | Week 4: 1/24 - 1/28
Payroll End to End | Week 4: 1/24 - 1/28
Fixed Asset Acquire to Retire | Week 5: 1/31 - 2/4
Statewide Contract Procure to Pay | Week 5: 1/31 - 2/4 | X
GHR Shell | Week 5: 1/31 - 2/4
Project 1.1 Project Setup and Maintanance | Week 5: 1/31 - 2/4 | X
Project 1.2 Project Processing Master (P&G only) | Week 5: 1/31 - 2/4 | X
AR Credit Monitoring | Week 6: 2/7 - 2/11 | X
Asset Management Maintenance | Week 6: 2/7 - 2/11
Service Contract Interagency Billing | Week 6: 2/7 - 2/11 | X
Project 1.3 Reports and Inquiry Master | Week 6: 2/7 - 2/11 & Week 7: 2/14 - 2/18 | X
Cash Ledger Payment | Week 7: 2/14 - 2/18 | X
Interagency Billing to Settlement | Week 7: 2/14 - 2/18 | X
Non-State Billing | Week 7: 2/14 - 2/18 | X
Procure to Pay Vendor Management Voids | Week 7: 2/14 - 2/18 | X
Vendor Refunds | Week 7: 2/14 - 2/18
Cash Management Deposit to Revenue | Week 8: 2/21 - 2/25
Custodial Accounts Setup | Week 8: 2/21 - 2/25 | X
Global Ledger Entries and Analysis | Week 8: 2/21 - 2/25 | X
Punchout Request to Payment | Week 8: 2/21 - 2/25 | X
Tax Refunds | Week 8: 2/21 - 2/25
Allocations | Week 9: 2/28 - 3/4
Budget | Week 9: 2/28 - 3/4 | X
Custodial Accounts Transaction Processing | Week 9: 2/28 - 3/4 | X
Month End/Year End | Week 9: 2/28 - 3/4
Define and Generate Recurring Invoices | Week 9: 2/28 - 3/4
Chart of Accounts Maintenance | Week 10: 3/7 - 3/11 | X
3rd Party Allocations | TBD | X

## Instructions
Luma System Integration Testing 3 (SIT 3) Instructions
Agency Functional Testing Dates | January 24 - March 11, 2022 Testing Schedule: Monday -Thursday 8:45 -11 am and 1:45 - 4:00 pm, Friday 9:00 - 11:00 am
Agency Testers Roles and Responsibilities | 1. Execute test scripts per SIT 3 schedule. 2. Review actual results against expected results. 3. Log defects as needed. 4. Retest failed test results to resolve defects. 5. Launch integrations during test cycle per schedule.
Testing Packet | 1. Test Scenario Excel File: Cover Page, Instruction Tab, Scenario Listing, Tab with each steps script detailed instruction to execute the script. 2. Data Sheets. 3. Email Template to use to report your testing results.
Testing Steps | 1. If you are the first step in the scenario, you may begin execution according to the the Date and Time in the Testing packet. If you are not on step 1, please wait for the step before you to complete their script and you receive communication to begin. 2. Execute assigned script(s) using the testing script and data sheet that was provided to you. 3. Sending Testing results via email using to the Test Management Team. (attached email sample) 4. Communicate to the next tester they can begin their script. (Slack or Email works)
What should you do if there are issues or you need assistance while testing? | 1. The Test Management Team will host an all-day SIT 3 Testing Support Hotline (WebEx Meeting). 2. Attendance is optional for SIT testers and testers should only join if they have questions or issues regarding SIT testing. 3. Testers should have an invite on their calendar that includes the WebEx Link.
How to submit a SIT 3 Testing Defect using ServiceNow: | 1. Visit https://auth.sco.idaho.gov/ in your web browser. Google Chrome and Microsoft Edge are recommended. 2. Enter your State ID number as the username and your password. Click the Sign In button. 3. You will be presented with a second page for Multi-Factor Authentication. Select an option and acknowledge the push or call, or enter a passcode from your Duo app. 4. You will see several buttons on your Enterprise Dashboard. One of these will be labeled Service Desk. This button will take you to the Service Portal. 5. There are four main buttons across the center of the page. Click Service Requests to be taken to the service menu. 7. Locate and select LUMA SIT3 Testing Issue from the options listed. 6. Select the SCO IT Services category from the list on the left side of the page. 7. Fill out form with Primary Contact, Short Description, Description, Category, Scenario Name, Script ID, add attachments/screenshots and submit the ticket.
What to do if there is a system outage? | 1. Please join the Testing Support Hotline if you run into any issues with the system and notify the meeting moderator of the issue. 2. If there is a system outage, the Test Management Team will work with the Communications team to notify Agency Testers.

## Email Submission Template
Click on Icon Below to Outlook Email Template

## Project Processing
SIT 3 Scenario - Project Procurement Processing
Agency:
SIT Week - Week 4 - 1/24 - 1/28
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Create RSS Requisition for a Project Item | 2968 | 12522 | Requester | Determines requirements & cost estimates for purchase of goods & services. Submits purchase requisition. | Assigned Agency | Carrie Parks | carrie.parks@labor.idaho.gov |  | PR-020-010 | 2022-01-25 | 8:45-9:30 AM
2 | Approve Requisition | 8539 | 12528 | Approver | Approve transactions such as requisitions, purchase orders, solicitations, and journal entries. | Assigned Agency | Various (dependant on cost center) |  |  | PR-010-060 | 2022-01-25 | 9:30-10AM
3 | Create a Purchase Order | 8169 | 12523 | Buyer | Review requisition and create purchase orders. Conduct market research, and monitor vendor commitments. Approve vendor returns. | Assigned Agency | Linda Redford | Linda.Redford@labor.idaho.gov |  | PR-050-040 | 2022-01-25 | 10-11AM
4 | Create a Receipt | 4581 | 12532 | Receiver | Receive and inspect incoming goods. Pick items for shipment/transfer. Dispose of items. Conduct vendor returns. Document variances. | Assigned Agency | Tony Hartz | tony.hartz@labor.idaho.gov | Receiving Messages | PR-050-070 | 2022-01-25 | 1-1:30PM
5 | Create Contract (Sub-Award) with Service Lines | 7219 | 12533 | Contract Manager | Compile contract file, including entering contract line-item details, terms & conditions, and pricing, and amends and renews contracts. | Assigned Agency | Linda Redford | Linda.Redford@labor.idaho.gov | First Line = $25,000 Second line = Remainder of the Sub-Award | PR-040-010 | 2022-01-25 | 1:30-2PM | WFDTF as subaward, Jobcorps CWI, Serve Idaho
6 | Create Contract - Contract Draft - Articles Tab | 7204 | 12531 | Contract Manager | Compile contract file, including entering contract line-item details, terms & conditions, and pricing, and amends and renews contracts. | Assigned Agency | Linda Redford | Linda.Redford@labor.idaho.gov |  | PR-040-010 | 2022-01-25 | 2-2:30PM
7 | Create Contract - Contract Draft - Participants Tab | 2667 | 12537 | Contract Manager | Compile contract file, including entering contract line-item details, terms & conditions, and pricing, and amends and renews contracts. | Assigned Agency | Linda Redford | Linda.Redford@labor.idaho.gov |  | PR-040-010 | 2022-01-25 | 2:30-3PM
8 | Create Contract - Contract Draft - Lines Tab - Service | 3375 | 12536 | Contract Manager | Compile contract file, including entering contract line-item details, terms & conditions, and pricing, and amends and renews contracts. | Assigned Agency | Linda Redford | Linda.Redford@labor.idaho.gov |  | PR-040-010 | 2022-01-25 | 3-3:30PM
9 | Create Contract - Contract Draft - Contacts Tab | 3335 | 12534 | Contract Manager | Compile contract file, including entering contract line-item details, terms & conditions, and pricing, and amends and renews contracts. | Assigned Agency | Linda Redford | Linda.Redford@labor.idaho.gov |  | PR-040-010 | 2022-01-26 | 8:45-9:30 AM
10 | Create Contract - Contract Draft - Releasing a Contract | 7203 | 12530 | Contract Manager | Compile contract file, including entering contract line-item details, terms & conditions, and pricing, and amends and renews contracts. | Assigned Agency | Linda Redford | Linda.Redford@labor.idaho.gov |  | PR-040-010 | 2022-01-26 | 9:30-10AM
11 | Create Contract - Contract Draft - Activating a Contract | 7202 | 12540 | Contract Manager | Compile contract file, including entering contract line-item details, terms & conditions, and pricing, and amends and renews contracts. | Assigned Agency | Linda Redford | Linda.Redford@labor.idaho.gov |  | PR-040-010 | 2022-01-26 | 10-11AM
12 | Contract Approval | 8353 | 12524 | Approver | Approve transactions such as requisitions, purchase orders, solicitations, and journal entries. | Assigned Agency | Tom Coles | thomas.coles@labor.idaho.gov |  | PR-040-010 | 2022-01-26 | 1-1:30PM | Based on Org Unit
13 | Create Requisition - Service Lines from Contract (Sub-Award) | 8323 | 12529 | Requester | Determines requirements & cost estimates for purchase of goods & services. Submits purchase requisition. | Assigned Agency | Carrie Parks | carrie.parks@labor.idaho.gov |  | PR-010-060 | 2022-01-26 | 1:30-2PM
14 | Approve Requisition | 8539 | 12539 | Approver | Approve transactions such as requisitions, purchase orders, solicitations, and journal entries. | Assigned Agency | Various (dependant on cost center) |  |  | PR-020-020 | 2022-01-26 | 2-2:30PM
15 | Create a Purchase Order | 2753 | 12538 | Buyer | Review requisition and create purchase orders. Conduct market research, and monitor vendor commitments. Approve vendor returns. | Assigned Agency | Linda Redford | Linda.Redford@labor.idaho.gov |  | PR-050-040 | 2022-01-26 | 2:30-3PM
16 | Create Invoice | 11374 | 12525 | Payables Invoice Processor | Process interface and XM files. Match payables invoices, and vendor list. Process payables payments. Generate 1099. | Assigned Agency | Ron Hanson | Ronald.hanson@labor.idaho.gov |  | MF-070-050 Enter a PO Invoice | 2022-01-26 | 3-3:30PM
17 | Approve Invoice | 11375 | 12527 | Approver | Approve transactions such as requisitions, purchase orders, solicitations, and journal entries. | Assigned Agency | Various (dependant on cost center) |  |  | MF-070-056 Invoice Approval Process | 2022-01-26 | 3:30 -4 PM
18 | Match Invoice | 11457 | 12535 | Payables Manager | Void & cancel payments. Reissue & mail warrants. Process period close. | Assigned Agency | Nancy Fulfer | nancy.fulfer@labor.idaho.gov |  | MF-070-070 Match Invoices | 2022-01-27 | 8:45-9:30 AM
19 | Process Payment for Invoice | 11442 | 12526 | Payables Manager | Void & cancel payments. Reissue & mail warrants. Process period close. | Assigned Agency | Nancy Fulfer | nancy.fulfer@labor.idaho.gov |  | MF-070-100 Process Invoice Payments | 2022-01-27 | 9:30-10AM

## Statewide Contract Procure to P
SIT 3 Scenario - Statewide Contract Procure to Pay
Agency:
SIT 3 Week - Week 5 - 1/31-2/4
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Create Contract with Rebate and Price Breaks Statewide for Envelopes - Create a Contract (Contract Tab) | 7219 | 11992 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-020 | 2022-01-31 | 8:45 - 11 AM
2 | Create Contract with Rebate and Price Breaks Statewide for Envelopes - Contract Draft (Articles) | 7204 | 11987 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-020 | 2022-01-31 | 8:45 - 11 AM
3 | Create Contract with Rebate and Price Breaks Statewide for Envelopes - Contract Draft - Participants | 2667 | 11997 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-020 | 2022-01-31 | 8:45 - 11 AM
4 | Create Contract with Rebate and Price Breaks Statewide for Envelopes - Contract Draft - Lines - Special | 8909 | 11995 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-020 | 2022-01-31 | 8:45 - 11 AM
5 | Create Contract with Rebate and Price Breaks Statewide for Envelopes - Contract Draft - Lines - Purchase Type Detail - Purchase Pricing | 2663 | 11996 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-020 | 2022-01-31 | 8:45 - 11 AM
6 | Create Contract with Rebate and Price Breaks Statewide for Envelopes - Contract Draft - Rebates | 2671 | 11998 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-020 | 2022-01-31 | 8:45 - 11 AM
7 | Create Contract with Rebate and Price Breaks Statewide for Envelopes - Contract Draft - Contacts | 3335 | 11993 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-020 | 2022-01-31 | 8:45 - 11 AM
8 | Create Contract with Rebate and Price Breaks Statewide for Envelopes - Releasing a Contract | 7203 | 11985 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-020 | 2022-01-31 | 8:45 - 11 AM
9 | Contract Approval | 8353 | 11979 | Approver | Compile contract file including entering contract line item details, terms & conditions along with pricing. | DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-020 | 2022-01-31 | 8:45 - 11 AM
10 | Create Contract with Rebate and Price Breaks Statewide for Envelopes - Activating a Contract | 7202 | 11978 | Contract Manager | Approve transactions such as requisitions, purchase orders, solicitation & journal entries. | DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-020 | 2022-01-31 | 1 - 1:30 PM
11 | Requisition - RSS | 8325 | 11988 | Requester | Determines requirements & cost estimates for purchase of goods & services. Submits purchase requisition. | Assigned Agency | Carrie Parks | carrie.parks@labor.idaho.gov | distribution to multiple org unit and agencies | PR-020-010 | 2022-01-31 | 1:30 - 2:30 PM
12 | Approve Requisition | 8539 | 11984 | Approver | Approve transactions such as requisitions, purchase orders, solicitation & journal entries. | Assigned Agency | Various (dependant on cost center) |  |  | PR-020-010 | 2022-01-31 | 2:30 - 3 PM
13 | Create PO from Requisition | 8327 | 11991 | Buyer | Review requisitions & create purchase orders. Conduct market research & monitor vendor commitments. Approve vendor returns. | Assigned Agency | Linda Redford | Linda.Redford@labor.idaho.gov |  | PR-050-040 | 2022-02-01 | 8:45-9:30 AM
14 | Receive Purchase Order | 3064 | 11977 | Receiver | Receive and inspect incoming goods. Pick items for shipment/transfer. Dispose of items. Vendor returns. Document variances. | Assigned Agency | Tony Hartz | tony.hartz@labor.idaho.gov |  | PR-050-070 | 2022-02-01 | 9:30-10AM
15 | Create Invoice | 11606 | 11983 | Payables Invoice Processor | Process interface and XM files. Match payables invoices, and vendor list. Process payables payments. Generate 1099. | Assigned Agency | Ron Hanson | Ronald.hanson@labor.idaho.gov |  | MF-070-050 Enter a PO Invoice | 2022-02-01 | 10-11AM
16 | Notify Buyer of Discrepancy | 11605 | 11982 | Payables Invoice Processor | Process interface and XM files. Match payables invoices, and vendor list. Process payables payments. Generate 1099. |  | Ron Hanson | Ronald.hanson@labor.idaho.gov |  | MF-070-050 Enter a PO Invoice | 2022-02-01 | 1-1:30PM
17 | Resolve Cost Discrepancy | New | 12004 | Buyer | Review requisition and create purchase orders. Conduct market research, and monitor vendor commitments. Approve vendor returns. | Assigned Agency | Linda Redford | Linda.Redford@labor.idaho.gov |  |  | 2022-02-01 | 1:30-2PM
18 | Submit Resolved Invoice for Approval | 11607 | 11989 | Payables Invoice Processor | Process interface and XM files. Match payables invoices, and vendor list. Process payables payments. Generate 1099. |  | Ron Hanson | Ronald.hanson@labor.idaho.gov |  | MF-070-050 Enter a PO Invoice | 2022-02-01 | 2-2:30PM
19 | Approve Invoice | 11608 | 11990 | Approver | Approve transactions such as requisitions, purchase orders, solicitations, and journal entries. | Assigned Agency | Various (dependant on cost center) |  |  | MF-070-056 Invoice Approval Process | 2022-02-01 | 2:30-3PM
20 | Match Invoice | 11609 | 11994 | Payables Manager | Void & cancel payments. Reissue & mail warrants. Process period close. | Assigned Agency | Nancy Fulfer | nancy.fulfer@labor.idaho.gov |  | MF-070-070 Match Invoices | 2022-02-01 | 3-3:30PM
21 | Process Payment for Invoice | 11442 | 11981 | Payables Manager | Void & cancel payments. Reissue & mail warrants. Process period close. | Assigned Agency | Nancy Fulfer | nancy.fulfer@labor.idaho.gov |  | MF-070-100 Process Invoice Payments | 2022-02-01 | 3-3:30PM
22 | Journalize | 11440 | 11980 | Payables Manager | Void & cancel payments. Reissue & mail warrants. Process period close. |  | Nancy Fulfer | nancy.fulfer@labor.idaho.gov |  | MF-070-110 Journalize AP Distributions | 2022-02-01 | 3-3:30PM
23 | Renew/Addendum Statewide Contract | 2773 | 11986 | Contract Manager | Compile contract file, including entering contract line-item details, terms & conditions, and pricing, and amends and renews contracts. | DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-050-010 | 2022-02-02 | 8:45-9:30 AM
24 | Load Rebate Invoices | New | 11999 | Supply Management Admin or Processor |  | Assigned Agency |  |  |  | PR-050-010 | 2022-02-02 | 9:30-10AM
25 | Calculate Rebate Amounts Due for a Contract | New | 12000 | Supply Management Admin or Processor | [5 empty] | PR-050-010 | 2022-02-02 | 10-11AM
26 | Review Rebate Due Information | New | 12001 | Contract Manager | Compile contract file, including entering contract line-item details, terms & conditions, and pricing, and amends and renews contracts. | Assigned Agency | DOP Tester | contractadmin@adm.idaho.gov |  | PR-050-010 | 2022-02-02 | 1-1:30PM
27 | Apply Rebate (Enter a Rebate Invoice in Payables | New | 12002 | Payables Manager | Void & cancel payments. Reissue & mail warrants. Process period close. |  | Lynn Christian | lynn.christian@adm.idaho.gov | There isn't an invoice type of Rebate Invoice???? | MF-260-070ZZ | 2022-02-03 | 8:45-9:30 AM
28 | Review Rebate Information | New | 12003 | Contract Manager | Compile contract file, including entering contract line-item details, terms & conditions, and pricing, and amends and renews contracts. |  | DOP Tester | contractadmin@adm.idaho.gov |  | PR-050-010 | 2022-02-03 | 9:30-10AM
29 | Verify Rebates posted in Cash Account |  |  | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Genny Casiano | genny.casiano@adm.idaho.gov |  | MF-260-070ZZ | 2022-02-03 | 10-11 AM

## Project 1.1 Project Setup and M
SIT 3 Scenario - Project Setup
Agency:
SIT 3 Week - Week 5 - 1/31-2/4
Sequence | Script ID | Tab | ALM Test ID # (view tab = "Tests" column A) | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Create Operational Project | FSM.PS001 |  | Project Administrator | Sets up projects and funding sources. | Assigned Agency | Carrie Peterman | carrie.peterman@labor.idaho.gov |  | MF-050-010 | Conference Room Pilot (In Person) 1/31 - 2/4
2 | Create Billable MultiFunded Project - External Grant/External Customer | FSM.PS002 |  | Project Administrator | Sets up projects and funding sources. | Assigned Agency | Carrie Peterman | carrie.peterman@labor.idaho.gov |  | MF-280-020 | Conference Room Pilot (In Person) 1/31 - 2/4
3 | Create Internal Only Project | FSM.PS003 |  | Project Administrator | Sets up projects and funding sources. | Assigned Agency | Carrie Peterman | carrie.peterman@labor.idaho.gov |  | MF-050-010 | Conference Room Pilot (In Person) 1/31 - 2/4
4 | Create MultiFunded Project w Program Income (Additive/ Deductive/ Cost Sharing) or Rebates Income Funding Source | FSM.PS004 |  | Project Administrator | Sets up projects and funding sources. | Assigned Agency | Carrie Peterman | carrie.peterman@labor.idaho.gov |  | MF-280-020 | Conference Room Pilot (In Person) 1/31 - 2/4
5 | Create Milestone Project(w/wo Override) | FSM.PS005 |  | Project Administrator | Sets up projects and funding sources. | Assigned Agency | Carrie Peterman | carrie.peterman@labor.idaho.gov |  | MF-280-020 | Conference Room Pilot (In Person) 1/31 - 2/4
6 | Create Project with Intercompany Funding | FSM.PS006 |  | Project Administrator | Sets up projects and funding sources. | Assigned Agency | Carrie Peterman | carrie.peterman@labor.idaho.gov |  | MF-280-020 | Conference Room Pilot (In Person) 1/31 - 2/4
7 | Create a New Posting Project (child) for existing Contract (new year project) | FSM.PS007 |  | Project Administrator | Sets up projects and funding sources. | Assigned Agency | Carrie Peterman | carrie.peterman@labor.idaho.gov |  | MF-280-020 | Conference Room Pilot (In Person) 1/31 - 2/4
8 | Create New Burden Codes | FSM.PS009 |  | Project Administrator | Sets up projects and funding sources. | Assigned Agency | Carrie Peterman | carrie.peterman@labor.idaho.gov |  | MF-280-000ZZ | Conference Room Pilot (In Person) 1/31 - 2/4
9 | Create New Selection Group | FSM.PS010 |  | Project Administrator | Sets up projects and funding sources. | Assigned Agency | Carrie Peterman | carrie.peterman@labor.idaho.gov |  | MF-280-000ZZ | Conference Room Pilot (In Person) 1/31 - 2/4
10 | Assign Burden Code To Posting Project | FSM.PS011 |  | Project Administrator | Sets up projects and funding sources. | Assigned Agency | Carrie Peterman | carrie.peterman@labor.idaho.gov |  | MF-280-030ZZ | Conference Room Pilot (In Person) 1/31 - 2/4
11 | Attach Burden to Funding Source | FSM.PS012 |  | Project Administrator | Sets up projects and funding sources. | Assigned Agency | Carrie Peterman | carrie.peterman@labor.idaho.gov |  | MF-280-030ZZ | Conference Room Pilot (In Person) 1/31 - 2/4
12 | Program Income Additive | FSM.PM001 |  | Project Administrator | Sets up projects and funding sources. | Assigned Agency | Carrie Peterman | carrie.peterman@labor.idaho.gov |  | MF-280-045ZZ | Conference Room Pilot (In Person) 1/31 - 2/4
13 | Program Income Deductive/Cost Sharing | FSM.PM002 |  | Project Administrator | Sets up projects and funding sources. | Assigned Agency | Carrie Peterman | carrie.peterman@labor.idaho.gov |  | MF-280-045ZZ | Conference Room Pilot (In Person) 1/31 - 2/4

## Project 1.2 Project Processing
Other Teams Involvement Identified
NOTE: Project processing actions take place after Procurement/AP/Payroll Processing.
SIT 3 Scenario - Project Processing (P&G Only)
Agency:
SIT Week - (dates)
Sequence | Script ID | SIT TEST ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Create Project transactions Journal Entry | FSM.PP001 | Project Accountant |  |  | Carrie Peterman | carrie.peterman@labor.idaho.gov |  | MF-020-050 | Conference Room Pilot (In Person) 1/31 - 2/4
2 | In-Kind Journal Entry ("on the books"/off books) | FSM.PP002 | Project Accountant |  |  | Carrie Peterman | carrie.peterman@labor.idaho.gov |  | MF-020-050 | Conference Room Pilot (In Person) 1/31 - 2/4
3 | Copy ( & Copy Reverse) Journal Entry | FSM.PP003 | Project Accountant |  |  | Carrie Peterman | carrie.peterman@labor.idaho.gov |  | MF-020-050 | Conference Room Pilot (In Person) 1/31 - 2/4
4 | Create I/C Journal Entry | FSM.PP004 | Project Accountant |  |  | Carrie Peterman | carrie.peterman@labor.idaho.gov |  | MF-020-050 | Conference Room Pilot (In Person) 1/31 - 2/4
5 | Create, Release and Journalize Recurring JE | FSM.PP005 | Project Accountant |  |  | Carrie Peterman | carrie.peterman@labor.idaho.gov |  | MF-020-050 | Conference Room Pilot (In Person) 1/31 - 2/4
6 | Post Journal |  | GL | [5 empty] | MF-020-090 | Conference Room Pilot (In Person) 1/31 - 2/4
7 | Create and Process Retainer Invoice | FSM.PP010 | Project Accountant |  |  | Carrie Peterman | carrie.peterman@labor.idaho.gov |  | MF-280-030: Grant Billing Processing | Conference Room Pilot (In Person) 1/31 - 2/4 |  | new process
8 | Generate Indirect Burdens | FSM.PP011 | Project Accountant |  |  | Carrie Peterman | carrie.peterman@labor.idaho.gov |  | DC-040-090 - Apply Overhead Costs | Conference Room Pilot (In Person) 1/31 - 2/4
9 | Delete Indirect Burden | FSM.PP012 | Project Accountant |  |  | Carrie Peterman | carrie.peterman@labor.idaho.gov |  | DC-040-090 - Apply Overhead Costs | Conference Room Pilot (In Person) 1/31 - 2/4
10 | Journalize Indirect Burden | FSM.PP013 | Project Accountant |  |  | Carrie Peterman | carrie.peterman@labor.idaho.gov |  | DC-040-090 - Apply Overhead Costs | Conference Room Pilot (In Person) 1/31 - 2/4
11 | Reverse Indirect Burden | FSM.PP014 | Project Accountant |  |  | Carrie Peterman | carrie.peterman@labor.idaho.gov |  | DC-040-090 - Apply Overhead Costs | Conference Room Pilot (In Person) 1/31 - 2/4
12 | Post Transaction in GL |  | GL | [5 empty] | DC-030-050 - Allocate Indirect Costs | Conference Room Pilot (In Person) 1/31 - 2/4
13 | Journalize IB Projects Transactions | FSM.PP013 | Project Accountant |  |  | Carrie Peterman | carrie.peterman@labor.idaho.gov |  | DC-030-050 - Allocate Indirect Costs | Conference Room Pilot (In Person) 1/31 - 2/4
14 | Post Transaction in GL |  | GL | [5 empty] | DC-030-050 - Allocate Indirect Costs | Conference Room Pilot (In Person) 1/31 - 2/4
15 | Create, Generate ,Update Certification Number & Date and Journalize Milestone Invoice | FSM.PP020 | Project Accountant |  |  | Carrie Peterman | carrie.peterman@labor.idaho.gov |  | MF-280-030: Grant Billing Processing | Conference Room Pilot (In Person) 1/31 - 2/4
16 | Create, Generate ,Update Certification Number & Date and Journalize Cost Reimbursement Invoice | FSM.PP021 | Project Accountant |  |  | Carrie Peterman | carrie.peterman@labor.idaho.gov |  | MF-280-030: Grant Billing Processing | Conference Room Pilot (In Person) 1/31 - 2/4
17 | Generate Mass Contract Invoice w/wo Billing Group, Mass Journalize and Review AR Transaction | FSM.PP022 | Project Accountant |  |  | Carrie Peterman | carrie.peterman@labor.idaho.gov |  | MF-280-030: Grant Billing Processing | Conference Room Pilot (In Person) 1/31 - 2/4
27 | Process Project Capitalization | FSM.PP040 | Project Accountant |  |  | Carrie Peterman | carrie.peterman@labor.idaho.gov |  | DC-050-030 - Capitalize Leased Asset | Conference Room Pilot (In Person) 1/31 - 2/4
28 | Contract Balance Adjustments | FSM.PP050 | Project Accountant |  |  | Carrie Peterman | carrie.peterman@labor.idaho.gov |  | MF-280-021ZZ | Conference Room Pilot (In Person) 1/31 - 2/4
29 | Reverse Indirect Burden | FSM.PP051 | Project Accountant |  |  | Carrie Peterman | carrie.peterman@labor.idaho.gov |  | DC-040-090 - Apply Overhead Costs | Conference Room Pilot (In Person) 1/31 - 2/4
30 | Delete Invoice | FSM.PP052 | Project Accountant |  |  | Carrie Peterman | carrie.peterman@labor.idaho.gov |  | MF-280-031ZZ | Conference Room Pilot (In Person) 1/31 - 2/4
31 | Reverse Journalize Invoice | FSM.PP053 | Project Accountant |  |  | Carrie Peterman | carrie.peterman@labor.idaho.gov |  | MF-280-032ZZ | Conference Room Pilot (In Person) 1/31 - 2/4
32 | New Burden Rate | FSM.PP054 | Project Accountant |  |  | Carrie Peterman | carrie.peterman@labor.idaho.gov |  | DC-040-091ZZ | Conference Room Pilot (In Person) 1/31 - 2/4
33 | Retainer Adjustment/ Re Applying Retainers | FSM.PP055 | Project Accountant |  |  | Carrie Peterman | carrie.peterman@labor.idaho.gov |  | MF-280-022ZZ | Conference Room Pilot (In Person) 1/31 - 2/4
34 | Backout & Reallocate FES Transactions | FSM.PP056 | Project Accountant |  |  | Carrie Peterman | carrie.peterman@labor.idaho.gov |  | MF-020-051ZZ | Conference Room Pilot (In Person) 1/31 - 2/4
35 | Review Partially Billed Transactions | FSM.PP057 | Project Accountant |  |  | Carrie Peterman | carrie.peterman@labor.idaho.gov |  | MF-280-030: Grant Billing Processing | Conference Room Pilot (In Person) 1/31 - 2/4
36 | Move Project within Structure | FSM.PP059 | Project Accountant |  |  | Carrie Peterman | carrie.peterman@labor.idaho.gov |  | MF-050-010: Set up Project | Conference Room Pilot (In Person) 1/31 - 2/4
37 | Copy Posting project | FSM.PP060 | Project Accountant |  |  | Carrie Peterman | carrie.peterman@labor.idaho.gov |  | MF-050-010: Set up Project | Conference Room Pilot (In Person) 1/31 - 2/4
38 | Copy Project Funding Source | FSM.PP061 | Project Accountant |  |  | Carrie Peterman | carrie.peterman@labor.idaho.gov |  | MF-050-010: Set up Project | Conference Room Pilot (In Person) 1/31 - 2/4
39 | Change SEFA flag | FSM.PP062 | Project Accountant |  |  | Carrie Peterman | carrie.peterman@labor.idaho.gov |  | MF-050-010: Set up Project | Conference Room Pilot (In Person) 1/31 - 2/4
40 | Change PoP for Specific System Code on a Posting Project | FSM.PP063 | Project Accountant |  |  | Carrie Peterman | carrie.peterman@labor.idaho.gov |  | MF-050-010: Set up Project | Conference Room Pilot (In Person) 1/31 - 2/4

## Project 1.3 Reports and Inquiry
Project closing takes place after project processing generally).
SIT 3 Scenario - Closing Projects
Agency:
SIT 3 Week - Week 6: 2/7 - 2/11 & Week 7: 2/14 - 2/18
Sequence | Script ID | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Project Close | FSM.PC001 | Project Accountant | Create, maintain, and close projects and grants, with billing, receiving, and cost allocations. | Assigned Agency | Carrie Peterman | carrie.peterman@labor.idaho.gov |  | MF-050-090 | 2022-02-15 | 8:45-9:30 AM
2 | Review Project | FSM.PIN001 | Project Accountant | Create, maintain, and close projects and grants, with billing, receiving, and cost allocations. | Assigned Agency | Carrie Peterman | carrie.peterman@labor.idaho.gov |  | DC-030-080 | 2022-02-15 | 9:30-10AM
3 | GL Journal Transaction Detail | FSM.PIN002 | Project Accountant | Create, maintain, and close projects and grants, with billing, receiving, and cost allocations. | Assigned Agency | Carrie Peterman | carrie.peterman@labor.idaho.gov |  | DC-030-080 | 2022-02-15 | 10-10:30 AM
4 | Project Searches - Transactions | FSM.PIN003 | Project Accountant | Create, maintain, and close projects and grants, with billing, receiving, and cost allocations. | Assigned Agency | Carrie Peterman | carrie.peterman@labor.idaho.gov |  | DC-030-080 | 2022-02-15 | 10:30 - 11 AM
5 | View all Contact Invoices & all invoices Lines | FSM.PIN004 | Project Accountant | Create, maintain, and close projects and grants, with billing, receiving, and cost allocations. | Assigned Agency | Carrie Peterman | carrie.peterman@labor.idaho.gov |  | DC-030-080 | 2022-02-15 | 1-1:30PM
6 | Assign Reports | FSM.PRP001 | Project Accountant | Create, maintain, and close projects and grants, with billing, receiving, and cost allocations. | Assigned Agency | Carrie Peterman | carrie.peterman@labor.idaho.gov |  | DC-030-080 | 2022-02-15 | 1:30-2PM
7 | View Project Report | FSM.PRP002 | Project Accountant | Create, maintain, and close projects and grants, with billing, receiving, and cost allocations. | Assigned Agency | Carrie Peterman | carrie.peterman@labor.idaho.gov |  | DC-030-080 | 2022-02-15 | 2-2:30PM
8 | Personalize Report | FSM.PRP003 | Project Accountant | Create, maintain, and close projects and grants, with billing, receiving, and cost allocations. | Assigned Agency | Carrie Peterman | carrie.peterman@labor.idaho.gov |  | DC-030-080 | 2022-02-15 | 2:30-3PM
9 | View Funding Source List | FSM.PRA001 | Project Accountant | Create, maintain, and close projects and grants, with billing, receiving, and cost allocations. | Assigned Agency | Carrie Peterman | carrie.peterman@labor.idaho.gov |  | DC-030-080 | 2022-02-15 | 3 - 3:30 PM
10 | View Project Contract Reports | FSM.PRA002 | Project Accountant | Create, maintain, and close projects and grants, with billing, receiving, and cost allocations. | Assigned Agency | Carrie Peterman | carrie.peterman@labor.idaho.gov |  | DC-030-080 | 2022-02-15 | 3:30 - 4 PM
11 | View Payables Reports | FSM.PRA003 | Financials Viewer |  | Assigned Agency | Ben Thill | ben.thill@labor.idaho.gov |  | DC-030-080 | 2022-02-16 | 8:45-9:30 AM
12 | View Budget Reports | FSM.PRA004 | Project Accountant | Create, maintain, and close projects and grants, with billing, receiving, and cost allocations. | Assigned Agency | Carrie Peterman | carrie.peterman@labor.idaho.gov |  | DC-030-080 | 2022-02-16 | 9:30-10AM
13 | View Receivables Reports | FSM.PRA005 | Financials Viewer |  | Assigned Agency | Ben Thill | ben.thill@labor.idaho.gov |  | DC-030-080 | 2022-02-16 | 10-10:30 AM
14 | View d/EPM Dashboard Reports | FSM.PBI001 | Project Accountant | Create, maintain, and close projects and grants, with billing, receiving, and cost allocations. | Assigned Agency | Carrie Peterman | carrie.peterman@labor.idaho.gov |  | DC-030-080 | 2022-02-16 | 10-10:30 AM

## AR Credit Monitoring
SIT 3 Scenario - AR Credit Monitoring
Agency:
SIT Week - Week 6 - 2/7 - 2/11
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | ALM SIT 3 Test ID# | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution Date | Window to Complete Script
1 | Finance Charge Code Setup | 2845 | 12021 | Receivables Manager | Reconcile accounts receivables & collections and assess late fees. | Assigned Agency | Jamee Zahm | jamee.zahm@labor.idaho.gov |  | MF-260-010 | 2022-02-07 | 8:45-10 AM
2 | Finance Charge Text Code Setup | 2846 | 12022 | Receivables Manager | Reconcile accounts receivables & collections and assess late fees. | Assigned Agency | Jamee Zahm | jamee.zahm@labor.idaho.gov |  | MF-260-010 | 2022-02-07 | 8:45-10 AM
3 | Run Finance Charge Initiation | 8680 | 12018 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Georgann Mayer | georgann.mayer@labor.idaho.gov |  | MF-260-030 | 2022-02-07 | 10 AM-2 PM
4 | Run Finance Charge Late Payment | 8681 | 12020 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Georgann Mayer | georgann.mayer@labor.idaho.gov |  | MF-260-120 | 2022-02-07 | 10 AM-2 PM
5 | Create an Invoice Write Off | 10995 | 12019 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Georgann Mayer | georgann.mayer@labor.idaho.gov |  | MF-260-120 | 2022-02-07 | 10 AM-2 PM
6 | Run Customer Statements | 10986 | 12023 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Georgann Mayer | georgann.mayer@labor.idaho.gov |  | MF-260-060 | 2022-02-08 | 8:45 - 11 AM
7 | Run Advanced Dunning Letter Selection | 11409 | 12024 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Georgann Mayer | georgann.mayer@labor.idaho.gov |  | MF-260-120 | 2022-02-08 | 8:45 - 11 AM
8 | Run Advanced Dunning Letter File Generation | 11410 | 12025 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Georgann Mayer | georgann.mayer@labor.idaho.gov |  | MF-260-120 | 2022-02-08 | 8:45 - 11 AM
9 | Run Company Aging Report | 11898 | 12027 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Georgann Mayer | georgann.mayer@labor.idaho.gov |  | MF-260-110 | 2022-02-08 | 8:45 - 11 AM
10 | Run Customer Aging Report | 11899 | 12028 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Georgann Mayer | georgann.mayer@labor.idaho.gov |  | MF-260-110 | 2022-02-08 | 1- 2PM
11 | Review Invoices Paid Late | 11896 | 12026 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Georgann Mayer | georgann.mayer@labor.idaho.gov |  | MF-260-110 | 2022-02-08 | 1- 2PM

## Svc Cntract Interagency Billing
Completed by DOP/Luma Team
SIT 3 Scenario - Service Contract Procure to Pay Interagency Billing
Agency:
SIT Week - Week 6 - 2/7 - 2/11
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Create Requisition for Service | 8323 | 11936 | Requester | Determines requirements & cost estimates for purchase of goods & services. Submits purchase requisition. | Assigned Agency | Carrie Parks | carrie.parks@labor.idaho.gov |  | PR-020-010 | 2022-02-08 | 8:45-9:30 AM
2 | Approve Requisition | 8539 | 11929 | Approver | Approve transactions such as requisitions, purchase orders, solicitations, and journal entries. | Assigned Agency | Various (Dependant on cost center) |  |  | PR-020-020 | 2022-02-08 | 9:30-10AM
3 | Identify Requistions to send to Sourcing Event | 2896 | 11934 | Buyer | Review requisitions & create purchase orders. Conduct market research & monitor vendor commitments. Approve vendor returns. | Assigned Agency | Linda Redford | Linda.Redford@labor.idaho.gov |  | PR-020-020 | 2022-02-08 | 10-11AM
4 | Create Sourcing Event RFP | 7186 | 11949 | Sourcing Manager | Create souring events, evaluate supplier responses, and oversee selection & award of sourcing events. | Assigned Agency | Linda Redford and DOP Tester | Linda.Redford@labor.idaho.gov - contractadmin@adm.idaho.gov |  | PR-030-020 | 2022-02-08 | 1-1:30PM | Jason Skelton and ask for clarity.
5 | Approve Sourcing Event to Post | 7191 | 11941 | Approver | Approve transactions such as requisitions, purchase orders, solicitations, and journal entries. | Assigned Agency | DOP Tester | contractadmin@adm.idaho.gov |  | PR-030-010 | 2022-02-08 | 1:30-2PM
6 | Supplier Responds to Event | 1249 | 11944 | Supplier (Luma Team Member) |  | DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-030-020 | 2022-02-08 | 2-2:30PM
7 | Analyze and Award Suppler Responses | Refer to upload Template | 11952 | Sourcing Manager | Create souring events, evaluate supplier responses, and oversee selection & award of sourcing events. | Assigned Agency | DOP Tester | contractadmin@adm.idaho.gov |  | PR-030-050 | 2022-02-08 | 2:30-3PM
8 | Sourcing Event Award Approval | 7191 | 11947 | Approver | Approve transactions such as requisitions, purchase orders, solicitations, and journal entries. | Assigned Agency | DOP Tester | contractadmin@adm.idaho.gov |  | PR-030-040 | 2022-02-08 | 3-3:30PM
9 | Create Contract - Create a Contract - Contract Tab | 7219 | 11942 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | Assigned Agency/DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-010 | 2022-02-09 | 8:45 - 10:30AM
10 | Create Contract - Contract Draft - Articles Tab | 7204 | 11951 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | Assigned Agency/DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-010 | 2022-02-09 | 8:45 - 10:30AM
11 | Create Contract - Contract Draft - Participants Tab | 2667 | 11950 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | Assigned Agency/DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-010 | 2022-02-09 | 8:45 - 10:30AM
12 | Create Contract - Contract Draft - Lines Tab - Service | 3375 | 11948 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | Assigned Agency/DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-010 | 2022-02-09 | 8:45 - 10:30AM
13 | Create Contract - Contract Draft - Contacts Tab | 3335 | 11940 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | Assigned Agency/DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-010 | 2022-02-09 | 8:45 - 10:30AM
14 | Create Contract - Contract Draft - Releasing a Contract | 7203 | 11930 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | Assigned Agency/DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-010 | 2022-02-09 | 8:45 - 10:30AM
15 | Contract Approval | 8353 | 11939 | Approver | Compile contract file including entering contract line item details, terms & conditions along with pricing. | Assigned Agency/DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-010 | 2022-02-09 | 8:45 - 10:30AM
16 | Create Contract - Contract Draft - Activating a Contract | 7202 | 11931 | Contract Manager | Approve transactions such as requisitions, purchase orders, solicitations, and journal entries. | Assigned Agency | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-010 | 2022-02-09 | 10:30-11AM
17 | Create Contract Invoice | 11459 | 11933 | Payables Invoice Processor | Process interface and XM files. Match payables invoices, and vendor list. Process payables payments. Generate 1099. | Assigned Agency | Ben Thill | ben.thill@labor.idaho.gov |  | MF-070-050 Enter a PO Invoice | 2022-02-09 | 1 - 1:30PM
18 | Approve Invoice | 11460 | 11938 | Payables Manager | Void & cancel payments. Reissue & mail warrants. Process period close. | Assigned Agency | Nancy Fulfer | nancy.fulfer@labor.idaho.gov |  | MF-070-056 Invoice Approval Process | 2022-02-09 | 1:30 -3:30 PM
19 | Match Invoice | 11462 | 11946 | Payables Manager | Void & cancel payments. Reissue & mail warrants. Process period close. | Assigned Agency | Nancy Fulfer | nancy.fulfer@labor.idaho.gov |  | MF-070-070 Match Invoices | 2022-02-09 | 1:30 -3:30 PM
20 | Process Payment for Invoice | 11442 | 11932 | Payables Manager | Void & cancel payments. Reissue & mail warrants. Process period close. | Assigned Agency | Nancy Fulfer | nancy.fulfer@labor.idaho.gov |  | MF-070-100 Process Invoice Payments | 2022-02-09 | 1:30 -3:30 PM
21 | Create Interagency Billing - Basic | 8795 | 11945 | Intercompany Billing Specialist | Handle setup and processing of intercompany billing. | Assigned Agency | Nancy Fulfer | nancy.fulfer@labor.idaho.gov |  | MF-260-030ZZ | 2022-02-10 | 8:45-9:30 AM
22 | Identify Unpaid Interagency Billings | 11536 | 11937 | Payables Invoice Processor | Process interface and XM files. Match payables invoices, and vendor list. Process payables payments. Generate 1099. | Assigned Agency | Ben Thill | ben.thill@labor.idaho.gov |  | MF-070-050 Enter a PO Invoice | 2022-02-10 | 9:30-10AM
23 | Reclassify Interagency Expenditure Coding (AP110 Distribution Changes on Paid Invoice) | 11624 | 11935 | Payables Invoice Processor | Process interface and XM files. Match payables invoices, and vendor list. Process payables payments. Generate 1099. | Assigned Agency | Ben Thill | ben.thill@labor.idaho.gov |  | MF-070-050 Enter a PO Invoice | 2022-02-10 | 10-11AM
24 | Settle an Interagency Billing | 8794 | 11943 | Intercompany Billing Specialist | Handle setup and processing of intercompany billing. | Assigned Agency | Nancy Fulfer | nancy.fulfer@labor.idaho.gov |  | MF-260-030ZZ | 2022-02-10 | 1-1:30PM

## Cash Ledger Payment
SIT 3 Scenario - Cash Ledger Payment
Agency:
SIT Week - Week 7 - 2/14 -2/18
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Enter Cash Payment | Cash Payment Entry.xlsx | 12075 | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Ron Hanson | Ron.Hanson@labor.idaho.gov | Rotary/Site Draft, L Warrants |  | 2022-02-14 | 8:45 - 10 AM
1A | Record Cash Payment |  | 12525 | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Ron Hanson | Ron.Hanson@labor.idaho.gov |  |  | 2022-02-14 | 8:45 - 10 AM
2 | Approve Cash Payment | Cash Approve Cash Payment.xlsx | 12076 | Cash Manager | Manage all cash transactions. Review and update cash management policy as needed. | Assigned Agency | Nancy Fulfer | Nancy.Fulfer@labor.idaho.gov |  |  | 2022-02-14 | 10 - 11:30 AM
3 | Cash Requirements | Cash Requirements.xlsx | 12077 | Payables Payment Processor | Perform Cash Requirements, Schedule Payments, Complete Payment Cycle | Assigned Agency | Michelle French | michelle.french@labor.idaho.gov |  | MF-070-100 Process Invoice Payments | 2022-02-14 | 1 - 2:30 PM
4 | Review Check in Cash | Cash Review Check in Cash Management.xlsx | 12078 | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Ron Hanson | Ron.Hanson@labor.idaho.gov | Redeem or Void then Review again |  | 2022-02-14 | 2:30 - 4 PM
5 | Journalize Distributions | Cash Journalize Cash Transaction.xlsx | 12079 | Cash Manager | Manage all cash transactions. Review and update cash management policy as needed. | Assigned Agency | Nancy Fulfer | Nancy.Fulfer@labor.idaho.gov |  |  | 2022-02-15 | 8:45 - 10 AM
6 | Verify Results in Global Ledger Account Analysis |  | 12082 | Staff Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Chey Martineau | chey.martineau@labor.idaho.gov |  |  | 2022-02-15 | 10 - 11:30 AM
7 | Optional Void Cash Payment for Status Updates | Cash Void Cash Payment.xlsx | 12080 | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Ron Hanson | Ron.Hanson@labor.idaho.gov |  |  | 2022-02-15 | 1 - 2:30 PM
8 | Optional Void Cash Payment: Payment Void Stop Pay Update | 12161 | 12161 | Payables Payment Processor | Perform Cash Requirements, Schedule Payments, Complete Payment Cycle | Assigned Agency | Ben Thill | ben.thill@labor.idaho.gov |  |  | 2022-02-15 | 1 - 2:30 PM
9 | Optional Redeem Warrant for Status Updates | Cash Redeem Warrant.xlsx | 12081 | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Ron Hanson | Ron.Hanson@labor.idaho.gov |  |  | 2022-02-15 | 2:30 - 4 PM
Note on K5: Glenda Smith: Cash BPR's are not correct, do not reference.

## Interagency Billing to Settleme
SIT 3 Scenario - Interagency Billing to Settlement
Agency:
SIT Week - Week 7 - 2/14 -2/18
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Create Interagency Billing - Basic | 8795 | 11909 | Intercompany Billing Specialist | Handle setup and processing of intercompany billing. | Assigned Agency | Nancy Fulfer | nancy.fulfer@labor.idaho.gov |  | MF-260-030ZZ | 2022-02-14 | 8:45-9:30 AM
2 | Identify Unpaid Interagency Billings | 11536 | 11907 | Payables Invoice Processor | Process interface and XM files. Match payables invoices, and vendor list. Process payables payments. Generate 1099. | Assigned Agency | Ron Hanson | Ronald.hanson@labor.idaho.gov |  | MF-070-050 Enter a PO Invoice | 2022-02-14 | 9:30 - 10:30 AM
3 | Reclassify Interagency Expenditure Coding (AP110 Distribution Changes on Paid Invoice) | 11624 | 11906 | Payables Invoice Processor | Process interface and XM files. Match payables invoices, and vendor list. Process payables payments. Generate 1099. | Assigned Agency | Ron Hanson | Ronald.hanson@labor.idaho.gov |  | MF-070-050 Enter a PO Invoice | 2022-02-14 | 10:30 -11:30 AM
4 | Settle an Interagency Billing | 8794 | 11908 | Intercompany Billing Specialist | Handle setup and processing of intercompany billing. | Assigned Agency | Nancy Fulfer | nancy.fulfer@labor.idaho.gov |  | MF-260-030ZZ | 2022-02-14 | 1-1:30PM

## Nonstate Billing
SIT 3 Scenario - Non-State Billing_Master
Agency:
SIT Week - Week 7 - 2/14 -2/18
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 TEST ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Create Manual Batch Header | 10963 | 12456 | Billing Manager | Create and maintain bills for Accounts Receivable. | Assigned Agency | Georgann Mayer | georgann.mayer@labor.idaho.gov | Interfaced Invoices, Recurring Invoices | MF-260-030 | 2022-02-14 | 8:45-9:30 AM
2 | Create Billing Invoice | 10962 | 12449 | Billing Manager | Create and maintain bills for Accounts Receivable. | Assigned Agency | Georgann Mayer | georgann.mayer@labor.idaho.gov |  | MF-260-030 | 2022-02-14 | 9:30-10AM
3 | Create Credit Memo | 11562 | 12446 | Billing Manager | Create and maintain bills for Accounts Receivable. | Assigned Agency | Georgann Mayer | georgann.mayer@labor.idaho.gov | Debit Memo | MF-260-100 | 2022-02-14 | 10-10:30 AM
4 | Approve Invoice Batch | 11603 | 12452 | Billing Manager | Create and maintain bills for Accounts Receivable. | Assigned Agency | Georgann Mayer | georgann.mayer@labor.idaho.gov |  | MF-260-060 | 2022-02-14 | 10:30 - 11 AM
5 | Run Invoice Batch Release | 10966 | 12465 | Billing Manager | Create and maintain bills for Accounts Receivable. | Assigned Agency | Georgann Mayer | georgann.mayer@labor.idaho.gov |  | MF-260-060 | 2022-02-14 | 1-1:30PM
6 | Run Invoice Register and Print | 3511 | 12459 | Billing Manager | Create and maintain bills for Accounts Receivable. | Assigned Agency | Georgann Mayer | georgann.mayer@labor.idaho.gov |  | MF-260-060 | 2022-02-14 | 1:30-2PM
7 | Run Sub System Update (Interface Invoices to AR and Journalize) | 10965 | 12463 | Billing Manager | Create and maintain bills for Accounts Receivable. | Assigned Agency | Georgann Mayer | georgann.mayer@labor.idaho.gov |  | MF-260-090 | 2022-02-14 | 2-2:30PM
8 | Create Invoice Batch in AR | 8661 | 12458 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Sandra Rodriguez-Martinez | SANDRA.RODRIGUEZ-MARTINEZ@labor.idaho.gov |  | MF-260-060 | 2022-02-14 | 2:30-3PM
9 | Create Invoice in AR | 8660 | 12447 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Sandra Rodriguez-Martinez | SANDRA.RODRIGUEZ-MARTINEZ@labor.idaho.gov | Interfaced Invoices | MF-260-030 | 2022-02-14 | 3 - 3:30 PM
10 | Create Credit Memo in AR | 2812 | 12451 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Sandra Rodriguez-Martinez | SANDRA.RODRIGUEZ-MARTINEZ@labor.idaho.gov | Debit Memo | MF-260-050 | 2022-02-14 | 3:30 - 4 PM
11 | Approve AR Invoice (if not interfaced from BL) | 11603 | 12472 | Receivables Manager | Reconcile accounts receivables & collections and assess late fees. | Assigned Agency | Jamee Zahm | jamee.zahm@labor.idaho.gov |  | MF-260-ZZ | 2022-02-15 | 8:45-9:30 AM
12 | Run Journalize Preview | 8662 | 12466 | Receivables Manager | Reconcile accounts receivables & collections and assess late fees. | Assigned Agency | Jamee Zahm | jamee.zahm@labor.idaho.gov |  | MF-260-090 | 2022-02-15 | 9:30-10AM
13 | Run Journalize Distributions |  | 12464 | Receivables Manager | Reconcile accounts receivables & collections and assess late fees. | Assigned Agency | Jamee Zahm | jamee.zahm@labor.idaho.gov |  | MF-260-090 | 2022-02-15 | 10-10:30 AM
14 | Create Payment Batch | 8668 | 12457 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Sandra Rodriguez-Martinez | SANDRA.RODRIGUEZ-MARTINEZ@labor.idaho.gov | Interfaced Payments | MF-260-070 | 2022-02-15 | 10:30 - 11 AM
15 | Create Customer Payment | 8666 | 12448 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Sandra Rodriguez-Martinez | SANDRA.RODRIGUEZ-MARTINEZ@labor.idaho.gov | Interfaced Payments | MF-260-070 | 2022-02-15 | 1-1:30PM
16 | Create Payment Remittance | 11895 | 12470 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Sandra Rodriguez-Martinez | SANDRA.RODRIGUEZ-MARTINEZ@labor.idaho.gov |  | MF-260-070 | 2022-02-15 | 1:30-2PM
17 | Create Non AR Cash Payment | 8673 | 12468 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Sandra Rodriguez-Martinez | SANDRA.RODRIGUEZ-MARTINEZ@labor.idaho.gov | Interfaced Payments | MF-260-070 | 2022-02-15 | 2-2:30PM
18 | Apply Payment to Invoice | 8669 | 12460 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Sandra Rodriguez-Martinez | SANDRA.RODRIGUEZ-MARTINEZ@labor.idaho.gov | Automatic Cash Application | MF-260-080 | 2022-02-15 | 2:30-3PM
19 | Apply Credit Memo to Invoice | 2513 | 12469 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Sandra Rodriguez-Martinez | SANDRA.RODRIGUEZ-MARTINEZ@labor.idaho.gov | Automatic Memo Application | MF-260-100 | 2022-02-15 | 3 - 3:30 PM
20 | Approve Payment Batch | 11603 | 12473 | Receivables Manager | Reconcile accounts receivables & collections and assess late fees. | Treasury | Jamee Zahm | jamee.zahm@labor.idaho.gov |  | MF-260-ZZ | 2022-02-15 | 3:30 - 4 PM
21 | Create Payment Application Reversal | 11064 | 12450 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Sandra Rodriguez-Martinez | SANDRA.RODRIGUEZ-MARTINEZ@labor.idaho.gov |  | MF-260-ZZ | 2022-02-16 | 8:45-9:30 AM
22 | Run Application Reversal Creation | 11065 | 12455 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Sandra Rodriguez-Martinez | SANDRA.RODRIGUEZ-MARTINEZ@labor.idaho.gov |  | MF-260-ZZ | 2022-02-16 | 9:30-10AM
23 | Application Close | 8670 | 12462 | Receivables Manager | Reconcile accounts receivables & collections and assess late fees. | Assigned Agency | Jamee Zahm | jamee.zahm@labor.idaho.gov |  | MF-260-130 | 2022-02-16 | 10-10:30 AM
24 | Run Journalize Preview | 8671 | 12467 | Receivables Manager | Reconcile accounts receivables & collections and assess late fees. | Assigned Agency | Jamee Zahm | jamee.zahm@labor.idaho.gov |  | MF-260-090 | 2022-02-16 | 10:30 - 11 AM
25 | Run Journalize Distributions | 8672 | 12474 | Receivables Manager | Reconcile accounts receivables & collections and assess late fees. | Assigned Agency | Jamee Zahm | jamee.zahm@labor.idaho.gov |  | MF-260-090 | 2022-02-16 | 1-1:30PM
26 | Reconcile AR module to GL balance (Account Analysis/Reports) | 11672 | 12453 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate, and update allocations. | Assigned Agency | Chey Martineau | chey.martineau@labor.idaho.gov |  | MF-260-090 | 2022-02-16 | 1:30-2PM
27 | View Cash Fund Balance | Cash Fund Balance.lxsx - maybe in ALM already |  | Financial Viewer | View-only access to key financial workstreams and structures, such as Chart of Accounts, financial reports, and financial transaction data. | Assigned Agency | Michelle French | Michelle.French@labor.idaho.gov |  | MF-260-090 | 2022-02-16 | 2-2:30PM
28 | Create Return to Maker Payment | 11120 | 12454 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Sandra Rodriguez-Martinez | SANDRA.RODRIGUEZ-MARTINEZ@labor.idaho.gov |  | MF-260-ZZ | 2022-02-16 | 2:30-3PM
29 | Release Return to Maker Payment | 11124 | 12461 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Sandra Rodriguez-Martinez | SANDRA.RODRIGUEZ-MARTINEZ@labor.idaho.gov |  | MF-260-ZZ | 2022-02-16 | 3 - 3:30 PM
30 | Create Payment Reversal | 11064 | 12475 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Sandra Rodriguez-Martinez | SANDRA.RODRIGUEZ-MARTINEZ@labor.idaho.gov |  | MF-260-ZZ | 2022-02-16 | 3:30 - 4 PM
31 | Run Application Reversal Creation | 11065 | 12476 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Sandra Rodriguez-Martinez | SANDRA.RODRIGUEZ-MARTINEZ@labor.idaho.gov |  | MF-260-ZZ | 2022-02-17 | 8:45-9:30 AM

## Procure to Pay Vendor Mgt Voids
SIT 3 Scenario - Procure to Pay with Void and Vendor Update
Agency:
SIT Week - Week 7 - 2/14 -2/18
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | Luma Role (role switcher) | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Create Requisition - Special | 8324 | Requester | Assigned Agency | Carrie Parks | carrie.parks@labor.idaho.gov |  | PR-020-010 | 2022-02-14 | 8:45-9:30 AM
2 | Approve Requisition | 8539 | Approver | Assigned Agency | Various (Dependant on cost center) |  | Requisition not approved | PR-010-060 | 2022-02-14 | 9:30-10AM
3 | Create Purchase Order | 8170 | Buyer | Assigned Agency | Linda Redford | Linda.Redford@labor.idaho.gov |  | PR-050-040 | 2022-02-14 | 10-10:30 AM
4 | Receive Purchase Order | 4587 | Receiver | Assigned Agency | Tony Hartz | tony.hartz@labor.idaho.gov |  | PR-050-070 | 2022-02-14 | 10:30 - 11 AM
5 | Create Invoice | 11519 | Payables Invoice Processor | Assigned Agency | Ron Hansen | Ronald.hanson@labor.idaho.gov |  | MF-070-050 Enter a PO Invoice | 2022-02-14 | 1-1:30PM
6 | Approve Invoice | 11520 | Approver | Assigned Agency | Various (Dependant on cost center) |  |  | MF-070-056 Invoice Approval Process | 2022-02-14 | 1:30-2PM
7 | Match Invoice | 11458 | Payables Manager | Assigned Agency | Nancy Fulfer | nancy.fulfer@labor.idaho.gov |  | MF-070-070 Match Invoices | 2022-02-14 | 2-2:30PM
8 | Process Payment for Invoice | 11442 | Payables Manager | Assigned Agency | Nancy Fulfer | nancy.fulfer@labor.idaho.gov |  | MF-070-100 Process Invoice Payments | 2022-02-14 | 2:30-3PM
9 | Journalize | 11440 | Payables Manager |  | Nancy Fulfer | nancy.fulfer@labor.idaho.gov |  | MF-070-110 Journalize AP Distributions | 2022-02-14 | 3 - 3:30 PM
10 | Void Payment | 12080 | Cash Accountant | SCO | Michelle French | Michelle.French@labor.idaho.gov |  | MF-200-060 Void Cash Transactions | 2022-02-14 | 3:30 - 4 PM
11 | Cancel Invoice | 11523 | Payables Manager | Assigned Agency | Nancy Fulfer | nancy.fulfer@labor.idaho.gov |  | MF-070-050 Enter a PO Invoice | 2022-02-15 | 8:45-9:30 AM
12 | Request a new vendor | 11524 | Payables Invoice Processor | Assigned Agency | Ron Hansen | Ronald.hanson@labor.idaho.gov |  | PR-040-030 Create and Maintain Vendor | 2022-02-15 | 9:30-10AM
13 | Approve and setup new vendor | 11525 - Only SCO staff can do this | Approver | SCO | Nancy Fulfer | nancy.fulfer@labor.idaho.gov | Disapprove vendor | PR-040-030 Create and Maintain Vendor | 2022-02-15 | 10-10:30 AM
14 | Create Invoice | 11519 | Payables Invoice Processor | Assigned Agency | Ron Hansen | Ronald.hanson@labor.idaho.gov |  | MF-070-050 Enter a PO Invoice | 2022-02-15 | 10:30 - 11 AM
15 | Approve Invoice | 11520 | Approver | Assigned Agency | Various (Dependant on cost center) |  |  | MF-070-056 Invoice Approval Process | 2022-02-15 | 1-1:30PM
16 | Match Invoice | 11522 | Payables Invoice Processor | Assigned Agency | Ron Hansen | Ronald.hanson@labor.idaho.gov |  | MF-070-070 Match Invoices | 2022-02-15 | 1:30-2PM
17 | Process Payment for Invoice | 11442 | Payables Manager | Assigned Agency | Nancy Fulfer | nancy.fulfer@labor.idaho.gov |  | MF-070-100 Process Invoice Payments | 2022-02-15 | 2-2:30PM
18 | Post Transactions - Journalize | 11440 | Payables Manager | Assigned Agency | Nancy Fulfer | nancy.fulfer@labor.idaho.gov |  | MF-070-110 Journalize AP Distributions | 2022-02-15 | 2:30-3PM
19 | Cash Ledger Journalize | 12079 | Cash Manager | Assigned Agency | Simon So | simon.so@labor.idaho.gov |  | MF-200-050 Reconcile Payments Payables and Disbursements | 2022-02-15 | 3 - 3:30 PM
20 | Verify Voided Payables Checks | 12153 | Cash Accountant | Assigned Agency | Michelle French | Michelle.French@labor.idaho.gov |  | MF-200-060 Void Cash Transactions | 2022-02-15 | 3:30 - 4 PM
21 | View Fund Balance | Cash Fund Balance.xlsx (in ALM?)(in Cash Deposit to Revenue Scenario) | Cash Accountant | Assigned Agency | Michelle French | Michelle.French@labor.idaho.gov |  | MF-200-050 Reconcile Payments Payables and Disbursements | 2022-02-16 | 8:45-9:30 AM
22 | Comparative report from Birst |  | Cash Accountant | Assigned Agency | Michelle French | Michelle.French@labor.idaho.gov |  | MF-200-ZZ | 2022-02-16 | 9:30-10AM
23 | Cash Revenue Daily Report - Birst |  | Cash Manager | Assigned Agency | Simon So | simon.so@labor.idaho.gov |  | MF-200-ZZ | 2022-02-16 | 10-10:30 AM

## Custodial Account Set Up
SIT 3 Scenario - Custodial Account Set Up
Agency:
SIT Week - Week 8 - 2/21/ - 2/25
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Custodial Account Setup | TBD | 12071 | Custodial Account Manager | Monitor financial structure and Chart of Account dimensions for their Agency and recommendations for updates. Manage all financial processes. | Assigned Agency | JoAnna Henry | joanna.henry@labor.idaho.gov |  |  | 2022-02-22 | 8:45 - 10AM
2 | CAM Structure Setup | Refer to Upload Template | 12072 | Custodial Account Manager | 0 | Assigned Agency | JoAnna Henry | joanna.henry@labor.idaho.gov |  |  | 2022-02-22 | 10 - 11:30 AM
3 | Custodial Account Hierarchy Setup | Refer to Upload Template | 12073 | Custodial Account Manager | Monitor financial structure and Chart of Account dimensions for their Agency and recommendations for updates. Manage all financial processes. | Assigned Agency | JoAnna Henry | joanna.henry@labor.idaho.gov |  |  | 2022-02-22 | 1 - 2:30 PM
4 | Custodial Account Record Setup | Refer to Upload Template | 12074 | Custodial Account Manager | 0 | Assigned Agency | JoAnna Henry | joanna.henry@labor.idaho.gov |  |  | 2022-02-22 | 2:30 -4 PM

## Global Ledger Entries and Analy
SIT 3 Scenario - Global Legder Processing and Analysis
Agency:
SIT Week - Week 8 - 2/21/ - 2/25
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Create a Front-End Split Journal Entry (Front End Split Projects Only) | Refer to Upload Template | 12154 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Chey Martineau | chey.martineau@labor.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-010 | 2022-02-23 | 8:45-9:30 AM
2 | Create a Journal Entry | Refer to Upload Template | 11668 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Chey Martineau | chey.martineau@labor.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-010 | 2022-02-23 | 9:30-10AM
3 | Approve a Journal Entry | Refer to Upload Template | 11669 | Approver | Approve transactions such as requisitions, purchase orders, solicitation & journal entries. | Assigned Agency | Jamee Zahm | jamee.zahm@labor.idaho.gov |  | MF-025-060 | 2022-02-23 | 10-11AM
4 | Create a Journal Entry from an Existing Journal | Refer to Upload Template | 11671 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Chey Martineau | chey.martineau@labor.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-010 | 2022-02-23 | 1-1:30PM
5 | Create a Journal Entry from a Template | Refer to Upload Template | 11670 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Chey Martineau | chey.martineau@labor.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-010 | 2022-02-23 | 1:30-2PM
6 | Create a Recurring Journal | Refer to Upload Template | 11673 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Chey Martineau | chey.martineau@labor.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-020 | 2022-02-23 | 2-2:30PM
7 | Journalize a Recurring Journal Entry | Refer to Upload Template | 12155 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Chey Martineau | chey.martineau@labor.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-030 | 2022-02-23 | 2:30-3PM
8 | Post Multiple Journal Entries | Refer to Upload Template | 12156 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Chey Martineau | chey.martineau@labor.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-23 | 3-3:30PM
9 | Post Journals from Subsystems | Refer to Upload Template | 12157 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Chey Martineau | chey.martineau@labor.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-050 | 2022-02-24 | 8:45-9:30 AM
10 | Validate (here) Reconcile (close) Subsystems to the General Ledger | Bill will put these scripts here and in close scenario | TBD | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Chey Martineau | chey.martineau@labor.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-24 | 9:30-10AM
11 | Analyze Global Ledger Totals | Refer to Upload Template | 12158 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Chey Martineau | chey.martineau@labor.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-24 | 10-11AM
12 | Perform Account Analysis | Refer to Upload Template | 11672 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Chey Martineau | chey.martineau@labor.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-24 | 1-1:30PM
13 | Perform Fund Analysis | Refer to Upload Template | 12159 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Chey Martineau | chey.martineau@labor.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-24 | 1:30-2PM
14 | Perform Organizational Unit Analysis | Refer to Upload Template | 12160 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Chey Martineau | chey.martineau@labor.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-24 | 2-2:30PM
15 | View Transactions by Entity-Account | Refer to Upload Template | 11674 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Chey Martineau | chey.martineau@labor.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-25 | 9- 9:30 AM
16 | BIRST/BI/CSF Analytic Reporting |  | TBD | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Chey Martineau | chey.martineau@labor.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-25 | 9:30 - 10 AM
17 | Evaluate Encumbrances | Placeholder - Judy and Bill (and Eileen/Cathy) are working on script for this; will have this week (12/23/21) | TBD | Staff Accountant |  | Assigned Agency | Chey Martineau | chey.martineau@labor.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-25 | 10 - 11 AM

## Punchout Request to Payment
SIT 3 Scenario - Punchout Request to Payment
Agency:
SIT Week - Week 8 - 2/21 - 2/25
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Create Punchout Requisition using RSS | 3501 | 11924 | Requester | Determines requirements & cost estimates for purchase of goods & services. Submits purchase requisition. | Assigned Agency | Carrie Parks | carrie.parks@labor.idaho.gov |  | PR-020-010 | 2022-02-22 | 8:45-9:30 AM
2 | Approve Requisition | 8539 | 11925 | Approver | Approve transactions such as requisitions, purchase orders, solicitation & journal entries. | Assigned Agency | Various (Dependant on cost center) |  | Deny Requisition - add note - need more information Approve Requisition | PR-010-060 | 2022-02-22 | 9:30-10AM
3 | Locate Punchout PO | Refer to Upload template | 12034 | Requester |  |  | Carrie Parks | carrie.parks@labor.idaho.gov |  | PR-050-040 | 2022-02-22 | 10-11AM
4 | Review Punchout PO | Refer to Upload template | 11927 | Buyer | Review requisitions & create purchase orders. Conduct market research & monitor vendor commitments. Approve vendor returns. | Assigned Agency | Linda Redford | Linda.Redford@labor.idaho.gov | This will be a review of schedule job creating PO. Other variations would be manual creation, or Job run creation submitted as needed. | PR-050-040 | 2022-02-22 | 1-1:30PM
5 | Review Punchout Receipt | Refer to Upload template | 11928 | Receiver | Receive and inspect incoming goods. Pick items for shipment/transfer. Dispose of items. Vendor returns. Document variances. | Assigned Agency | Tony Hartz | tony.hartz@labor.idaho.gov | Manual release of receipt vs. auto release | PR-050-070 | 2022-02-22 | 1:30-2PM
6 | Review Punchout Invoice | 11610 | 11922 | Payables Invoice Processor | Processes interface and XM files. Match Payables invoices. Manages vendor list. Processes Payables payments. Generates 1099. | Assigned Agency | Ron Hanson | Ronald.hanson@labor.idaho.gov |  | MF-070-050 Enter a PO Invoice | 2022-02-22 | 2-2:30PM
7 | Approve Invoice | 11611 | 11923 | Approver |  |  | Various (Dependant on cost center) |  |  | MF-070-056 Invoice Approval Process | 2022-02-22 | 2:30-3PM
8 | Match Invoice | 11613 | 11926 | Payables Manager | Void & cancel payments, reissue & mail warrants. Process period close. | Assigned Agency | Nancy Fulfer | nancy.fulfer@labor.idaho.gov |  | MF-070-070 Match Invoices | 2022-02-22 | 3-3:30PM
9 | Process Invoice for Payment | 11442 | 11921 | Payables Manager | Void & cancel payments, reissue & mail warrants. Process period close. | Assigned Agency | Nancy Fulfer | nancy.fulfer@labor.idaho.gov |  | MF-070-100 Process Invoice Payments | 2022-02-22 | 3:30 - 4 PM

## Budget
DFM Approval
SIT 3 Scenario - Budget Change Request
Agency:
SIT 3 Week - Week 9 - 2/28 - 3/4
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | New SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Budget Change Request | 1974 | 11632 | Budget Analyst | Create and maintain budget templates, scenarios, and budgets. Process budget changes. | Assigned Agency | Karina Myles | karina.myles@labor.idaho.gov | Associate with project | MB-070-120 Submit Budget Adjustments for Approval | 2022-02-28 | 8:45-9:30 AM
2 | Create JE (Lines) | 1974 | 12037 | Budget Analyst | Create and maintain budget templates, scenarios, and budgets. Process budget changes. | Assigned Agency | Karina Myles | karina.myles@labor.idaho.gov |  | MB-070-110 Load Budget Adjustments | 2022-02-28 | 9:30-10:30 AM
3 | Budget Change Request 1st level Approver | 1974 | 12038 | Budget Controller | Review/monitor and manage publish results for budget, strategic plan & performance measures. | Assigned Agency | Karina Myles | karina.myles@labor.idaho.gov | Deny Requisition - add note - need more information Approve Requisition | MB-070-130 DFM Approval | 2022-02-28 | 10:30-11:30 AM
4 | Approve Budget Change Request | 1974 | 12039 | DFM Analyst | DFM will approve all Budget Change Requests made to the Appropriation Scenario only. | DFM |  |  |  | MB-070-130 DFM Approval | 2022-02-28 | 1-1:30PM
5 | Budget Scenario Upload | 1972 | 11633 | Budget Analyst | Maintain the ensures the scenario's stay in sync when a budget change request is approved. | Assigned Agency | Karina Myles | karina.myles@labor.idaho.gov | Susan feels SCO will only upload | MB-070-140 Budget Change Order Released | 2022-02-28 | 1:30-2PM
Note on J5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard

## Custodial Accounts
SIT 3 Scenario - Budget Reporting and Trust Accounting
Agency:
SIT 3 Week - Week 9 - 2/28 - 3/4
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Set up Custodial Accounts |  | TBD | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate, and update allocations. | Assigned Agency | Chey Martineau | chey.martineau@labor.idaho.gov | Associate with project | PR-050-070 | 2022-02-28 | 8:45-9:30 AM
2 | Enter cash receipt for the Custodial Account |  | TBD | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Michelle French | Michelle.French@labor.idaho.gov | Deny Requisition - add note - need more information Approve Requisition | MF-260-070 Enter Cash Receipts | 2022-02-28 | 9:30-10AM
2 | Approve Cash Receipt |  | TBD | Cash Manager | Manage all cash transactions. Review and update cash management policy as needed. | Assigned Agency | Simon So | simon.so@labor.idaho.gov |  | MF-260-070 Enter Cash Receipts | 2022-02-28 | 10-11AM
3 | Final Approval of Cash Receipt |  | TBD | Cash Manager | Manage all cash transactions. Review and update cash management policy as needed. | STO | Simon So | simon.so@labor.idaho.gov |  | MF-260-070 Enter Cash Receipts | 2022-02-28 | 1-1:30PM
4 | Journalize Cash Management |  | TBD | Cash Manager | Manage all cash transactions. Review and update cash management policy as needed. | Assigned Agency | Simon So | simon.so@labor.idaho.gov |  | MF-260-090 Post to General Ledger | 2022-02-28 | 1:30-2PM
5 | View Trust Balance report in Birst |  | TBD | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate, and update allocations. | Assigned Agency | Chey Martineau | chey.martineau@labor.idaho.gov |  |  | 2022-02-28 | 2-2:30PM
6 | Enter Invoice for trust account | 11443 | TBD | Payables Invoice Processor | Process interface and XM files. Match payables invoices, and vendor list. Process payables payments. Generate 1099. | Assigned Agency | Ron Hansen | Ronald.hanson@labor.idaho.gov |  | MF-070-060 Enter a Non-PO invoice | 2022-02-28 | 2:30-3PM
7 | Enter Comments & Attachments | 11445 | TBD | Payables Invoice Processor |  |  | Ron Hansen | Ronald.hanson@labor.idaho.gov |  | MF-070-060 Enter a Non-PO invoice | 2022-02-28 | 3-3:30PM
8 | Approve invoice | 11444 | TBD | Approver | Approve transactions such as requisitions, purchase orders, solicitations, and journal entries. | Assigned Agency | Jamee Zahm | jamee.zahm@labor.idaho.gov |  | MF-070-080 Invoice Approval Process | 2022-03-02 | 8:45-9:30 AM
9 | Run Cash Requirements | 11442 | TBD | Payables Manager | Void & cancel payments. Reissue & mail warrants. Process period close. | Assigned Agency | Nancy Fulfer | nancy.fulfer@labor.idaho.gov |  | MF-070-100 Process Invoice Payments | 2022-03-02 | 9:30-10AM
10 | Journalize Payables | 11440 | TBD | Payables Manager | Void & cancel payments. Reissue & mail warrants. Process period close. | Assigned Agency | Nancy Fulfer | nancy.fulfer@labor.idaho.gov |  | MF-070-110 Journalize Distributions | 2022-03-02 | 10-11AM
11 | View Trust Balance Report in Birst |  | TBD | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate, and update allocations. | Assigned Agency | Chey Martineau | chey.martineau@labor.idaho.gov | Receive less/more than ordered |  | 2022-03-02 | 1-1:30PM
12 | Run Average Daily Balance Report |  | TBD | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate, and update allocations. | Assigned Agency | Chey Martineau | chey.martineau@labor.idaho.gov | Inspection Failed, Vendor Return |  | 2022-03-02 | 1:30-2PM

## Chart of Accounts Maintenance
SIT 3 Scenario - Chart of Accounts Maintenance
Agency:
SIT Week - Week 10 - 3/7 - 3/11
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | View and Validate an Organizational Unit |  | TBD | Staff Accountant |  |  | Chey Martineau | chey.martineau@labor.idaho.gov |  |  | 2022-03-07 | 8:45-9:30 AM
2 | View and Validate a Project |  | TBD | Staff Accountant |  |  | Chey Martineau | chey.martineau@labor.idaho.gov |  |  | 2022-03-07 | 9:30-10AM
3 | View and Validate a Program |  | TBD | Staff Accountant |  |  | Chey Martineau | chey.martineau@labor.idaho.gov |  |  | 2022-03-07 | 10-11AM
4 | View and Validate a Location |  | TBD | Staff Accountant |  |  | Chey Martineau | chey.martineau@labor.idaho.gov |  |  | 2022-03-07 | 1-1:30PM
5 | View and Validate Additional Reporting |  | TBD | Staff Accountant |  |  | Chey Martineau | chey.martineau@labor.idaho.gov |  |  | 2022-03-07 | 1:30-2PM
6 | View and Validate Custodial Accounts (CAM) |  | TBD | Staff Accountant |  |  | Chey Martineau | chey.martineau@labor.idaho.gov |  |  | 2022-03-07 | 2-2:30PM
7 | Request a new account |  | TBD | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Chey Martineau | chey.martineau@labor.idaho.gov |  |  | 2022-03-07 | 2:30-3PM
8 | Request a new organizational unit |  | TBD | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Chey Martineau | chey.martineau@labor.idaho.gov |  |  | 2022-03-07 | 3-3:30PM
9 | View and Validate Beginning Balances |  | TBD | Staff Accountant |  |  | Chey Martineau | chey.martineau@labor.idaho.gov |  |  | 2022-03-08 | 8:45-9:30 AM
10 | Update Summary Conversion Balances to Detail |  | TBD | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. |  | Chey Martineau | chey.martineau@labor.idaho.gov |  |  | 2022-03-08 | 9:30-10AM