## SIT 3 Listing & Schedule
SIT 3 End to End Scenarios | SIT 3 Scheduled Week | 245 - Department of Environmental Quality
Inventory Management Cycle | Week 4: 1/24 - 1/28
Pcard End to End Process | Week 4: 1/24 - 1/28
Project Processing (RQ, PO, Contract, INV) | Week 4: 1/24 - 1/28 | X
XM Pcard NO Cash Advance | Week 4: 1/24 - 1/28
XM Pcard WITH Cash Advance | Week 4: 1/24 - 1/28
Payroll End to End | Week 4: 1/24 - 1/28
Fixed Asset Acquire to Retire | Week 5: 1/31 - 2/4
Statewide Contract Procure to Pay | Week 5: 1/31 - 2/4 | X
GHR Shell | Week 5: 1/31 - 2/4
Project 1.1 Project Setup and Maintanance | Week 5: 1/31 - 2/4 | X
Project 1.2 Project Processing Master (P&G only) | Week 5: 1/31 - 2/4 | X
AR Credit Monitoring | Week 6: 2/7 - 2/11 | X
Asset Management Maintenance | Week 6: 2/7 - 2/11 | X
Service Contract Interagency Billing | Week 6: 2/7 - 2/11 | X
Project 1.3 Reports and Inquiry Master | Week 6: 2/7 - 2/11 & Week 7: 2/14 - 2/18 | X
Cash Ledger Payment | Week 7: 2/14 - 2/18 | X
Interagency Billing to Settlement | Week 7: 2/14 - 2/18
Non-State Billing | Week 7: 2/14 - 2/18 | X
Procure to Pay Vendor Management Voids | Week 7: 2/14 - 2/18 | X
Vendor Refunds | Week 7: 2/14 - 2/18
Cash Management Deposit to Revenue | Week 8: 2/21 - 2/25 | X
Custodial Accounts Setup | Week 8: 2/21 - 2/25
Global Ledger Entries and Analysis | Week 8: 2/21 - 2/25
Punchout Request to Payment | Week 8: 2/21 - 2/25 | X
Tax Refunds | Week 8: 2/21 - 2/25
Allocations | Week 9: 2/28 - 3/4 | X
Budget | Week 9: 2/28 - 3/4 | X
Custodial Accounts Transaction Processing | Week 9: 2/28 - 3/4
Month End/Year End | Week 9: 2/28 - 3/4
Define and Generate Recurring Invoices | Week 9: 2/28 - 3/4
Chart of Accounts Maintenance | Week 10: 3/7 - 3/11 | X
3rd Party Allocations | TBD

## Instructions
Luma System Integration Testing 3 (SIT 3) Instructions
Agency Functional Testing Dates | January 24 - March 11, 2022 Testing Schedule: Monday -Thursday 8:45 -11 am and 1:45 - 4:00 pm, Friday 9:00 - 11:00 am
Agency Testers Roles and Responsibilities | 1. Execute test scripts per SIT 3 schedule. 2. Review actual results against expected results. 3. Log defects as needed. 4. Retest failed test results to resolve defects. 5. Launch integrations during test cycle per schedule.
Testing Packet | 1. Test Scenario Excel File: Cover Page, Instruction Tab, Scenario Listing, Tab with each steps script detailed instruction to execute the script. 2. Data Sheets. 3. Email Template to use to report your testing results.
Testing Steps | 1. If you are the first step in the scenario, you may begin execution according to the the Date and Time in the Testing packet. If you are not on step 1, please wait for the step before you to complete their script and you receive communication to begin. 2. Execute assigned script(s) using the testing script and data sheet that was provided to you. 3. Sending Testing results via email using to the Test Management Team. (attached email sample) 4. Communicate to the next tester they can begin their script. (Slack or Email works)
What should you do if there are issues or you need assistance while testing? | 1. The Test Management Team will host an all-day SIT 3 Testing Support Hotline (WebEx Meeting). 2. Attendance is optional for SIT testers and testers should only join if they have questions or issues regarding SIT testing. 3. Testers should have an invite on their calendar that includes the WebEx Link.
How to submit a SIT 3 Testing Defect using ServiceNow: | 1. Visit https://auth.sco.idaho.gov/ in your web browser. Google Chrome and Microsoft Edge are recommended. 2. Enter your State ID number as the username and your password. Click the Sign In button. 3. You will be presented with a second page for Multi-Factor Authentication. Select an option and acknowledge the push or call, or enter a passcode from your Duo app. 4. You will see several buttons on your Enterprise Dashboard. One of these will be labeled Service Desk. This button will take you to the Service Portal. 5. There are four main buttons across the center of the page. Click Service Requests to be taken to the service menu. 7. Locate and select LUMA SIT3 Testing Issue from the options listed. 6. Select the SCO IT Services category from the list on the left side of the page. 7. Fill out form with Primary Contact, Short Description, Description, Category, Scenario Name, Script ID, add attachments/screenshots and submit the ticket.
What to do if there is a system outage? | 1. Please join the Testing Support Hotline if you run into any issues with the system and notify the meeting moderator of the issue. 2. If there is a system outage, the Test Management Team will work with the Communications team to notify Agency Testers.

## Email Submission Template
Click on Icon Below to Outlook Email Template

## Project Processing
SIT 3 Scenario - Project Procurement Processing
Agency:
SIT Week - Week 4 - 1/24 - 1/28
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Create RSS Requisition for a Project Item | 2968 | 12522 | Requester | Determines requirements & cost estimates for purchase of goods & services. Submits purchase requisition. | Assigned Agency | Tessa Stevens | Tessa.Stevens@deq.idaho.gov |  | PR-020-010 | 2022-01-25 | 8:45-9:30 AM
2 | Approve Requisition | 8539 | 12528 | Approver | Approve transactions such as requisitions, purchase orders, solicitations, and journal entries. | Assigned Agency | L1 Dana Swift L2 Jeri Ann Fogg | dana.swift@deq.idaho.gov jeriann.fogg@deq.idaho.gov |  | PR-010-060 | 2022-01-25 | 9:30-10AM
3 | Create a Purchase Order | 8169 | 12523 | Buyer | Review requisition and create purchase orders. Conduct market research, and monitor vendor commitments. Approve vendor returns. | Assigned Agency | Carrie Champlin | carrie.champlin@deq.idaho.gov |  | PR-050-040 | 2022-01-25 | 10-11AM
4 | Create a Receipt | 4581 | 12532 | Receiver | Receive and inspect incoming goods. Pick items for shipment/transfer. Dispose of items. Conduct vendor returns. Document variances. | Assigned Agency | Tessa Stevens | Tessa.Stevens@deq.idaho.gov | Receiving Messages | PR-050-070 | 2022-01-25 | 1-1:30PM
5 | Create Contract (Sub-Award) with Service Lines | 7219 | 12533 | Contract Manager | Compile contract file, including entering contract line-item details, terms & conditions, and pricing, and amends and renews contracts. | Assigned Agency | Carrie Champlin | carrie.champlin@deq.idaho.gov | First Line = $25,000 Second line = Remainder of the Sub-Award | PR-040-010 | 2022-01-25 | 1:30-2PM
6 | Create Contract - Contract Draft - Articles Tab | 7204 | 12531 | Contract Manager | Compile contract file, including entering contract line-item details, terms & conditions, and pricing, and amends and renews contracts. | Assigned Agency | Carrie Champlin | carrie.champlin@deq.idaho.gov |  | PR-040-010 | 2022-01-25 | 2-2:30PM
7 | Create Contract - Contract Draft - Participants Tab | 2667 | 12537 | Contract Manager | Compile contract file, including entering contract line-item details, terms & conditions, and pricing, and amends and renews contracts. | Assigned Agency | Carrie Champlin | carrie.champlin@deq.idaho.gov |  | PR-040-010 | 2022-01-25 | 2:30-3PM
8 | Create Contract - Contract Draft - Lines Tab - Service | 3375 | 12536 | Contract Manager | Compile contract file, including entering contract line-item details, terms & conditions, and pricing, and amends and renews contracts. | Assigned Agency | Carrie Champlin | carrie.champlin@deq.idaho.gov |  | PR-040-010 | 2022-01-25 | 3-3:30PM
9 | Create Contract - Contract Draft - Contacts Tab | 3335 | 12534 | Contract Manager | Compile contract file, including entering contract line-item details, terms & conditions, and pricing, and amends and renews contracts. | Assigned Agency | Carrie Champlin | carrie.champlin@deq.idaho.gov |  | PR-040-010 | 2022-01-26 | 8:45-9:30 AM
10 | Create Contract - Contract Draft - Releasing a Contract | 7203 | 12530 | Contract Manager | Compile contract file, including entering contract line-item details, terms & conditions, and pricing, and amends and renews contracts. | Assigned Agency | Carrie Champlin | carrie.champlin@deq.idaho.gov |  | PR-040-010 | 2022-01-26 | 9:30-10AM
11 | Contract Approval | 8353 | 12524 | Approver | Approve transactions such as requisitions, purchase orders, solicitations, and journal entries. | Assigned Agency | L1 Carrie Champlin L2 Matt Orem | carrie.champlin@deq.idaho.gov matt.orem@deq.idaho.gov |  | PR-040-010 | 2022-01-26 | 10-11AM
12 | Create Contract - Contract Draft - Activating a Contract | 7202 | 12540 | Contract Manager | Compile contract file, including entering contract line-item details, terms & conditions, and pricing, and amends and renews contracts. | Assigned Agency | Carrie Champlin | carrie.champlin@deq.idaho.gov |  | PR-040-010 | 2022-01-26 | 1-1:30PM
13 | Create Requisition - Service Lines from Contract (Sub-Award) | 8323 | 12529 | Requester | Determines requirements & cost estimates for purchase of goods & services. Submits purchase requisition. | Assigned Agency | Tessa Stevens | Tessa.Stevens@deq.idaho.gov |  | PR-010-060 | 2022-01-26 | 1:30-2PM
14 | Approve Requisition | 8539 | 12539 | Approver | Approve transactions such as requisitions, purchase orders, solicitations, and journal entries. | Assigned Agency | L1 Dana Swift L2 Jeri Ann Fogg | dana.swift@deq.idaho.gov jeriann.fogg@deq.idaho.gov |  | PR-020-020 | 2022-01-26 | 2-2:30PM
15 | Create a Purchase Order | 2753 | 12538 | Buyer | Review requisition and create purchase orders. Conduct market research, and monitor vendor commitments. Approve vendor returns. | Assigned Agency | Carrie Champlin | carrie.champlin@deq.idaho.gov |  | PR-050-040 | 2022-01-26 | 2:30-3PM
16 | Create Invoice | 11374 | 12525 | Payables Invoice Processor | Process interface and XM files. Match payables invoices, and vendor list. Process payables payments. Generate 1099. | Assigned Agency | Lisa Pierce | lisa.pierce@deq.idaho.gov |  | MF-070-050 Enter a PO Invoice | 2022-01-26 | 3-3:30PM
17 | Approve Invoice | 11375 | 12527 | Approver | Approve transactions such as requisitions, purchase orders, solicitations, and journal entries. | Assigned Agency | See Workflow Workbook |  |  | MF-070-056 Invoice Approval Process | 2022-01-26 | 3:30 -4 PM
18 | Match Invoice | 11457 | 12535 | Payables Manager | Void & cancel payments. Reissue & mail warrants. Process period close. | Assigned Agency | Lisa Pierce | lisa.pierce@deq.idaho.gov |  | MF-070-070 Match Invoices | 2022-01-27 | 8:45-9:30 AM
19 | Process Payment for Invoice | 11442 | 12526 | Payables Manager | Void & cancel payments. Reissue & mail warrants. Process period close. | Assigned Agency | Lisa Pierce | lisa.pierce@deq.idaho.gov |  | MF-070-100 Process Invoice Payments | 2022-01-27 | 9:30-10AM
Note on J4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard

## Statewide Contract Procure to P
SIT 3 Scenario - Statewide Contract Procure to Pay
Agency:
SIT 3 Week - Week 5 - 1/31-2/4
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Create Contract with Rebate and Price Breaks Statewide for Envelopes - Create a Contract (Contract Tab) | 7219 | 11992 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-020 | 2022-01-31 | 8:45 - 11 AM
2 | Create Contract with Rebate and Price Breaks Statewide for Envelopes - Contract Draft (Articles) | 7204 | 11987 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-020 | 2022-01-31 | 8:45 - 11 AM
3 | Create Contract with Rebate and Price Breaks Statewide for Envelopes - Contract Draft - Participants | 2667 | 11997 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-020 | 2022-01-31 | 8:45 - 11 AM
4 | Create Contract with Rebate and Price Breaks Statewide for Envelopes - Contract Draft - Lines - Special | 8909 | 11995 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-020 | 2022-01-31 | 8:45 - 11 AM
5 | Create Contract with Rebate and Price Breaks Statewide for Envelopes - Contract Draft - Lines - Purchase Type Detail - Purchase Pricing | 2663 | 11996 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-020 | 2022-01-31 | 8:45 - 11 AM
6 | Create Contract with Rebate and Price Breaks Statewide for Envelopes - Contract Draft - Rebates | 2671 | 11998 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-020 | 2022-01-31 | 8:45 - 11 AM
7 | Create Contract with Rebate and Price Breaks Statewide for Envelopes - Contract Draft - Contacts | 3335 | 11993 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-020 | 2022-01-31 | 8:45 - 11 AM
8 | Create Contract with Rebate and Price Breaks Statewide for Envelopes - Releasing a Contract | 7203 | 11985 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-020 | 2022-01-31 | 8:45 - 11 AM
9 | Contract Approval | 8353 | 11979 | Approver | Approve transactions such as requisitions, purchase orders, solicitation & journal entries. | DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-020 | 2022-01-31 | 8:45 - 11 AM
10 | Create Contract with Rebate and Price Breaks Statewide for Envelopes - Activating a Contract | 7202 | 11978 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-020 | 2022-01-31 | 1 - 1:30 PM
11 | Requisition - RSS | 8325 | 11988 | Requester | Determines requirements & cost estimates for purchase of goods & services. Submits purchase requisition. | Assigned Agency | Tessa Stevens | Tessa.Stevens@deq.idaho.gov | distribution to multiple org unit and agencies | PR-020-010 | 2022-01-31 | 1:30 - 2:30 PM
12 | Approve Requisition | 8539 | 11984 | Approver | Approve transactions such as requisitions, purchase orders, solicitation & journal entries. | Assigned Agency | L1 Dana Swift L2 Jeri Ann Fogg | dana.swift@deq.idaho.gov jeriann.fogg@deq.idaho.gov |  | PR-020-010 | 2022-01-31 | 2:30 - 3 PM
13 | Create PO from Requisition | 8327 | 11991 | Buyer | Review requisitions & create purchase orders. Conduct market research & monitor vendor commitments. Approve vendor returns. | Assigned Agency | Carrie Champlin | carrie.champlin@deq.idaho.gov |  | PR-050-040 | 2022-02-01 | 8:45-9:30 AM
14 | Receive Purchase Order | 3064 | 11977 | Receiver | Receive and inspect incoming goods. Pick items for shipment/transfer. Dispose of items. Vendor returns. Document variances. | Assigned Agency | Tessa Stevens | Tessa.Stevens@deq.idaho.gov |  | PR-050-070 | 2022-02-01 | 9:30-10AM
15 | Create Invoice | 11606 | 11983 | Payables Invoice Processor | Process interface and XM files. Match payables invoices, and vendor list. Process payables payments. Generate 1099. | Assigned Agency | Lisa Pierce | lisa.pierce@deq.idaho.gov |  | MF-070-050 Enter a PO Invoice | 2022-02-01 | 10-11AM
16 | Notify Buyer of Discrepancy | 11605 | 11982 | Payables Invoice Processor | Process interface and XM files. Match payables invoices, and vendor list. Process payables payments. Generate 1099. |  | Lisa Pierce | lisa.pierce@deq.idaho.gov |  | MF-070-050 Enter a PO Invoice | 2022-02-01 | 1-1:30PM
17 | Resolve Cost Discrepancy | New | 12004 | Buyer | Review requisition and create purchase orders. Conduct market research, and monitor vendor commitments. Approve vendor returns. | Assigned Agency | Carrie Champlin | carrie.champlin@deq.idaho.gov |  |  | 2022-02-01 | 1:30-2PM
18 | Submit Resolved Invoice for Approval | 11607 | 11989 | Payables Invoice Processor | Process interface and XM files. Match payables invoices, and vendor list. Process payables payments. Generate 1099. |  | Lisa Pierce | lisa.pierce@deq.idaho.gov |  | MF-070-050 Enter a PO Invoice | 2022-02-01 | 2-2:30PM
19 | Approve Invoice | 11608 | 11990 | Approver | Approve transactions such as requisitions, purchase orders, solicitations, and journal entries. | Assigned Agency | See workflow Workbook |  |  | MF-070-056 Invoice Approval Process | 2022-02-01 | 2:30-3PM
20 | Match Invoice | 11609 | 11994 | Payables Manager | Void & cancel payments. Reissue & mail warrants. Process period close. | Assigned Agency | Lisa Pierce | lisa.pierce@deq.idaho.gov |  | MF-070-070 Match Invoices | 2022-02-01 | 3-3:30PM
21 | Process Payment for Invoice | 11442 | 11981 | Payables Manager | Void & cancel payments. Reissue & mail warrants. Process period close. | Assigned Agency | Lisa Pierce | lisa.pierce@deq.idaho.gov |  | MF-070-100 Process Invoice Payments | 2022-02-01 | 3-3:30PM
22 | Journalize | 11440 | 11980 | Payables Manager | Void & cancel payments. Reissue & mail warrants. Process period close. |  | Lisa Pierce | lisa.pierce@deq.idaho.gov |  | MF-070-110 Journalize AP Distributions | 2022-02-01 | 3-3:30PM
23 | Renew/Addendum Statewide Contract | 2773 | 11986 | Contract Manager | Compile contract file, including entering contract line-item details, terms & conditions, and pricing, and amends and renews contracts. | DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-050-010 | 2022-02-02 | 8:45-9:30 AM
24 | Load Rebate Invoices | New | 11999 | Supply Management Admin or Processor |  | Assigned Agency |  |  |  | PR-050-010 | 2022-02-02 | 9:30-10AM
25 | Calculate Rebate Amounts Due for a Contract | New | 12000 | Contract Manager |  |  | DOP Tester | contractadmin@adm.idaho.gov |  | PR-050-010 | 2022-02-02 | 10-11AM
26 | Review Rebate Due Information | New | 12001 | Contract Manager | Compile contract file, including entering contract line-item details, terms & conditions, and pricing, and amends and renews contracts. | Assigned Agency | DOP Tester | contractadmin@adm.idaho.gov |  | PR-050-010 | 2022-02-02 | 1-1:30PM
27 | Apply Rebate (Enter a Rebate Invoice in Payables | New | 12002 | Payables Manager | Void & cancel payments. Reissue & mail warrants. Process period close. |  | Lynn Christian | lynn.christian@adm.idaho.gov | There isn't an invoice type of Rebate Invoice???? | MF-260-070ZZ | 2022-02-03 | 8:45-9:30 AM
28 | Review Rebate Information | New | 12003 | Contract Manager | Compile contract file, including entering contract line-item details, terms & conditions, and pricing, and amends and renews contracts. |  | DOP Tester | contractadmin@adm.idaho.gov |  | PR-050-010 | 2022-02-03 | 9:30-10AM
29 | Verify Rebates posted in Cash Account |  |  | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Genny Casiano | genny.casiano@adm.idaho.gov |  | MF-260-070ZZ | 2022-02-03 | 10-11 AM
Note on J5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard

## Project 1.1 Project Setup and M
SIT 3 Scenario - Project Setup
Agency:
SIT 3 Week - Week 5 - 1/31-2/4
Sequence | Script ID | Tab | ALM Test ID # (view tab = "Tests" column A) | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Create Operational Project | FSM.PS001 |  | Project Administrator | Sets up projects and funding sources. | Assigned Agency | Jeri Ann Fogg | jeriann.fogg@deq.idaho.gov |  | MF-050-010 | Conference Room Pilot (In Person) 1/31 - 2/4
2 | Create Billable MultiFunded Project - External Grant/External Customer | FSM.PS002 |  | Project Administrator | Sets up projects and funding sources. | Assigned Agency | Jeri Ann Fogg | jeriann.fogg@deq.idaho.gov |  | MF-280-020 | Conference Room Pilot (In Person) 1/31 - 2/4
3 | Create Internal Only Project | FSM.PS003 |  | Project Administrator | Sets up projects and funding sources. | Assigned Agency | Jeri Ann Fogg | jeriann.fogg@deq.idaho.gov |  | MF-050-010 | Conference Room Pilot (In Person) 1/31 - 2/4
4 | Create MultiFunded Project w Program Income (Additive/ Deductive/ Cost Sharing) or Rebates Income Funding Source | FSM.PS004 |  | Project Administrator | Sets up projects and funding sources. | Assigned Agency | Jeri Ann Fogg | jeriann.fogg@deq.idaho.gov |  | MF-280-020 | Conference Room Pilot (In Person) 1/31 - 2/4
5 | Create Milestone Project(w/wo Override) | FSM.PS005 |  | Project Administrator | Sets up projects and funding sources. | Assigned Agency | Jeri Ann Fogg | jeriann.fogg@deq.idaho.gov |  | MF-280-020 | Conference Room Pilot (In Person) 1/31 - 2/4
6 | Create Project with Intercompany Funding | FSM.PS006 |  | Project Administrator | Sets up projects and funding sources. | Assigned Agency | Jeri Ann Fogg | jeriann.fogg@deq.idaho.gov |  | MF-280-020 | Conference Room Pilot (In Person) 1/31 - 2/4
7 | Create a New Posting Project (child) for existing Contract (new year project) | FSM.PS007 |  | Project Administrator | Sets up projects and funding sources. | Assigned Agency | Jeri Ann Fogg | jeriann.fogg@deq.idaho.gov |  | MF-280-020 | Conference Room Pilot (In Person) 1/31 - 2/4
8 | Create New Burden Codes | FSM.PS009 |  | Project Administrator | Sets up projects and funding sources. | Assigned Agency | Jeri Ann Fogg | jeriann.fogg@deq.idaho.gov |  | MF-280-000ZZ | Conference Room Pilot (In Person) 1/31 - 2/4
9 | Create New Selection Group | FSM.PS010 |  | Project Administrator | Sets up projects and funding sources. | Assigned Agency | Jeri Ann Fogg | jeriann.fogg@deq.idaho.gov |  | MF-280-000ZZ | Conference Room Pilot (In Person) 1/31 - 2/4
10 | Assign Burden Code To Posting Project | FSM.PS011 |  | Project Administrator | Sets up projects and funding sources. | Assigned Agency | Jeri Ann Fogg | jeriann.fogg@deq.idaho.gov |  | MF-280-030ZZ | Conference Room Pilot (In Person) 1/31 - 2/4
11 | Attach Burden to Funding Source | FSM.PS012 |  | Project Administrator | Sets up projects and funding sources. | Assigned Agency | Jeri Ann Fogg | jeriann.fogg@deq.idaho.gov |  | MF-280-030ZZ | Conference Room Pilot (In Person) 1/31 - 2/4
12 | Program Income Additive | FSM.PM001 |  | Project Administrator | Sets up projects and funding sources. | Assigned Agency | Jeri Ann Fogg | jeriann.fogg@deq.idaho.gov |  | MF-280-045ZZ | Conference Room Pilot (In Person) 1/31 - 2/4
13 | Program Income Deductive/Cost Sharing | FSM.PM002 |  | Project Administrator | Sets up projects and funding sources. | Assigned Agency | Jeri Ann Fogg | jeriann.fogg@deq.idaho.gov |  | MF-280-045ZZ | Conference Room Pilot (In Person) 1/31 - 2/4
Note on J5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard

## Project 1.2 Project Processing
| NOTE: Project processing actions take place after Procurement/AP/Payroll Processing. | Other Teams Involvement Identified
SIT 3 Scenario - Project Processing (P&G Only)
Agency:
SIT Week - (dates)
Sequence | Script ID | SIT TEST ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Create Project transactions Journal Entry | FSM.PP001 | Project Accountant |  | 245 DEQ | Jeri Ann Fogg |  |  | MF-020-050 | Conference Room Pilot (In Person) 1/31 - 2/4
2 | In-Kind Journal Entry ("on the books"/off books) | FSM.PP002 | Project Accountant |  | 245 DEQ | Jeri Ann Fogg |  |  | MF-020-050 | Conference Room Pilot (In Person) 1/31 - 2/4
3 | Copy ( & Copy Reverse) Journal Entry | FSM.PP003 | Project Accountant |  | 245 DEQ | Jeri Ann Fogg |  |  | MF-020-050 | Conference Room Pilot (In Person) 1/31 - 2/4
4 | Create I/C Journal Entry | FSM.PP004 | Project Accountant |  | 245 DEQ | Jeri Ann Fogg |  |  | MF-020-050 | Conference Room Pilot (In Person) 1/31 - 2/4
5 | Create, Release and Journalize Recurring JE | FSM.PP005 | Project Accountant |  | 245 DEQ | Jeri Ann Fogg |  |  | MF-020-050 | Conference Room Pilot (In Person) 1/31 - 2/4
6 | Post Journal |  | GL | [5 empty] | MF-020-090 | Conference Room Pilot (In Person) 1/31 - 2/4
7 | Create and Process Retainer Invoice | FSM.PP010 | Project Accountant |  | 245 DEQ | Jeri Ann Fogg |  |  | MF-280-030: Grant Billing Processing | Conference Room Pilot (In Person) 1/31 - 2/4 |  | new process
8 | Generate Indirect Burdens | FSM.PP011 | Project Accountant |  | 245 DEQ | Jeri Ann Fogg |  |  | DC-040-090 - Apply Overhead Costs | Conference Room Pilot (In Person) 1/31 - 2/4
9 | Delete Indirect Burden | FSM.PP012 | Project Accountant |  | 245 DEQ | Jeri Ann Fogg |  |  | DC-040-090 - Apply Overhead Costs | Conference Room Pilot (In Person) 1/31 - 2/4
10 | Journalize Indirect Burden | FSM.PP013 | Project Accountant |  | 245 DEQ | Jeri Ann Fogg |  |  | DC-040-090 - Apply Overhead Costs | Conference Room Pilot (In Person) 1/31 - 2/4
11 | Reverse Indirect Burden | FSM.PP014 | Project Accountant |  | 245 DEQ | Jeri Ann Fogg |  |  | DC-040-090 - Apply Overhead Costs | Conference Room Pilot (In Person) 1/31 - 2/4
12 | Post Transaction in GL |  | GL | [5 empty] | DC-030-050 - Allocate Indirect Costs | Conference Room Pilot (In Person) 1/31 - 2/4
13 | Journalize IB Projects Transactions | FSM.PP013 | Project Accountant |  | 245 DEQ | Jeri Ann Fogg |  |  | DC-030-050 - Allocate Indirect Costs | Conference Room Pilot (In Person) 1/31 - 2/4
14 | Post Transaction in GL |  | GL | [5 empty] | DC-030-050 - Allocate Indirect Costs | Conference Room Pilot (In Person) 1/31 - 2/4
15 | Create, Generate ,Update Certification Number & Date and Journalize Milestone Invoice | FSM.PP020 | Project Accountant |  | 245 DEQ | Jeri Ann Fogg |  |  | MF-280-030: Grant Billing Processing | Conference Room Pilot (In Person) 1/31 - 2/4
16 | Create, Generate ,Update Certification Number & Date and Journalize Cost Reimbursement Invoice | FSM.PP021 | Project Accountant |  | 245 DEQ | Jeri Ann Fogg |  |  | MF-280-030: Grant Billing Processing | Conference Room Pilot (In Person) 1/31 - 2/4
17 | Generate Mass Contract Invoice w/wo Billing Group, Mass Journalize and Review AR Transaction | FSM.PP022 | Project Accountant |  | 245 DEQ | Jeri Ann Fogg |  |  | MF-280-030: Grant Billing Processing | Conference Room Pilot (In Person) 1/31 - 2/4
27 | Process Project Capitalization | FSM.PP040 | Project Accountant |  | 245 DEQ | Jeri Ann Fogg |  |  | DC-050-030 - Capitalize Leased Asset | Conference Room Pilot (In Person) 1/31 - 2/4
28 | Contract Balance Adjustments | FSM.PP050 | Project Accountant |  | 245 DEQ | Jeri Ann Fogg |  |  | MF-280-021ZZ | Conference Room Pilot (In Person) 1/31 - 2/4
29 | Reverse Indirect Burden | FSM.PP051 | Project Accountant |  | 245 DEQ | Jeri Ann Fogg |  |  | DC-040-090 - Apply Overhead Costs | Conference Room Pilot (In Person) 1/31 - 2/4
30 | Delete Invoice | FSM.PP052 | Project Accountant |  | 245 DEQ | Jeri Ann Fogg |  |  | MF-280-031ZZ | Conference Room Pilot (In Person) 1/31 - 2/4
31 | Reverse Journalize Invoice | FSM.PP053 | Project Accountant |  | 245 DEQ | Jeri Ann Fogg |  |  | MF-280-032ZZ | Conference Room Pilot (In Person) 1/31 - 2/4
32 | New Burden Rate | FSM.PP054 | Project Accountant |  | 245 DEQ | Jeri Ann Fogg |  |  | DC-040-091ZZ | Conference Room Pilot (In Person) 1/31 - 2/4
33 | Retainer Adjustment/ Re Applying Retainers | FSM.PP055 | Project Accountant |  | 245 DEQ | Jeri Ann Fogg |  |  | MF-280-022ZZ | Conference Room Pilot (In Person) 1/31 - 2/4
34 | Backout & Reallocate FES Transactions | FSM.PP056 | Project Accountant |  | 245 DEQ | Jeri Ann Fogg |  |  | MF-020-051ZZ | Conference Room Pilot (In Person) 1/31 - 2/4
35 | Review Partially Billed Transactions | FSM.PP057 | Project Accountant |  | 245 DEQ | Jeri Ann Fogg |  |  | MF-280-030: Grant Billing Processing | Conference Room Pilot (In Person) 1/31 - 2/4
36 | Move Project within Structure | FSM.PP059 | Project Accountant |  | 245 DEQ | Jeri Ann Fogg |  |  | MF-050-010: Set up Project | Conference Room Pilot (In Person) 1/31 - 2/4
37 | Copy Posting project | FSM.PP060 | Project Accountant |  | 245 DEQ | Jeri Ann Fogg |  |  | MF-050-010: Set up Project | Conference Room Pilot (In Person) 1/31 - 2/4
38 | Copy Project Funding Source | FSM.PP061 | Project Accountant |  | 245 DEQ | Jeri Ann Fogg |  |  | MF-050-010: Set up Project | Conference Room Pilot (In Person) 1/31 - 2/4
39 | Change SEFA flag | FSM.PP062 | Project Accountant |  | 245 DEQ | Jeri Ann Fogg |  |  | MF-050-010: Set up Project | Conference Room Pilot (In Person) 1/31 - 2/4
40 | Change PoP for Specific System Code on a Posting Project | FSM.PP063 | Project Accountant |  | 245 DEQ | Jeri Ann Fogg |  |  | MF-050-010: Set up Project | Conference Room Pilot (In Person) 1/31 - 2/4
Note on I5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard

## Project 1.3 Reports and Inquiry
Project closing takes place after project processing generally).
SIT 3 Scenario - Closing Projects
Agency:
SIT 3 Week - Week 6: 2/7 - 2/11 & Week 7: 2/14 - 2/18
Sequence | Script ID | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Project Close | FSM.PC001 | Project Accountant | Create, maintain, and close projects and grants, with billing, receiving, and cost allocations. | Assigned Agency | Jeri Ann Fogg | jeriann.fogg@deq.idaho.gov |  | MF-050-090 | 2022-02-15 | 8:45-9:30 AM
2 | Review Project | FSM.PIN001 | Project Accountant | Create, maintain, and close projects and grants, with billing, receiving, and cost allocations. | Assigned Agency | Jeri Ann Fogg | jeriann.fogg@deq.idaho.gov |  | DC-030-080 | 2022-02-15 | 9:30-10AM
3 | GL Journal Transaction Detail | FSM.PIN002 | Project Accountant | Create, maintain, and close projects and grants, with billing, receiving, and cost allocations. | Assigned Agency | Jeri Ann Fogg | jeriann.fogg@deq.idaho.gov |  | DC-030-080 | 2022-02-15 | 10-10:30 AM
4 | Project Searches - Transactions | FSM.PIN003 | Project Accountant | Create, maintain, and close projects and grants, with billing, receiving, and cost allocations. | Assigned Agency | Jeri Ann Fogg | jeriann.fogg@deq.idaho.gov |  | DC-030-080 | 2022-02-15 | 10:30 - 11 AM
5 | View all Contact Invoices & all invoices Lines | FSM.PIN004 | Project Accountant | Create, maintain, and close projects and grants, with billing, receiving, and cost allocations. | Assigned Agency | Jeri Ann Fogg | jeriann.fogg@deq.idaho.gov |  | DC-030-080 | 2022-02-15 | 1-1:30PM
6 | Assign Reports | FSM.PRP001 | Project Accountant | Create, maintain, and close projects and grants, with billing, receiving, and cost allocations. | Assigned Agency | Jeri Ann Fogg | jeriann.fogg@deq.idaho.gov |  | DC-030-080 | 2022-02-15 | 1:30-2PM
7 | View Project Report | FSM.PRP002 | Project Accountant | Create, maintain, and close projects and grants, with billing, receiving, and cost allocations. | Assigned Agency | Jeri Ann Fogg | jeriann.fogg@deq.idaho.gov |  | DC-030-080 | 2022-02-15 | 2-2:30PM
8 | Personalize Report | FSM.PRP003 | Project Accountant | Create, maintain, and close projects and grants, with billing, receiving, and cost allocations. | Assigned Agency | Jeri Ann Fogg | jeriann.fogg@deq.idaho.gov |  | DC-030-080 | 2022-02-15 | 2:30-3PM
9 | View Funding Source List | FSM.PRA001 | Project Accountant | Create, maintain, and close projects and grants, with billing, receiving, and cost allocations. | Assigned Agency | Jeri Ann Fogg | jeriann.fogg@deq.idaho.gov |  | DC-030-080 | 2022-02-15 | 3 - 3:30 PM
10 | View Project Contract Reports | FSM.PRA002 | Project Accountant | Create, maintain, and close projects and grants, with billing, receiving, and cost allocations. | Assigned Agency | Jeri Ann Fogg | jeriann.fogg@deq.idaho.gov |  | DC-030-080 | 2022-02-15 | 3:30 - 4 PM
11 | View Payables Reports | FSM.PRA003 | Financials Viewer |  | Assigned Agency |  |  |  | DC-030-080 | 2022-02-16 | 8:45-9:30 AM
12 | View Budget Reports | FSM.PRA004 | Project Accountant | Create, maintain, and close projects and grants, with billing, receiving, and cost allocations. | Assigned Agency | Jeri Ann Fogg | jeriann.fogg@deq.idaho.gov |  | DC-030-080 | 2022-02-16 | 9:30-10AM
13 | View Receivables Reports | FSM.PRA005 | Financials Viewer |  | Assigned Agency |  |  |  | DC-030-080 | 2022-02-16 | 10-10:30 AM
14 | View d/EPM Dashboard Reports | FSM.PBI001 | Project Accountant | Create, maintain, and close projects and grants, with billing, receiving, and cost allocations. | Assigned Agency | Jeri Ann Fogg | jeriann.fogg@deq.idaho.gov |  | DC-030-080 | 2022-02-16 | 10-10:30 AM
Note on I5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard

## AR Credit Monitoring
SIT 3 Scenario - AR Credit Monitoring
Agency:
SIT Week - Week 6 - 2/7 - 2/11
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | ALM SIT 3 Test ID# | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution Date | Window to Complete Script
1 | Finance Charge Code Setup | 2845 | 12021 | Receivables Manager | Reconcile accounts receivables & collections and assess late fees. | Assigned Agency | Rhonda Yadon | rhonda.yadon@deq.idaho.gov |  | MF-260-010 | 2022-02-07 | 8:45-10 AM
2 | Finance Charge Text Code Setup | 2846 | 12022 | Receivables Manager | Reconcile accounts receivables & collections and assess late fees. | Assigned Agency | Rhonda Yadon | rhonda.yadon@deq.idaho.gov |  | MF-260-010 | 2022-02-07 | 8:45-10 AM
3 | Run Finance Charge Initiation | 8680 | 12018 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Lisa Pierce | lisa.pierce@deq.idaho.gov |  | MF-260-030 | 2022-02-07 | 10 AM-2 PM
4 | Run Finance Charge Late Payment | 8681 | 12020 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Lisa Pierce | lisa.pierce@deq.idaho.gov |  | MF-260-120 | 2022-02-07 | 10 AM-2 PM
5 | Create an Invoice Write Off | 10995 | 12019 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Lisa Pierce | lisa.pierce@deq.idaho.gov |  | MF-260-120 | 2022-02-07 | 10 AM-2 PM
6 | Run Customer Statements | 10986 | 12023 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Lisa Pierce | lisa.pierce@deq.idaho.gov |  | MF-260-060 | 2022-02-08 | 8:45 - 11 AM
7 | Run Advanced Dunning Letter Selection | 11409 | 12024 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Lisa Pierce | lisa.pierce@deq.idaho.gov |  | MF-260-120 | 2022-02-08 | 8:45 - 11 AM
8 | Run Advanced Dunning Letter File Generation | 11410 | 12025 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Lisa Pierce | lisa.pierce@deq.idaho.gov |  | MF-260-120 | 2022-02-08 | 8:45 - 11 AM
9 | Run Company Aging Report | 11898 | 12027 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Lisa Pierce | lisa.pierce@deq.idaho.gov |  | MF-260-110 | 2022-02-08 | 8:45 - 11 AM
10 | Run Customer Aging Report | 11899 | 12028 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Lisa Pierce | lisa.pierce@deq.idaho.gov |  | MF-260-110 | 2022-02-08 | 1- 2PM
11 | Review Invoices Paid Late | 11896 | 12026 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Lisa Pierce | lisa.pierce@deq.idaho.gov |  | MF-260-110 | 2022-02-08 | 1- 2PM
Note on J5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard

## Asset Management Maintenance
SIT 3 Scenario - Asset Management Maintenance
Agency:
SIT Week - Week 6 - 2/7 - 2/11
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Add Asset Manually | 8521 | 12012 | Asset Analyst | Create, add, transfer, adjust, retire, or dispose of assets, including privileges to run depreciation. | Assigned Agency | Rhonda Yadon | rhonda.yadon@deq.idaho.gov | Add asset using fund override | MF-040-020-010 | 2022-02-07 | 8:45-9:30 AM
2 | Run Release Assets | 8524 | 12015 | Asset Manager | Manage the process to tract fixed asset activity: create, transfer, and retire fixed assets. | Assigned Agency | Rhonda Yadon | rhonda.yadon@deq.idaho.gov |  | MF-040-020-020 | 2022-02-07 | 9:30-10AM
3 | Asset Disposal | 8523 | 12014 | Asset Analyst | Create, add, transfer, adjust, retire, or dispose of assets, including privileges to run depreciation. | Assigned Agency | Rhonda Yadon | rhonda.yadon@deq.idaho.gov |  | MF-040-060-020 | 2022-02-07 | 10-11AM
4 | Asset Reinstatement | 8525 | 12016 | Asset Manager | Manage the process to tract fixed asset activity: create, transfer, and retire fixed assets. | Assigned Agency | Rhonda Yadon | rhonda.yadon@deq.idaho.gov |  | MF-040-060-060 | 2022-02-07 | 1-1:30PM
5 | Adjust a Released Asset | 8526 | 12013 | Asset Analyst | Create, add, transfer, adjust, retire, or dispose of assets, including privileges to run depreciation. | Assigned Agency | Rhonda Yadon | rhonda.yadon@deq.idaho.gov |  | MF-040-040-020 | 2022-02-07 | 1:30-2PM
6 | Transfer an Asset | 3173 | 12011 | Asset Analyst | Create, add, transfer, adjust, retire, or dispose of assets, including privileges to run depreciation. | Assigned Agency | Rhonda Yadon | rhonda.yadon@deq.idaho.gov |  | MF-040-050-020 | 2022-02-07 | 2-2:30PM
7 | Create Mass Adjustment Selection Group | Refer to upload template | 12005 | Asset Analyst | Create, add, transfer, adjust, retire, or dispose of assets, including privileges to run depreciation. | Assigned Agency | Rhonda Yadon | rhonda.yadon@deq.idaho.gov |  | MF-040-040-010 | 2022-02-08 | 8:45-9:30 AM
8 | Create Mass Disposal Selection Group | Refer to upload template | 12006 | Asset Analyst | Create, add, transfer, adjust, retire, or dispose of assets, including privileges to run depreciation. | Assigned Agency | Rhonda Yadon | rhonda.yadon@deq.idaho.gov |  | MF-040-060-010 | 2022-02-08 | 9:30-10AM
9 | Create Mass Transfer Selection Group | Refer to upload template | 12007 | Asset Analyst | Create, add, transfer, adjust, retire, or dispose of assets, including privileges to run depreciation. | Assigned Agency | Rhonda Yadon | rhonda.yadon@deq.idaho.gov |  | MF-040-050-010 | 2022-02-08 | 10-11AM
10 | Perform Mass Asset Adjustment | Refer to upload template | 12008 | Asset Manager | Manage the process to tract fixed asset activity: create, transfer, and retire fixed assets. | Assigned Agency | Rhonda Yadon | rhonda.yadon@deq.idaho.gov |  | MF-040-040-030 | 2022-02-08 | 1-1:30PM
11 | Perform Mass Asset Disposal | Refer to upload template | 12009 | Asset Manager | Manage the process to tract fixed asset activity: create, transfer, and retire fixed assets. | Assigned Agency | Rhonda Yadon | rhonda.yadon@deq.idaho.gov |  | MF-040-060-040 | 2022-02-08 | 1:30-2PM
12 | Perform Mass Asset Transfer | Refer to upload template | 12010 | Asset Manager | Manage the process to tract fixed asset activity: create, transfer, and retire fixed assets. | Assigned Agency | Rhonda Yadon | rhonda.yadon@deq.idaho.gov |  | MF-040-050-030 | 2022-02-08 | 2-2:30PM
13 | Run Released Assets | 8524 | 12017 | Asset Manager | Manage the process to tract fixed asset activity: create, transfer, and retire fixed assets. | Assigned Agency | Rhonda Yadon | rhonda.yadon@deq.idaho.gov |  | MF-040-070-870 | 2022-02-08 | 2:30-3PM
Note on J5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard

## Svc Cntract Interagency Billing
SIT 3 Scenario - Service Contract Procure to Pay Interagency Billing
Agency:
SIT Week - Week 6 - 2/7 - 2/11
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Create Requisition for Service | 8323 | 11936 | Requester | Determines requirements & cost estimates for purchase of goods & services. Submits purchase requisition. | Assigned Agency | Tessa Stevens | Tessa.Stevens@deq.idaho.gov |  | PR-020-010 | 2022-02-08 | 8:45-9:30 AM
2 | Approve Requisition | 8539 | 11929 | Approver | Approve transactions such as requisitions, purchase orders, solicitations, and journal entries. | Assigned Agency | L1 Dana Swift L2 Jeri Ann Fogg | dana.swift@deq.idaho.gov jeriann.fogg@deq.idaho.gov |  | PR-020-020 | 2022-02-08 | 9:30-10AM
3 | Identify Requistions to send to Sourcing Event | 2896 | 11934 | Buyer | Review requisitions & create purchase orders. Conduct market research & monitor vendor commitments. Approve vendor returns. | Assigned Agency | Carrie Champlin | carrie.champlin@deq.idaho.gov |  | PR-020-020 | 2022-02-08 | 10-11AM
4 | Create Sourcing Event RFP | 7186 | 11949 | Sourcing Manager | Create souring events, evaluate supplier responses, and oversee selection & award of sourcing events. | Assigned Agency | Agency Tester AND DOP Tester | Agency Email - contractadmin@adm.idaho.gov |  | PR-030-020 | 2022-02-08 | 1-1:30PM
5 | Approve Sourcing Event to Post | 7191 | 11941 | Approver | Approve transactions such as requisitions, purchase orders, solicitations, and journal entries. | Assigned Agency | DOP Tester | contractadmin@adm.idaho.gov |  | PR-030-010 | 2022-02-08 | 1:30-2PM
6 | Supplier Responds to Event | 1249 | 11944 | Supplier (Luma Team Member) |  | DOP |  |  |  | PR-030-020 | 2022-02-08 | 2-2:30PM
7 | Analyze and Award Suppler Responses | Refer to upload Template | 11952 | Sourcing Manager | Create souring events, evaluate supplier responses, and oversee selection & award of sourcing events. | Assigned Agency | DOP Tester | contractadmin@adm.idaho.gov |  | PR-030-050 | 2022-02-08 | 2:30-3PM
8 | Sourcing Event Award Approval | 7191 | 11947 | Approver | Approve transactions such as requisitions, purchase orders, solicitations, and journal entries. | Assigned Agency | DOP Tester | contractadmin@adm.idaho.gov |  | PR-030-040 | 2022-02-08 | 3-3:30PM
9 | Create Contract - Create a Contract - Contract Tab | 7219 | 11942 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | Assigned Agency/DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-010 | 2022-02-09 | 8:45 - 10:30AM
10 | Create Contract - Contract Draft - Articles Tab | 7204 | 11951 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | Assigned Agency/DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-010 | 2022-02-09 | 8:45 - 10:30AM
11 | Create Contract - Contract Draft - Participants Tab | 2667 | 11950 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | Assigned Agency/DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-010 | 2022-02-09 | 8:45 - 10:30AM
12 | Create Contract - Contract Draft - Lines Tab - Service | 3375 | 11948 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | Assigned Agency/DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-010 | 2022-02-09 | 8:45 - 10:30AM
13 | Create Contract - Contract Draft - Contacts Tab | 3335 | 11940 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | Assigned Agency/DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-010 | 2022-02-09 | 8:45 - 10:30AM
14 | Create Contract - Contract Draft - Releasing a Contract | 7203 | 11930 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | Assigned Agency/DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-010 | 2022-02-09 | 8:45 - 10:30AM
15 | Contract Approval | 8353 | 11939 | Approver | Approve transactions such as requisitions, purchase orders, solicitations, and journal entries. | Assigned Agency | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-010 | 2022-02-09 | 8:45 - 10:30AM
16 | Create Contract - Contract Draft - Activating a Contract | 7202 | 11931 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | Assigned Agency/DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-010 | 2022-02-09 | 10:30-11AM
17 | Create Contract Invoice | 11459 | 11933 | Payables Invoice Processor | Process interface and XM files. Match payables invoices, and vendor list. Process payables payments. Generate 1099. | Assigned Agency | Lisa Pierce | lisa.pierce@deq.idaho.gov |  | MF-070-050 Enter a PO Invoice | 2022-02-09 | 1 - 1:30PM
18 | Approve Invoice | 11460 | 11938 | Payables Manager | Void & cancel payments. Reissue & mail warrants. Process period close. | Assigned Agency | Lisa Pierce | lisa.pierce@deq.idaho.gov |  | MF-070-056 Invoice Approval Process | 2022-02-09 | 1:30 -3:30 PM
19 | Match Invoice | 11462 | 11946 | Payables Manager | Void & cancel payments. Reissue & mail warrants. Process period close. | Assigned Agency | Lisa Pierce | lisa.pierce@deq.idaho.gov |  | MF-070-070 Match Invoices | 2022-02-09 | 1:30 -3:30 PM
20 | Process Payment for Invoice | 11442 | 11932 | Payables Manager | Void & cancel payments. Reissue & mail warrants. Process period close. | Assigned Agency | Lisa Pierce | lisa.pierce@deq.idaho.gov |  | MF-070-100 Process Invoice Payments | 2022-02-09 | 1:30 -3:30 PM
21 | Create Interagency Billing - Basic | 8795 | 11945 | Intercompany Billing Specialist | Handle setup and processing of intercompany billing. | Assigned Agency | Lisa Pierce | lisa.pierce@deq.idaho.gov |  | MF-260-030ZZ | 2022-02-10 | 8:45-9:30 AM
22 | Identify Unpaid Interagency Billings | 11536 | 11937 | Payables Invoice Processor | Process interface and XM files. Match payables invoices, and vendor list. Process payables payments. Generate 1099. | Assigned Agency | Lisa Pierce | lisa.pierce@deq.idaho.gov |  | MF-070-050 Enter a PO Invoice | 2022-02-10 | 9:30-10AM
23 | Reclassify Interagency Expenditure Coding (AP110 Distribution Changes on Paid Invoice) | 11624 | 11935 | Payables Invoice Processor | Process interface and XM files. Match payables invoices, and vendor list. Process payables payments. Generate 1099. | Assigned Agency | Lisa Pierce | lisa.pierce@deq.idaho.gov |  | MF-070-050 Enter a PO Invoice | 2022-02-10 | 10-11AM
24 | Settle an Interagency Billing | 8794 | 11943 | Intercompany Billing Specialist | Handle setup and processing of intercompany billing. | Assigned Agency | Lisa Pierce | lisa.pierce@deq.idaho.gov |  | MF-260-030ZZ | 2022-02-10 | 1-1:30PM
Note on J5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard

## Cash Ledger Payment
SIT 3 Scenario - Cash Ledger Payment
Agency:
SIT Week - Week 7 - 2/14 -2/18
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Enter Cash Payment | Cash Payment Entry.xlsx | 12075 | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Lisa Pierce | lisa.pierce@deq.idaho.gov | Rotary/Site Draft, L Warrants |  | 2022-02-14 | 8:45 - 10 AM
1A | Record Cash Payment |  | 12525 | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Lisa Pierce | lisa.pierce@deq.idaho.gov |  |  | 2022-02-14 | 8:45 - 10 AM
2 | Approve Cash Payment | Cash Approve Cash Payment.xlsx | 12076 | Cash Manager | Manage all cash transactions. Review and update cash management policy as needed. | Assigned Agency | Jerri Ann Fogg | jeriann.fogg@deq.idaho.gov |  |  | 2022-02-14 | 10 - 11:30 AM
3 | Cash Requirements | Cash Requirements.xlsx | 12077 | Payables Payment Processor | Perform Cash Requirements, Schedule Payments, Complete Payment Cycle | Assigned Agency | Jerri Ann Fogg | jeriann.fogg@deq.idaho.gov |  | MF-070-100 Process Invoice Payments | 2022-02-14 | 1 - 2:30 PM
4 | Review Check in Cash | Cash Review Check in Cash Management.xlsx | 12078 | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Lisa Pierce | lisa.pierce@deq.idaho.gov | Redeem or Void then Review again |  | 2022-02-14 | 2:30 - 4 PM
5 | Journalize Distributions | Cash Journalize Cash Transaction.xlsx | 12079 | Cash Manager | Manage all cash transactions. Review and update cash management policy as needed. | Assigned Agency | Jerri Ann Fogg | jeriann.fogg@deq.idaho.gov |  |  | 2022-02-15 | 8:45 - 10 AM
6 | Verify Results in Global Ledger Account Analysis |  | 12082 | Staff Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Jerri Ann Fogg | jeriann.fogg@deq.idaho.gov |  |  | 2022-02-15 | 10 - 11:30 AM
7 | Optional Void Cash Payment for Status Updates | Cash Void Cash Payment.xlsx | 12080 | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Lisa Pierce | lisa.pierce@deq.idaho.gov |  |  | 2022-02-15 | 1 - 2:30 PM
8 | Optional Void Cash Payment: Payment Void Stop Pay Update | 12161 | 12161 | Payables Payment Processor | Perform Cash Requirements, Schedule Payments, Complete Payment Cycle | Assigned Agency | Jerri Ann Fogg | jeriann.fogg@deq.idaho.gov |  |  | 2022-02-15 | 1 - 2:30 PM
9 | Optional Redeem Warrant for Status Updates | Cash Redeem Warrant.xlsx | 12081 | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Lisa Pierce | lisa.pierce@deq.idaho.gov |  |  | 2022-02-15 | 2:30 - 4 PM
Note on I4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard
Note on K5: Glenda Smith: Cash BPR's are not correct, do not reference.

## Nonstate Billing
SIT 3 Scenario - Non-State Billing_Master
Agency:
SIT Week - Week 7 - 2/14 -2/18
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 TEST ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Create Manual Batch Header | 10963 | 12456 | Billing Manager | Create and maintain bills for Accounts Receivable. | Assigned Agency | Rhonda Yadon | rhonda.yadon@deq.idaho.gov | Interfaced Invoices, Recurring Invoices | MF-260-030 | 2022-02-14 | 8:45-9:30 AM
2 | Create Billing Invoice | 10962 | 12449 | Billing Manager | Create and maintain bills for Accounts Receivable. | Assigned Agency | Rhonda Yadon | rhonda.yadon@deq.idaho.gov |  | MF-260-030 | 2022-02-14 | 9:30-10AM
3 | Create Credit Memo | 11562 | 12446 | Billing Manager | Create and maintain bills for Accounts Receivable. | Assigned Agency | Rhonda Yadon | rhonda.yadon@deq.idaho.gov | Debit Memo | MF-260-100 | 2022-02-14 | 10-10:30 AM
4 | Approve Invoice Batch | 11603 | 12452 | Billing Manager | Create and maintain bills for Accounts Receivable. | Assigned Agency | Rhonda Yadon | rhonda.yadon@deq.idaho.gov |  | MF-260-060 | 2022-02-14 | 10:30 - 11 AM
5 | Run Invoice Batch Release | 10966 | 12465 | Billing Manager | Create and maintain bills for Accounts Receivable. | Assigned Agency | Rhonda Yadon | rhonda.yadon@deq.idaho.gov |  | MF-260-060 | 2022-02-14 | 1-1:30PM
6 | Run Invoice Register and Print | 3511 | 12459 | Billing Manager | Create and maintain bills for Accounts Receivable. | Assigned Agency | Rhonda Yadon | rhonda.yadon@deq.idaho.gov |  | MF-260-060 | 2022-02-14 | 1:30-2PM
7 | Run Sub System Update (Interface Invoices to AR and Journalize) | 10965 | 12463 | Billing Manager | Create and maintain bills for Accounts Receivable. | Assigned Agency | Rhonda Yadon | rhonda.yadon@deq.idaho.gov |  | MF-260-090 | 2022-02-14 | 2-2:30PM
8 | Create Invoice Batch in AR | 8661 | 12458 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Lisa Pierce | lisa.pierce@deq.idaho.gov |  | MF-260-060 | 2022-02-14 | 2:30-3PM
9 | Create Invoice in AR | 8660 | 12447 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Lisa Pierce | lisa.pierce@deq.idaho.gov | Interfaced Invoices | MF-260-030 | 2022-02-14 | 3 - 3:30 PM
10 | Create Credit Memo in AR | 2812 | 12451 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Lisa Pierce | lisa.pierce@deq.idaho.gov | Debit Memo | MF-260-050 | 2022-02-14 | 3:30 - 4 PM
11 | Approve AR Invoice (if not interfaced from BL) | 11603 | 12472 | Receivables Manager | Reconcile accounts receivables & collections and assess late fees. | Assigned Agency | Rhonda Yadon | rhonda.yadon@deq.idaho.gov |  | MF-260-ZZ | 2022-02-15 | 8:45-9:30 AM
12 | Run Journalize Preview | 8662 | 12466 | Receivables Manager | Reconcile accounts receivables & collections and assess late fees. | Assigned Agency | Rhonda Yadon | rhonda.yadon@deq.idaho.gov |  | MF-260-090 | 2022-02-15 | 9:30-10AM
13 | Run Journalize Distributions |  | 12464 | Receivables Manager | Reconcile accounts receivables & collections and assess late fees. | Assigned Agency | Rhonda Yadon | rhonda.yadon@deq.idaho.gov |  | MF-260-090 | 2022-02-15 | 10-10:30 AM
14 | Create Payment Batch | 8668 | 12457 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Lisa Pierce | lisa.pierce@deq.idaho.gov | Interfaced Payments | MF-260-070 | 2022-02-15 | 10:30 - 11 AM
15 | Create Customer Payment | 8666 | 12448 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Lisa Pierce | lisa.pierce@deq.idaho.gov | Interfaced Payments | MF-260-070 | 2022-02-15 | 1-1:30PM
16 | Create Payment Remittance | 11895 | 12470 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Lisa Pierce | lisa.pierce@deq.idaho.gov |  | MF-260-070 | 2022-02-15 | 1:30-2PM
17 | Create Non AR Cash Payment | 8673 | 12468 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Lisa Pierce | lisa.pierce@deq.idaho.gov | Interfaced Payments | MF-260-070 | 2022-02-15 | 2-2:30PM
18 | Apply Payment to Invoice | 8669 | 12460 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Lisa Pierce | lisa.pierce@deq.idaho.gov | Automatic Cash Application | MF-260-080 | 2022-02-15 | 2:30-3PM
19 | Apply Credit Memo to Invoice | 2513 | 12469 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Lisa Pierce | lisa.pierce@deq.idaho.gov | Automatic Memo Application | MF-260-100 | 2022-02-15 | 3 - 3:30 PM
20 | Approve Payment Batch | 11603 | 12473 | Receivables Manager | Reconcile accounts receivables & collections and assess late fees. | Treasury | Rhonda Yadon | rhonda.yadon@deq.idaho.gov |  | MF-260-ZZ | 2022-02-15 | 3:30 - 4 PM
21 | Create Payment Application Reversal | 11064 | 12450 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Lisa Pierce | lisa.pierce@deq.idaho.gov |  | MF-260-ZZ | 2022-02-16 | 8:45-9:30 AM
22 | Run Application Reversal Creation | 11065 | 12455 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Lisa Pierce | lisa.pierce@deq.idaho.gov |  | MF-260-ZZ | 2022-02-16 | 9:30-10AM
23 | Application Close | 8670 | 12462 | Receivables Manager | Reconcile accounts receivables & collections and assess late fees. | Assigned Agency | Rhonda Yadon | rhonda.yadon@deq.idaho.gov |  | MF-260-130 | 2022-02-16 | 10-10:30 AM
24 | Run Journalize Preview | 8671 | 12467 | Receivables Manager | Reconcile accounts receivables & collections and assess late fees. | Assigned Agency | Rhonda Yadon | rhonda.yadon@deq.idaho.gov |  | MF-260-090 | 2022-02-16 | 10:30 - 11 AM
25 | Run Journalize Distributions | 8672 | 12474 | Receivables Manager | Reconcile accounts receivables & collections and assess late fees. | Assigned Agency | Rhonda Yadon | rhonda.yadon@deq.idaho.gov |  | MF-260-090 | 2022-02-16 | 1-1:30PM
26 | Reconcile AR module to GL balance (Account Analysis/Reports) | 11672 | 12453 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate, and update allocations. | Assigned Agency | Jeri Ann Fogg | jeriann.fogg@deq.idaho.gov |  | MF-260-090 | 2022-02-16 | 1:30-2PM
27 | View Cash Fund Balance | Cash Fund Balance.lxsx - maybe in ALM already |  | Financial Viewer | View-only access to key financial workstreams and structures, such as Chart of Accounts, financial reports, and financial transaction data. | Assigned Agency |  |  |  | MF-260-090 | 2022-02-16 | 2-2:30PM
28 | Create Return to Maker Payment | 11120 | 12454 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Lisa Pierce | lisa.pierce@deq.idaho.gov |  | MF-260-ZZ | 2022-02-16 | 2:30-3PM
29 | Release Return to Maker Payment | 11124 | 12461 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Lisa Pierce | lisa.pierce@deq.idaho.gov |  | MF-260-ZZ | 2022-02-16 | 3 - 3:30 PM
30 | Create Payment Reversal | 11064 | 12475 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Lisa Pierce | lisa.pierce@deq.idaho.gov |  | MF-260-ZZ | 2022-02-16 | 3:30 - 4 PM
31 | Run Application Reversal Creation | 11065 | 12476 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Lisa Pierce | lisa.pierce@deq.idaho.gov |  | MF-260-ZZ | 2022-02-17 | 8:45-9:30 AM
Note on J5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard

## Procure to Pay Vendor Mgt Voids
SIT 3 Scenario - Procure to Pay with Void and Vendor Update
Agency:
SIT Week - Week 7 - 2/14 -2/18
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | Luma Role (role switcher) | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Create Requisition - Special | 8324 | Requester | Assigned Agency | Tessa Stevens | Tessa.Stevens@deq.idaho.gov |  | PR-020-010 | 2022-02-14 | 8:45-9:30 AM
2 | Approve Requisition | 8539 | Approver | Assigned Agency | L1 Dana Swift L2 Jeri Ann Fogg | dana.swift@deq.idaho.gov jeriann.fogg@deq.idaho.gov | Requisition not approved | PR-010-060 | 2022-02-14 | 9:30-10AM
3 | Create Purchase Order | 8170 | Buyer | Assigned Agency | Carrie Champlin | carrie.champlin@deq.idaho.gov |  | PR-050-040 | 2022-02-14 | 10-10:30 AM
4 | Receive Purchase Order | 4587 | Receiver | Assigned Agency | Tessa Stevens | Tessa.Stevens@deq.idaho.gov |  | PR-050-070 | 2022-02-14 | 10:30 - 11 AM
5 | Create Invoice | 11519 | Payables Invoice Processor | Assigned Agency | Lisa Pierce | lisa.pierce@deq.idaho.gov |  | MF-070-050 Enter a PO Invoice | 2022-02-14 | 1-1:30PM
6 | Approve Invoice | 11520 | Approver | Assigned Agency | See Workflow Workbook |  |  | MF-070-056 Invoice Approval Process | 2022-02-14 | 1:30-2PM
7 | Match Invoice | 11458 | Payables Manager | Assigned Agency | Lisa Pierce | lisa.pierce@deq.idaho.gov |  | MF-070-070 Match Invoices | 2022-02-14 | 2-2:30PM
8 | Process Payment for Invoice | 11442 | Payables Manager | Assigned Agency | Lisa Pierce | lisa.pierce@deq.idaho.gov |  | MF-070-100 Process Invoice Payments | 2022-02-14 | 2:30-3PM
9 | Journalize | 11440 | Payables Manager |  | Lisa Pierce | lisa.pierce@deq.idaho.gov |  | MF-070-110 Journalize AP Distributions | 2022-02-14 | 3 - 3:30 PM
10 | Void Payment | 12080 | Cash Accountant | SCO | Lisa Pierce | lisa.pierce@deq.idaho.gov |  | MF-200-060 Void Cash Transactions | 2022-02-14 | 3:30 - 4 PM
11 | Cancel Invoice | 11523 | Payables Manager | Assigned Agency | Lisa Pierce | lisa.pierce@deq.idaho.gov |  | MF-070-050 Enter a PO Invoice | 2022-02-15 | 8:45-9:30 AM
12 | Request a new vendor | 11524 | Payables Invoice Processor | Assigned Agency | Lisa Pierce | lisa.pierce@deq.idaho.gov |  | PR-040-030 Create and Maintain Vendor | 2022-02-15 | 9:30-10AM
13 | Approve and setup new vendor | 11525 - Only SCO staff can do this | Approver | SCO | See Workflow Workbook |  | Disapprove vendor | PR-040-030 Create and Maintain Vendor | 2022-02-15 | 10-10:30 AM
14 | Create Invoice | 11519 | Payables Invoice Processor | Assigned Agency | Lisa Pierce | lisa.pierce@deq.idaho.gov |  | MF-070-050 Enter a PO Invoice | 2022-02-15 | 10:30 - 11 AM
15 | Approve Invoice | 11520 | Approver | Assigned Agency | See Workflow Workbook |  |  | MF-070-056 Invoice Approval Process | 2022-02-15 | 1-1:30PM
16 | Match Invoice | 11522 | Payables Invoice Processor | Assigned Agency | Lisa Pierce | lisa.pierce@deq.idaho.gov |  | MF-070-070 Match Invoices | 2022-02-15 | 1:30-2PM
17 | Process Payment for Invoice | 11442 | Payables Manager | Assigned Agency | Lisa Pierce | lisa.pierce@deq.idaho.gov |  | MF-070-100 Process Invoice Payments | 2022-02-15 | 2-2:30PM
18 | Post Transactions - Journalize | 11440 | Payables Manager | Assigned Agency | Lisa Pierce | lisa.pierce@deq.idaho.gov |  | MF-070-110 Journalize AP Distributions | 2022-02-15 | 2:30-3PM
19 | Cash Ledger Journalize | 12079 | Cash Manager | Assigned Agency | Jeri Ann Fogg | jeriann.fogg@deq.idaho.gov |  | MF-200-050 Reconcile Payments Payables and Disbursements | 2022-02-15 | 3 - 3:30 PM
20 | Verify Voided Payables Checks | 12153 | Cash Accountant | Assigned Agency | Lisa Pierce | lisa.pierce@deq.idaho.gov |  | MF-200-060 Void Cash Transactions | 2022-02-15 | 3:30 - 4 PM
21 | View Fund Balance | Cash Fund Balance.xlsx (in ALM?)(in Cash Deposit to Revenue Scenario) | Cash Accountant | Assigned Agency | Lisa Pierce | lisa.pierce@deq.idaho.gov |  | MF-200-050 Reconcile Payments Payables and Disbursements | 2022-02-16 | 8:45-9:30 AM
22 | Comparative report from Birst |  | Cash Accountant | Assigned Agency | Lisa Pierce | lisa.pierce@deq.idaho.gov |  | MF-200-ZZ | 2022-02-16 | 9:30-10AM
23 | Cash Revenue Daily Report - Birst |  | Cash Manager | Assigned Agency | Jeri Ann Fogg | jeriann.fogg@deq.idaho.gov |  | MF-200-ZZ | 2022-02-16 | 10-10:30 AM
Note on H5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard

## Cash Managem Deposit to Revenue
SIT 3 Scenario - Deposit to Revenue
Agency:
SIT Week - Week 8 - 2/21/ - 2/25
Sequence | Script ID | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 BPR PROCESSES | Execution date | Window to Complete Script
1 | Cash Fund Balance - Before Processing Transactions | TBD | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Lisa Pierce | lisa.pierce@deq.idaho.gov |  |  | 2022-02-22 | 8:45-9:30 AM
2 | Create Cash Receipt | TBD | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Lisa Pierce | lisa.pierce@deq.idaho.gov |  |  | 2022-02-22 | 9:30-10AM
3 | Approve Cash Receipt (Approve Cash Transactions in InBasket) | TBD | Cash Manager | Manage all cash transactions. Review and update cash management policy as needed. | Assigned Agency | Jeri Ann Fogg | jeriann.fogg@deq.idaho.gov |  |  | 2022-02-22 | 10-11AM
4 | Cash Receipt Final Release (Approve Cash Transactions in InBasket) | TBD | Cash Manager | Manage all cash transactions. Review and update cash management policy as needed. | 150 | Jeri Ann Fogg | jeriann.fogg@deq.idaho.gov |  |  | 2022-02-22 | 1-1:30PM
5 | Process NSF | TBD | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Lisa Pierce | lisa.pierce@deq.idaho.gov |  |  | 2022-02-22 | 1:30-2PM
6 | Approve NSF (Approve Cash Transactions in InBasket) | TBD | Cash Manager | Manage all cash transactions. Review and update cash management policy as needed. | Assigned Agency | Jeri Ann Fogg | jeriann.fogg@deq.idaho.gov |  |  | 2022-02-22 | 2-2:30PM
7 | NSF Final Release (Approve Cash Transactions in InBasket) | TBD | Cash Manager | Manage all cash transactions. Review and update cash management policy as needed. | 150 | Jeri Ann Fogg | jeriann.fogg@deq.idaho.gov |  |  | 2022-02-22 | 2:30-3PM
8 | Reclass From Suspense: No Customer (Cash Receipt Transfer) | TBD | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Lisa Pierce | lisa.pierce@deq.idaho.gov |  |  | 2022-02-22 | 3-3:30PM
9 | Reclass From Suspense Customer (Go to AR Scenario) | TBD | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Lisa Pierce | lisa.pierce@deq.idaho.gov | Process under development. |  | 2022-02-23 | 8:45-9:30 AM
10 | Operating Transfer (Cash Ledger Transaction Transfer) | TBD | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Lisa Pierce | lisa.pierce@deq.idaho.gov |  |  | 2022-02-23 | 9:30-10AM
11 | Statutory Transfer (Cash Ledger Transaction Transfer) | TBD | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Lisa Pierce | lisa.pierce@deq.idaho.gov |  |  | 2022-02-23 | 10-11AM
12 | Approve Cash Transfer (Approve Cash Transactions in InBasket) | TBD | Cash Manager | Manage all cash transactions. Review and update cash management policy as needed. | Assigned Agency | Jeri Ann Fogg | jeriann.fogg@deq.idaho.gov |  |  | 2022-02-23 | 1-1:30PM
13 | Cash Fund Balance - After Processing Transactions | TBD | Cash Manager | Manage all cash transactions. Review and update cash management policy as needed. | Assigned Agency | Jeri Ann Fogg | jeriann.fogg@deq.idaho.gov |  |  | 2022-02-23 | 1:30-2PM
14 | Journalize Cash Transactions | TBD | Cash Manager | Manage all cash transactions. Review and update cash management policy as needed. | Assigned Agency | Jeri Ann Fogg | jeriann.fogg@deq.idaho.gov |  |  | 2022-02-23 | 2-2:30PM
15 | Post GL Journals | TBD | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate, and update allocations. | Assigned Agency | Jeri Ann Fogg | jeriann.fogg@deq.idaho.gov | Check for autopost |  | 2022-02-23 | 2:30-3PM
16 | Review Global Ledger for Transactions Processed | TBD | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate, and update allocations. | Assigned Agency | Jeri Ann Fogg | jeriann.fogg@deq.idaho.gov |  |  | 2022-02-23 | 3-3:30PM
Note on I5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard

## Punchout Request to Payment
SIT 3 Scenario - Punchout Request to Payment
Agency:
SIT Week - Week 8 - 2/21 - 2/25
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Create Punchout Requisition using RSS | 3501 | 11924 | Requester | Determines requirements & cost estimates for purchase of goods & services. Submits purchase requisition. | Assigned Agency | Tessa Stevens | Tessa.Stevens@deq.idaho.gov |  | PR-020-010 | 2022-02-22 | 8:45-9:30 AM
2 | Approve Requisition | 8539 | 11925 | Approver | Approve transactions such as requisitions, purchase orders, solicitation & journal entries. | Assigned Agency | L1 Dana Swift L2 Jeri Ann Fogg | dana.swift@deq.idaho.gov jeriann.fogg@deq.idaho.gov | Deny Requisition - add note - need more information Approve Requisition | PR-010-060 | 2022-02-22 | 9:30-10AM
3 | Locate Punchout PO | Refer to Upload template | 12034 | Requester |  |  | Tessa Stevens | Tessa.Stevens@deq.idaho.gov |  | PR-050-040 | 2022-02-22 | 10-11AM
4 | Review Punchout PO | Refer to Upload template | 11927 | Buyer | Review requisitions & create purchase orders. Conduct market research & monitor vendor commitments. Approve vendor returns. | Assigned Agency | Carrie Champlin | carrie.champlin@deq.idaho.gov | This will be a review of schedule job creating PO. Other variations would be manual creation, or Job run creation submitted as needed. | PR-050-040 | 2022-02-22 | 1-1:30PM
5 | Review Punchout Receipt | Refer to Upload template | 11928 | Receiver | Receive and inspect incoming goods. Pick items for shipment/transfer. Dispose of items. Vendor returns. Document variances. | Assigned Agency | Tessa Stevens | Tessa.Stevens@deq.idaho.gov | Manual release of receipt vs. auto release | PR-050-070 | 2022-02-22 | 1:30-2PM
6 | Review Punchout Invoice | 11610 | 11922 | Payables Invoice Processor | Processes interface and XM files. Match Payables invoices. Manages vendor list. Processes Payables payments. Generates 1099. | Assigned Agency | Lisa Pierce | lisa.pierce@deq.idaho.gov |  | MF-070-050 Enter a PO Invoice | 2022-02-22 | 2-2:30PM
7 | Approve Invoice | 11611 | 11923 | Approver |  |  | See Workflow Workbook |  |  | MF-070-056 Invoice Approval Process | 2022-02-22 | 2:30-3PM
8 | Match Invoice | 11613 | 11926 | Payables Manager | Void & cancel payments, reissue & mail warrants. Process period close. | Assigned Agency | Lisa Pierce | lisa.pierce@deq.idaho.gov |  | MF-070-070 Match Invoices | 2022-02-22 | 3-3:30PM
9 | Process Invoice for Payment | 11442 | 11921 | Payables Manager | Void & cancel payments, reissue & mail warrants. Process period close. | Assigned Agency | Lisa Pierce | lisa.pierce@deq.idaho.gov |  | MF-070-100 Process Invoice Payments | 2022-02-22 | 3:30 - 4 PM
Note on J5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard

## Allocations
SIT 3 Scenario - Allocations
Agency:
SIT 3 Week - Week 9 - 2/28 - 3/4
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Create Allocation Control | Allocation Control.xlsx | 12063 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate, and update allocations. | Assigned Agency | Jeri Ann Fogg | jeriann.fogg@deq.idaho.gov |  | MF-025-030 | 2022-02-28 | 8:45-9:30 AM
2 | Create Allocation | Allocation.xlsx | 12064 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate, and update allocations. | Assigned Agency | Jeri Ann Fogg | jeriann.fogg@deq.idaho.gov |  | MF-025-030 | 2022-02-28 | 9:30-10:30 AM
3 | Enter Allocation Lines 1 Dimension Override | Allocation Lines 1 Dimension Override.xlsx | 12065 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate, and update allocations. | Assigned Agency | Jeri Ann Fogg | jeriann.fogg@deq.idaho.gov |  | MF-025-030 | 2022-02-28 | 10:30-11:30 AM
4 | Enter Allocation Lines 2+ Dimension Manual Override | Allocation Lines 2+ Dimension Manual Override.xlsx | 12066 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate, and update allocations. | Assigned Agency | Jeri Ann Fogg | jeriann.fogg@deq.idaho.gov |  | MF-025-031 | 2022-02-28 | 1-1:30PM
5 | Create Group Override List | Allocation Group Overrides.xlsx | 12067 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate, and update allocations. | Assigned Agency | Jeri Ann Fogg | jeriann.fogg@deq.idaho.gov |  | MF-025-040 | 2022-02-28 | 1:30-2PM
6 | Calculate Allocations | Allocations Calculation.xlsx | 12068 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate, and update allocations. | Assigned Agency | Jeri Ann Fogg | jeriann.fogg@deq.idaho.gov |  | MF-025-030 | 2022-02-28 | 2-2:30PM
7 | Journalize Allocations | Allocations Journalize.xlsx | 12069 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate, and update allocations. | Assigned Agency | Jeri Ann Fogg | jeriann.fogg@deq.idaho.gov |  | MF-025-040 | 2022-02-28 | 2:30-3PM
8 | JE Approve and Post | 2920 | 12070 | Approver | Approve transactions such as requisitions, purchase orders, solicitations, and journal entries. | Assigned Agency | See Workflow Workbook |  |  | MF-025-060 | 2022-02-28 | 3:30 - 4 PM
Note on J5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard

## Budget
SIT 3 Scenario - Budget Change Request
Agency:
SIT 3 Week - Week 9 - 2/28 - 3/4
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | New SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Budget Change Request | 1974 | 11632 | Budget Analyst | Create and maintain budget templates, scenarios, and budgets. Process budget changes. | Assigned Agency | Jeri Ann Fogg | jeriann.fogg@deq.idaho.gov | Associate with project | MB-070-120 Submit Budget Adjustments for Approval | 2022-02-28 | 8:45-9:30 AM
2 | Create JE (Lines) | 1974 | 12037 | Budget Analyst | Create and maintain budget templates, scenarios, and budgets. Process budget changes. | Assigned Agency | Jeri Ann Fogg | jeriann.fogg@deq.idaho.gov |  | MB-070-110 Load Budget Adjustments | 2022-02-28 | 9:30-10:30 AM
3 | Budget Change Request 1st level Approver | 1974 | 12038 | Budget Controller | Review/monitor and manage publish results for budget, strategic plan & performance measures. | Assigned Agency | Jeri Ann Fogg | jeriann.fogg@deq.idaho.gov | Deny Requisition - add note - need more information Approve Requisition | MB-070-130 DFM Approval | 2022-02-28 | 10:30-11:30 AM
4 | Approve Budget Change Request | 1974 | 12039 | DFM Analyst | DFM will approve all Budget Change Requests made to the Appropriation Scenario only. | DFM |  |  |  | MB-070-130 DFM Approval | 2022-02-28 | 1-1:30PM
5 | Budget Scenario Upload | 1972 | 11633 | Budget Analyst | Maintain the ensures the scenario's stay in sync when a budget change request is approved. | Assigned Agency | Jeri Ann Fogg | jeriann.fogg@deq.idaho.gov | Susan feels SCO will only upload | MB-070-140 Budget Change Order Released | 2022-02-28 | 1:30-2PM
Note on J5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard

## Chart of Accounts Maintenance
SIT 3 Scenario - Chart of Accounts Maintenance
Agency:
SIT Week - Week 10 - 3/7 - 3/11
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | View and Validate an Organizational Unit |  | TBD | Staff Accountant |  |  | Jeri Ann Fogg | jeriann.fogg@deq.idaho.gov |  |  | 2022-03-07 | 8:45-9:30 AM
2 | View and Validate a Project |  | TBD | Staff Accountant |  |  | Jeri Ann Fogg | jeriann.fogg@deq.idaho.gov |  |  | 2022-03-07 | 9:30-10AM
3 | View and Validate a Program |  | TBD | Staff Accountant |  |  | Jeri Ann Fogg | jeriann.fogg@deq.idaho.gov |  |  | 2022-03-07 | 10-11AM
4 | View and Validate a Location |  | TBD | Staff Accountant |  |  | Jeri Ann Fogg | jeriann.fogg@deq.idaho.gov |  |  | 2022-03-07 | 1-1:30PM
5 | View and Validate Additional Reporting |  | TBD | Staff Accountant |  |  | Jeri Ann Fogg | jeriann.fogg@deq.idaho.gov |  |  | 2022-03-07 | 1:30-2PM
6 | View and Validate Custodial Accounts (CAM) |  | TBD | Staff Accountant |  |  | Jeri Ann Fogg | jeriann.fogg@deq.idaho.gov |  |  | 2022-03-07 | 2-2:30PM
7 | Request a new account |  | TBD | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Jeri Ann Fogg | jeriann.fogg@deq.idaho.gov |  |  | 2022-03-07 | 2:30-3PM
8 | Request a new organizational unit |  | TBD | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Jeri Ann Fogg | jeriann.fogg@deq.idaho.gov |  |  | 2022-03-07 | 3-3:30PM
9 | View and Validate Beginning Balances |  | TBD | Staff Accountant |  |  | Jeri Ann Fogg | jeriann.fogg@deq.idaho.gov |  |  | 2022-03-08 | 8:45-9:30 AM
10 | Update Summary Conversion Balances to Detail |  | TBD | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. |  | Jeri Ann Fogg | jeriann.fogg@deq.idaho.gov |  |  | 2022-03-08 | 9:30-10AM
Note on J5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard