## SIT 3 Listing & Schedule
SIT 3 End to End Scenarios | SIT 3 Scheduled Week | 330 - Idaho State Police
Inventory Management Cycle | Week 4: 1/24 - 1/28 | X
Pcard End to End Process | Week 4: 1/24 - 1/28
Project Processing (RQ, PO, Contract, INV) | Week 4: 1/24 - 1/28
XM Pcard NO Cash Advance | Week 4: 1/24 - 1/28
XM Pcard WITH Cash Advance | Week 4: 1/24 - 1/28
Payroll End to End | Week 4: 1/24 - 1/28
Fixed Asset Acquire to Retire | Week 5: 1/31 - 2/4 | X
Statewide Contract Procure to Pay | Week 5: 1/31 - 2/4 | X
GHR Shell | Week 5: 1/31 - 2/4
Project 1.1 Project Setup and Maintanance | Week 5: 1/31 - 2/4
Project 1.2 Project Processing Master (P&G only) | Week 5: 1/31 - 2/4
AR Credit Monitoring | Week 6: 2/7 - 2/11 | X
Asset Management Maintenance | Week 6: 2/7 - 2/11
Service Contract Interagency Billing | Week 6: 2/7 - 2/11 | X
Project 1.3 Reports and Inquiry Master | Week 6: 2/7 - 2/11 & Week 7: 2/14 - 2/18
Cash Ledger Payment | Week 7: 2/14 - 2/18 | X
Interagency Billing to Settlement | Week 7: 2/14 - 2/18
Non-State Billing | Week 7: 2/14 - 2/18 | X
Procure to Pay Vendor Management Voids | Week 7: 2/14 - 2/18 | X
Vendor Refunds | Week 7: 2/14 - 2/18
Cash Management Deposit to Revenue | Week 8: 2/21 - 2/25
Custodial Accounts Setup | Week 8: 2/21 - 2/25 | X
Global Ledger Entries and Analysis | Week 8: 2/21 - 2/25 | X
Punchout Request to Payment | Week 8: 2/21 - 2/25 | X
Tax Refunds | Week 8: 2/21 - 2/25
Allocations | Week 9: 2/28 - 3/4
Budget | Week 9: 2/28 - 3/4
Custodial Accounts Transaction Processing | Week 9: 2/28 - 3/4 | X
Month End/Year End | Week 9: 2/28 - 3/4
Define and Generate Recurring Invoices | Week 9: 2/28 - 3/4
Chart of Accounts Maintenance | Week 10: 3/7 - 3/11 | X
3rd Party Allocations | TBD

## Instructions
Luma System Integration Testing 3 (SIT 3) Instructions
Agency Functional Testing Dates | January 24 - March 11, 2022 Testing Schedule: Monday -Thursday 8:45 -11 am and 1:45 - 4:00 pm, Friday 9:00 - 11:00 am
Agency Testers Roles and Responsibilities | 1. Execute test scripts per SIT 3 schedule. 2. Review actual results against expected results. 3. Log defects as needed. 4. Retest failed test results to resolve defects. 5. Launch integrations during test cycle per schedule.
Testing Packet | 1. Test Scenario Excel File: Cover Page, Instruction Tab, Scenario Listing, Tab with each steps script detailed instruction to execute the script. 2. Data Sheets. 3. Email Template to use to report your testing results.
Testing Steps | 1. If you are the first step in the scenario, you may begin execution according to the the Date and Time in the Testing packet. If you are not on step 1, please wait for the step before you to complete their script and you receive communication to begin. 2. Execute assigned script(s) using the testing script and data sheet that was provided to you. 3. Sending Testing results via email using to the Test Management Team. (attached email sample) 4. Communicate to the next tester they can begin their script. (Slack or Email works)
What should you do if there are issues or you need assistance while testing? | 1. The Test Management Team will host an all-day SIT 3 Testing Support Hotline (WebEx Meeting). 2. Attendance is optional for SIT testers and testers should only join if they have questions or issues regarding SIT testing. 3. Testers should have an invite on their calendar that includes the WebEx Link.
How to submit a SIT 3 Testing Defect using ServiceNow: | 1. Visit https://auth.sco.idaho.gov/ in your web browser. Google Chrome and Microsoft Edge are recommended. 2. Enter your State ID number as the username and your password. Click the Sign In button. 3. You will be presented with a second page for Multi-Factor Authentication. Select an option and acknowledge the push or call, or enter a passcode from your Duo app. 4. You will see several buttons on your Enterprise Dashboard. One of these will be labeled Service Desk. This button will take you to the Service Portal. 5. There are four main buttons across the center of the page. Click Service Requests to be taken to the service menu. 7. Locate and select LUMA SIT3 Testing Issue from the options listed. 6. Select the SCO IT Services category from the list on the left side of the page. 7. Fill out form with Primary Contact, Short Description, Description, Category, Scenario Name, Script ID, add attachments/screenshots and submit the ticket.
What to do if there is a system outage? | 1. Please join the Testing Support Hotline if you run into any issues with the system and notify the meeting moderator of the issue. 2. If there is a system outage, the Test Management Team will work with the Communications team to notify Agency Testers.

## Email Submission Template
Click on Icon Below to Outlook Email Template

## Inventory Mgt Cycle
SIT 3 Scenario - Inventory Management Cycle
Agency:
SIT Week - Week 4 - 1/24 - 1/28
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | ALM SIT 3 Test ID # | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Request a New Item | 3289 | 11659 | Requester | Determines requirements & cost estimates for purchase of goods & services. Submits purchase requisition. | Assigned Agency | Debie Beavers-Rudolph | Debie.beavers-rudolph@isp.idaho.gov |  | PR-010-060 | 2022-01-24 | 8:45-9:30 AM
2 | Approve New Item - Add Item | added | 12035 | Approver | Approve transactions such as requisitions, purchase orders, solicitation & journal entries. | SCO | Luma Team | Luma Team |  | PR-010-060 | 2022-01-24 | 9:30-10AM
3 | Add Item - Manually | 1680 | 12040 | Inventory Manager | Manage/monitor: reconciliation of counts, item master, forecast methods & replenishment, reorder & disposal policy compliance. | SCO | Randy Byrne | randy.byrne@isp.idaho.gov | Manually Add New Item (Test ID 1680) - This test will use the Inventory Manager Role | PR-010-060 | 2022-01-24 | 10-11AM
4 | Attach Item to Inventory Location | 1682 | 11667 | Inventory Manager | Manage/monitor: reconciliation of counts, item master, forecast methods & replenishment, reorder & disposal policy compliance. | Assigned Agency | Randy Byrne | randy.byrne@isp.idaho.gov |  | PR-050-090 | 2022-01-24 | 1-1:30PM
5 | Inventory Issue - Requisition Inventory Item | 3243 | 11663 | Warehouse Clerk | Receive and inspect incoming goods. Pick items for shipment/transfer. Dispose of items. Document variances. | Assigned Agency | Diana Jones | diana.jones@isp.idaho.gov |  | PR-020-010 | 2022-01-24 | 1:30-2PM
6 | Inventory Issue - Item - Warehouse Pick List Print | 2889 | 11657 | Warehouse Clerk |  |  | Diana Jones | diana.jones@isp.idaho.gov |  | PR-050-090 | 2022-01-24 | 2-2:30PM
7 | Inventory Issue - Item - Warehouse Shipment Feedback | 2890 | 11660 | Warehouse Clerk | Receive and inspect incoming goods. Pick items for shipment/transfer. Dispose of items. Document variances. | Assigned Agency | Diana Jones | diana.jones@isp.idaho.gov |  | PR-050-090 | 2022-01-24 | 2:30-3PM
8 | Inventory Replenishment - Auto Replenishment | 2914 | 11658 | Inventory Manager | Manage/monitor: reconciliation of counts, item master, forecast methods & replenishment, reorder & disposal policy compliance. | Assigned Agency | Randy Byrne | randy.byrne@isp.idaho.gov | Update levels and Manual Replenishment | PR-050-090 | 2022-01-24 | 3-3:30PM
9 | Purchasing - Create Purchase Order | 2753 | 12041 | Buyer | Review requisitions & create purchase orders. Conduct market research & monitor vendor commitments. Approve vendor returns. | Assigned Agency | Randy Byrne | randy.byrne@isp.idaho.gov | Update levels and Manual Replenishment | PR-050-090 | 2022-01-25 | 8:45-9:30 AM
10 | Receive Items to Inventory | 1695 | 11666 | Receiver | Receive and inspect incoming goods. Pick items for shipment/transfer. Dispose of items. Vendor returns. Document variances. | Assigned Agency | Stephen Srodawa | stephen.srodawa@isp.idaho.gov | Receipt Discrepancies | PR-050-090 | 2022-01-25 | 9:30-10AM
11 | Perform Physical Inventory - Mass Freeze Items | 2607 | 11656 | Inventory Manager | Manage/monitor: reconciliation of counts, item master, forecast methods & replenishment, reorder & disposal policy compliance. | Assigned Agency | Randy Byrne | randy.byrne@isp.idaho.gov |  | PR-050-090 | 2022-01-25 | 10-11AM
12 | Perform Physical Inventory - View and Print Count Sheets | 2608 | 11661 | Inventory Manager | Manage/monitor: reconciliation of counts, item master, forecast methods & replenishment, reorder & disposal policy compliance. | Assigned Agency | Randy Byrne | randy.byrne@isp.idaho.gov |  | PR-050-090 | 2022-01-25 | 1-1:30PM
13 | Perform Physical Inventory - Enter Counts | 2775 | 11662 | Inventory Manager | Manage/monitor: reconciliation of counts, item master, forecast methods & replenishment, reorder & disposal policy compliance. | Assigned Agency | Randy Byrne | randy.byrne@isp.idaho.gov |  | PR-050-090 | 2022-01-25 | 1:30-2PM
14 | Perform Physical Inventory - Inventory Variance Update | Added | 12033 | Inventory Manager | Manage/monitor: reconciliation of counts, item master, forecast methods & replenishment, reorder & disposal policy compliance. | Assigned Agency | Randy Byrne | randy.byrne@isp.idaho.gov |  | PR-050-090 | 2022-01-25 | 2-2:30PM
15 | Perform Physical Inventory - Delete Freeze Records | 2776 | 11664 | Inventory Manager | Manage/monitor: reconciliation of counts, item master, forecast methods & replenishment, reorder & disposal policy compliance. | Assigned Agency | Randy Byrne | randy.byrne@isp.idaho.gov |  | PR-050-090 | 2022-01-25 | 2:30-3PM
16 | Post Physical Inventory Adjustments | 1693 | 11665 | Inventory Manager | Manage/monitor: reconciliation of counts, item master, forecast methods & replenishment, reorder & disposal policy compliance. | Assigned Agency | Randy Byrne | randy.byrne@isp.idaho.gov |  | PR-050-090 | 2022-01-25 | 3-3:30PM
17 | Review Beginning/End Inventory Balance |  |  | Staff Accountant | Account analysis to verify Inventory GL balance reflects inventory balance and adjustments. | Assigned Agency | RaeLynn North | raelynn.north@isp.idaho.gov |  | IL-20-ZZ Manage Inventory, Storage, and Movement (See Finance workbook MF-020 diagram) | 2022-01-25 | 3:30 -4 PM
Note on J5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard

## Fixed Assets Acquire To Retire
SIT 3 Scenario - Acquire Fixed Asset to Retire
Agency:
SIT 3 Week - Week 5 - 1/31-2/4
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | NEW SIT 3 ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Create Fixed Asset Requisition | 3041 | 11563 | Requester | Determines requirements & cost estimates for purchase of goods & services. Submits purchase requisition. | Assigned Agency | Debie Beavers-Rudolph | Debie.beavers-rudolph@isp.idaho.gov | Associate with project | PR-010-060 | 2022-01-31 | 8:45-9:30 AM
2 | Approve Requisition | 8539 | 11564 | Approver | Approve transactions such as requisitions, purchase orders, solicitations, and journal entries. | Assigned Agency | .01-1999 RaeLynn 2000-9999 Ken Suchy | raelynn.north@isp.idaho.gov ken.suchy@isp.idaho.gov | Deny Requisition - add note - need more information Approve Requisition | PR-020-020 | 2022-01-31 | 9:30-10AM
3 | Identify Requistions to send to Sourcing Event | 2896 | 11565 | Buyer | Review requisition and create purchase orders. Conduct market research, and monitor vendor commitments. Approve vendor returns. | Assigned Agency | Randy Byrne | randy.byrne@isp.idaho.gov |  | PR-030-020 | 2022-01-31 | 10-11AM
4 | Create Sourcing Event RFQ | 7186 | 11566 | Sourcing Manager | Create souring events, evaluate supplier responses, and oversee selection & award of sourcing events. | Assigned Agency | Randy Byrne | randy.byrne@isp.idaho.gov |  | PR-030-030 | 2022-01-31 | 1-1:30PM
5 | Approve Sourcing Event to Post | 8439 | 11567 | Approver | Approve transactions such as requisitions, purchase orders, solicitations, and journal entries. | Assigned Agency | Debie Beavers-Rudolph or Tina McBride | Debie.beavers-rudolph@isp.idaho.gov | Approve/Deny/Reject Sourcing Event to Post | PR-030-010 | 2022-01-31 | 1:30-2PM
6 | Enter A Manual response | 7187 | 11568 | Sourcing Manager | Develop/oversee supplier list; monitor & evaluate vendors. Evaluate proposals; create souring events, oversee selection & award contracts. | Assigned Agency | Randy Byrne | randy.byrne@isp.idaho.gov |  | PR-030-050 | 2022-01-31 | 2-2:30PM
7 | Analyze and Award an Event to Contract | 7189 | 11569 | Sourcing Manager | Develop/oversee supplier list; monitor & evaluate vendors. Evaluate proposals; create souring events, oversee selection & award contracts. | Assigned Agency | Randy Byrne | randy.byrne@isp.idaho.gov | Split Award by Line | PR-030-050 | 2022-01-31 | 2:30-3PM
8 | Sourcing Event Award Approval | 8440 | 11570 | Approver | Approve transactions such as requisitions, purchase orders, solicitations, and journal entries. | Assigned Agency | Debie Beavers-Rudolph or Tina McBride | Debie.beavers-rudolph@isp.idaho.gov | Approve/Deny/Reject | PR-030-050 | 2022-01-31 | 3-3:30PM
9 | Create Contract - Create a Contract - Contract Tab | 7219 | 11571 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | Assigned Agency | Debie Beavers-Rudolph | Debie.beavers-rudolph@isp.idaho.gov |  | PR-040-010 | 2022-02-01 | 8:45 - 10:30AM
10 | Create Contract - Contract Draft - Articles Tab | 7204 | 11572 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | Assigned Agency | Debie Beavers-Rudolph | Debie.beavers-rudolph@isp.idaho.gov |  | PR-040-010 | 2022-02-01 | 8:45 - 10:30AM
11 | Create Contract - Contract Draft - Participants Tab | 2667 | 11573 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | Assigned Agency | Debie Beavers-Rudolph | Debie.beavers-rudolph@isp.idaho.gov |  | PR-040-010 | 2022-02-01 | 8:45 - 10:30AM
12 | Create Contract - Contract Draft - Lines Tab - Special | 8909 | 11574 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | Assigned Agency | Debie Beavers-Rudolph | Debie.beavers-rudolph@isp.idaho.gov |  | PR-040-010 | 2022-02-01 | 8:45 - 10:30AM
13 | Create Contract - Contract Draft - Contacts Tab | 3335 | 11575 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | Assigned Agency | Debie Beavers-Rudolph | Debie.beavers-rudolph@isp.idaho.gov |  | PR-040-010 | 2022-02-01 | 8:45 - 10:30AM
14 | Create Contract - Contract Draft - Releasing a Contract | 7203 | 11576 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | Assigned Agency | Debie Beavers-Rudolph | Debie.beavers-rudolph@isp.idaho.gov |  | PR-040-010 | 2022-02-01 | 8:45 - 10:30AM
15 | Contract Approval | 8353 | 11578 | Approver | Approve transactions such as requisitions, purchase orders, solicitation & journal entries. | Assigned Agency | Debie Beavers-Rudolph or Tina McBride | Debie.beavers-rudolph@isp.idaho.gov | Approve/Deny/Reject | PR-040-010 | 2022-02-01 | 10:30-11AM
16 | Create Contract - Contract Draft - Activating a Contract | 7202 | 11577 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | Assigned Agency | Debie Beavers-Rudolph | Debie.beavers-rudolph@isp.idaho.gov |  | PR-040-010 | 2022-02-01 | 8:45 - 10:30AM
17 | Create Fixed Asset Requisition | 3041 | 11579 | Requester | Determines requirements & cost estimates for purchase of goods & services. Submits purchase requisition. | Assigned Agency | Debie Beavers-Rudolph | Debie.beavers-rudolph@isp.idaho.gov |  | PR-010-060 | 2022-02-01 | 1-1:30PM
18 | Approve Requisition | 8539 | 11580 | Approver | Approve transactions such as requisitions, purchase orders, solicitations, and journal entries. | Assigned Agency | .01-1999 RaeLynn 2000-9999 Ken Suchy | raelynn.north@isp.idaho.gov ken.suchy@isp.idaho.gov |  | PR-020-020 | 2022-02-01 | 1:30-2PM
19 | Create Purchase Order | 2753 | 11581 | Buyer | Review requisition and create purchase orders. Conduct market research, and monitor vendor commitments. Approve vendor returns. | Assigned Agency | Randy Byrne | randy.byrne@isp.idaho.gov |  | PR-050-040 | 2022-02-01 | 2-2:30PM
20 | Receive Purchase Order | 2178 | 11582 | Receiver | Receive and inspect incoming goods. Pick items for shipment/transfer. Dispose of items. Conduct vendor returns. Document variances. | Assigned Agency | Stephen Srodawa | stephen.srodawa@isp.idaho.gov | Receive less/more than ordered | PR-050-070 | 2022-02-01 | 2:30-3PM
21 | Inspect Item | 2181 | 11583 | Receiver | Receive and inspect incoming goods. Pick items for shipment/transfer. Dispose of items. Conduct vendor returns. Document variances. | Assigned Agency | Stephen Srodawa | stephen.srodawa@isp.idaho.gov | Inspection Failed, Vendor Return | PR-050-070 | 2022-02-01 | 3-3:30PM
22 | Create Invoice | 11447 | 11584 | Payables Invoice Processor | Process interface and XM files. Match payables invoices, and vendor list. Process payables payments. Generate 1099. | Assigned Agency | Joshua Rigenhagen | joshua.rigenhagen@isp.idaho.gov |  | MF-070-050 Enter a PO Invoice | 2022-02-02 | 8:45-9:30 AM
23 | Approve Invoice | 11448 | 11585 | Approver | Approve transactions such as requisitions, purchase orders, solicitations, and journal entries. | Assigned Agency | Lvl 1 Vanessa Wendland Lvl 2 Ken Suchy | Vanessa.Wendland@isp.idaho.gov ken.suchy@isp.idaho.gov |  | MF-070-056 Invoice Approval Process | 2022-02-02 | 9:30-10AM
24 | Match Invoice | 11455 | 11586 | Payables Manager | Void & cancel payments. Reissue & mail warrants. Process period close. | Assigned Agency | Vanessa Wendland | Vanessa.Wendland@isp.idaho.gov |  | MF-070-070 Match Invoices | 2022-02-02 | 10-10:30AM
25 | Process Payment for Invoice | 11442 | 11587 | Payables Manager | Void & cancel payments. Reissue & mail warrants. Process period close. | Assigned Agency | Vanessa Wendland | Vanessa.Wendland@isp.idaho.gov |  | MF-070-100 Process Invoice Payments | 2022-02-02 | 10:30-11AM
26 | Interface AP Asset to Asset Management | 2713 | 11900 | Asset Analyst | Create, add, transfer, adjust, retire, or dispose of assets, including privileges to run depreciation. | Assigned Agency | Diane Fisher | diane.fisher@isp.idaho.gov |  | MF-040-030-010 | 2022-02-02 | 1-1:30PM
27 | Run Release Assets - Update | 8524 | 11905 | Asset Analyst | Create, add, transfer, adjust, retire, or dispose of assets, including privileges to run depreciation. | Assigned Agency | Diane Fisher | diane.fisher@isp.idaho.gov | Associate with project | MF-040-030-020 | 2022-02-02 | 1:30-2PM
28 | Run Depreciation | 8522 | 11904 | Asset Manager | Manage the process to tract fixed asset activity: create, transfer, and retire fixed assets. | Assigned Agency | Diane Fisher | diane.fisher@isp.idaho.gov |  | MF-040-070-020 | 2022-02-02 | 2-2:30PM
29 | Review Fixed Asset GL Account Transactions |  |  | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate, and update allocations. | Assigned Agency | RaeLynn North | raelynn.north@isp.idaho.gov |  | MF-020-010 | 2022-02-02 | 2:30-3PM
30 | Asset Surplus Disposal | 11062 | 11902 | Asset Analyst | Create, add, transfer, adjust, retire, or dispose of assets, including privileges to run depreciation. | Assigned Agency | Diane Fisher | diane.fisher@isp.idaho.gov | Transfer, retire | MF-040-060-020 | 2022-02-02 | 3-3:30PM
31 | Approve Disposal | 11263 | 11903 | Asset Manager | Manage the process to tract fixed asset activity: create, transfer, and retire fixed assets. | Assigned Agency | Justin Freeman | justin.freeman@isp.idaho.gov | Transfer | MF-040-060-020 | 2022-02-02 | 3:30-4PM
32 | Close Contract | 2636 | 11901 | Contract Manager | Compile contract file, including entering contract line-item details, terms & conditions, and pricing, and amends and renews contracts. | Assigned Agency | Debie Beavers-Rudolph | Debie.beavers-rudolph@isp.idaho.gov |  | PR-050-030 | 2022-02-03 | 8:45-9:30 AM
Note on J5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard

## Statewide Contract Procure to P
SIT 3 Scenario - Statewide Contract Procure to Pay
Agency:
SIT 3 Week - Week 5 - 1/31-2/4
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Create Contract with Rebate and Price Breaks Statewide for Envelopes - Create a Contract (Contract Tab) | 7219 | 11992 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-020 | 2022-01-31 | 8:45 - 11 AM
2 | Create Contract with Rebate and Price Breaks Statewide for Envelopes - Contract Draft (Articles) | 7204 | 11987 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-020 | 2022-01-31 | 8:45 - 11 AM
3 | Create Contract with Rebate and Price Breaks Statewide for Envelopes - Contract Draft - Participants | 2667 | 11997 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-020 | 2022-01-31 | 8:45 - 11 AM
4 | Create Contract with Rebate and Price Breaks Statewide for Envelopes - Contract Draft - Lines - Special | 8909 | 11995 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-020 | 2022-01-31 | 8:45 - 11 AM
5 | Create Contract with Rebate and Price Breaks Statewide for Envelopes - Contract Draft - Lines - Purchase Type Detail - Purchase Pricing | 2663 | 11996 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-020 | 2022-01-31 | 8:45 - 11 AM
6 | Create Contract with Rebate and Price Breaks Statewide for Envelopes - Contract Draft - Rebates | 2671 | 11998 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-020 | 2022-01-31 | 8:45 - 11 AM
7 | Create Contract with Rebate and Price Breaks Statewide for Envelopes - Contract Draft - Contacts | 3335 | 11993 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-020 | 2022-01-31 | 8:45 - 11 AM
8 | Create Contract with Rebate and Price Breaks Statewide for Envelopes - Releasing a Contract | 7203 | 11985 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-020 | 2022-01-31 | 8:45 - 11 AM
9 | Contract Approval | 8353 | 11979 | Approver | Approve transactions such as requisitions, purchase orders, solicitation & journal entries. | DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-020 | 2022-01-31 | 1 - 1:30 PM
10 | Create Contract with Rebate and Price Breaks Statewide for Envelopes - Activating a Contract | 7202 | 11978 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-020 | 2022-01-31 | 8:45 - 11 AM
11 | Requisition - RSS | 8325 | 11988 | Requester | Determines requirements & cost estimates for purchase of goods & services. Submits purchase requisition. | Assigned Agency | Debie Beavers-Rudolph | Debie.beavers-rudolph@isp.idaho.gov | distribution to multiple org unit and agencies | PR-020-010 | 2022-01-31 | 1:30 - 2:30 PM
12 | Approve Requisition | 8539 | 11984 | Approver | Approve transactions such as requisitions, purchase orders, solicitation & journal entries. | Assigned Agency | .01-1999 RaeLynn 2000-9999 Ken Suchy | raelynn.north@isp.idaho.gov ken.suchy@isp.idaho.gov |  | PR-020-010 | 2022-01-31 | 2:30 - 3 PM
13 | Create PO from Requisition | 8327 | 11991 | Buyer | Review requisitions & create purchase orders. Conduct market research & monitor vendor commitments. Approve vendor returns. | Assigned Agency | Randy Byrne | randy.byrne@isp.idaho.gov |  | PR-050-040 | 2022-02-01 | 8:45-9:30 AM
14 | Receive Purchase Order | 3064 | 11977 | Receiver | Receive and inspect incoming goods. Pick items for shipment/transfer. Dispose of items. Vendor returns. Document variances. | Assigned Agency | Stephen Srodawa | stephen.srodawa@isp.idaho.gov |  | PR-050-070 | 2022-02-01 | 9:30-10AM
15 | Create Invoice | 11606 | 11983 | Payables Invoice Processor | Process interface and XM files. Match payables invoices, and vendor list. Process payables payments. Generate 1099. | Assigned Agency | Joshua Rigenhagen | joshua.rigenhagen@isp.idaho.gov |  | MF-070-050 Enter a PO Invoice | 2022-02-01 | 10-11AM
16 | Notify Buyer of Discrepancy | 11605 | 11982 | Payables Invoice Processor | Process interface and XM files. Match payables invoices, and vendor list. Process payables payments. Generate 1099. |  | Joshua Rigenhagen | joshua.rigenhagen@isp.idaho.gov |  | MF-070-050 Enter a PO Invoice | 2022-02-01 | 1-1:30PM
17 | Resolve Cost Discrepancy | New | 12004 | Buyer | Review requisition and create purchase orders. Conduct market research, and monitor vendor commitments. Approve vendor returns. | Assigned Agency | Randy Byrne | randy.byrne@isp.idaho.gov |  |  | 2022-02-01 | 1:30-2PM
18 | Submit Resolved Invoice for Approval | 11607 | 11989 | Payables Invoice Processor | Process interface and XM files. Match payables invoices, and vendor list. Process payables payments. Generate 1099. |  | Joshua Rigenhagen | joshua.rigenhagen@isp.idaho.gov |  | MF-070-050 Enter a PO Invoice | 2022-02-01 | 2-2:30PM
19 | Approve Invoice | 11608 | 11990 | Approver | Approve transactions such as requisitions, purchase orders, solicitations, and journal entries. | Assigned Agency | Lvl 1 Vanessa Wendland Lvl 2 Ken Suchy | Vanessa.Wendland@isp.idaho.gov ken.suchy@isp.idaho.gov |  | MF-070-056 Invoice Approval Process | 2022-02-01 | 2:30-3PM
20 | Match Invoice | 11609 | 11994 | Payables Manager | Void & cancel payments. Reissue & mail warrants. Process period close. | Assigned Agency | Vanessa Wendland | Vanessa.Wendland@isp.idaho.gov |  | MF-070-070 Match Invoices | 2022-02-01 | 3-3:30PM
21 | Process Payment for Invoice | 11442 | 11981 | Payables Manager | Void & cancel payments. Reissue & mail warrants. Process period close. | Assigned Agency | Vanessa Wendland | Vanessa.Wendland@isp.idaho.gov |  | MF-070-100 Process Invoice Payments | 2022-02-01 | 3-3:30PM
22 | Journalize | 11440 | 11980 | Payables Manager | Void & cancel payments. Reissue & mail warrants. Process period close. |  | Vanessa Wendland | Vanessa.Wendland@isp.idaho.gov |  | MF-070-110 Journalize AP Distributions | 2022-02-01 | 3-3:30PM
23 | Renew/Addendum Statewide Contract | 2773 | 11986 | Contract Manager | Compile contract file, including entering contract line-item details, terms & conditions, and pricing, and amends and renews contracts. | DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-050-010 | 2022-02-02 | 8:45-9:30 AM
24 | Load Rebate Invoices | New | 11999 | Supply Management Admin or Processor |  | Assigned Agency |  |  |  | PR-050-010 | 2022-02-02 | 9:30-10AM
25 | Calculate Rebate Amounts Due for a Contract | New | 12000 | Supply Management Admin or Processor | [5 empty] | PR-050-010 | 2022-02-02 | 10-11AM
26 | Review Rebate Due Information | New | 12001 | Contract Manager | Compile contract file, including entering contract line-item details, terms & conditions, and pricing, and amends and renews contracts. | Assigned Agency | DOP Tester | contractadmin@adm.idaho.gov |  | PR-050-010 | 2022-02-02 | 1-1:30PM
27 | Apply Rebate (Enter a Rebate Invoice in Payables | New | 12002 | Payables Manager | Void & cancel payments. Reissue & mail warrants. Process period close. |  | Lynn Christian | lynn.christian@adm.idaho.gov | There isn't an invoice type of Rebate Invoice???? | MF-260-070ZZ | 2022-02-03 | 8:45-9:30 AM
28 | Review Rebate Information | New | 12003 | Contract Manager | Compile contract file, including entering contract line-item details, terms & conditions, and pricing, and amends and renews contracts. |  | DOP Tester | contractadmin@adm.idaho.gov |  | PR-050-010 | 2022-02-03 | 9:30-10AM
29 | Verify Rebates posted in Cash Account |  |  | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Genny Casiano | genny.casiano@adm.idaho.gov |  | MF-260-070ZZ | 2022-02-03 | 10-11 AM
Note on J5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard

## AR Credit Monitoring
SIT 3 Scenario - AR Credit Monitoring
Agency:
SIT Week - Week 6 - 2/7 - 2/11
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | ALM SIT 3 Test ID# | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution Date | Window to Complete Script
1 | Finance Charge Code Setup | 2845 | 12021 | Receivables Manager | Reconcile accounts receivables & collections and assess late fees. | Assigned Agency | RaeAnn Newman, Melissa Torres, or Eileen Allen | raeann.newman@isp.idaho.gov, melissa.torres@isp.idaho.gov, eileen.allen@isp.idaho.gov |  | MF-260-010 | 2022-02-07 | 8:45-10 AM
2 | Finance Charge Text Code Setup | 2846 | 12022 | Receivables Manager | Reconcile accounts receivables & collections and assess late fees. | Assigned Agency | RaeAnn Newman, Melissa Torres, or Eileen Allen | raeann.newman@isp.idaho.gov, melissa.torres@isp.idaho.gov, eileen.allen@isp.idaho.gov |  | MF-260-010 | 2022-02-07 | 8:45-10 AM
3 | Run Finance Charge Initiation | 8680 | 12018 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Dessislava Tulilova | Dessislava.Tulilova@isp.idaho.gov |  | MF-260-030 | 2022-02-07 | 10 AM-2 PM
4 | Run Finance Charge Late Payment | 8681 | 12020 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Dessislava Tulilova | Dessislava.Tulilova@isp.idaho.gov |  | MF-260-120 | 2022-02-07 | 10 AM-2 PM
5 | Create an Invoice Write Off | 10995 | 12019 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Dessislava Tulilova | Dessislava.Tulilova@isp.idaho.gov |  | MF-260-120 | 2022-02-07 | 10 AM-2 PM
6 | Run Customer Statements | 10986 | 12023 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Dessislava Tulilova | Dessislava.Tulilova@isp.idaho.gov |  | MF-260-060 | 2022-02-08 | 8:45 - 11 AM
7 | Run Advanced Dunning Letter Selection | 11409 | 12024 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Dessislava Tulilova | Dessislava.Tulilova@isp.idaho.gov |  | MF-260-120 | 2022-02-08 | 8:45 - 11 AM
8 | Run Advanced Dunning Letter File Generation | 11410 | 12025 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Dessislava Tulilova | Dessislava.Tulilova@isp.idaho.gov |  | MF-260-120 | 2022-02-08 | 8:45 - 11 AM
9 | Run Company Aging Report | 11898 | 12027 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Dessislava Tulilova | Dessislava.Tulilova@isp.idaho.gov |  | MF-260-110 | 2022-02-08 | 8:45 - 11 AM
10 | Run Customer Aging Report | 11899 | 12028 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Dessislava Tulilova | Dessislava.Tulilova@isp.idaho.gov |  | MF-260-110 | 2022-02-08 | 1- 2PM
11 | Review Invoices Paid Late | 11896 | 12026 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Dessislava Tulilova | Dessislava.Tulilova@isp.idaho.gov |  | MF-260-110 | 2022-02-08 | 1- 2PM
Note on J5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard

## Svc Cntract Interagency Billing
SIT 3 Scenario - Service Contract Procure to Pay Interagency Billing
Agency:
SIT Week - Week 6 - 2/7 - 2/11
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Create Requisition for Service | 8323 | 11936 | Requester | Determines requirements & cost estimates for purchase of goods & services. Submits purchase requisition. | Assigned Agency | Debie Beavers-Rudolph | Debie.beavers-rudolph@isp.idaho.gov |  | PR-020-010 | 2022-02-08 | 8:45-9:30 AM
2 | Approve Requisition | 8539 | 11929 | Approver | Approve transactions such as requisitions, purchase orders, solicitations, and journal entries. | Assigned Agency | .01-1999 Vanessa 2000-9999 Ken Suchy | vanessa.wendland@isp.idaho.gov ken.suchy@isp.idaho.gov |  | PR-020-020 | 2022-02-08 | 9:30-10AM
3 | Identify Requistions to send to Sourcing Event | 2896 | 11934 | Buyer | Review requisitions & create purchase orders. Conduct market research & monitor vendor commitments. Approve vendor returns. | Assigned Agency | Randy Byrne | randy.byrne@isp.idaho.gov |  | PR-020-020 | 2022-02-08 | 10-11AM
4 | Create Sourcing Event RFP | 7186 | 11949 | Sourcing Manager | Create souring events, evaluate supplier responses, and oversee selection & award of sourcing events. | Assigned Agency | Randy Byrne and DOP Tester | randy.byrne@isp.idaho.gov - contractadmin@adm.idaho.gov |  | PR-030-020 | 2022-02-08 | 1-1:30PM
5 | Approve Sourcing Event to Post | 7191 | 11941 | Approver | Approve transactions such as requisitions, purchase orders, solicitations, and journal entries. | Assigned Agency | DOP Tester | contractadmin@adm.idaho.gov |  | PR-030-010 | 2022-02-08 | 1:30-2PM
6 | Supplier Responds to Event | 1249 | 11944 | Supplier (Luma Team Member) |  | DOP |  |  |  | PR-030-020 | 2022-02-08 | 2-2:30PM
7 | Analyze and Award Suppler Responses | Refer to upload Template | 11952 | Sourcing Manager | Create souring events, evaluate supplier responses, and oversee selection & award of sourcing events. | Assigned Agency | DOP Tester | contractadmin@adm.idaho.gov |  | PR-030-050 | 2022-02-08 | 2:30-3PM
8 | Sourcing Event Award Approval | 7191 | 11947 | Approver | Approve transactions such as requisitions, purchase orders, solicitations, and journal entries. | Assigned Agency | DOP Tester | contractadmin@adm.idaho.gov |  | PR-030-040 | 2022-02-08 | 3-3:30PM
9 | Create Contract - Create a Contract - Contract Tab | 7219 | 11942 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | Assigned Agency/DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-010 | 2022-02-09 | 8:45 - 10:30AM
10 | Create Contract - Contract Draft - Articles Tab | 7204 | 11951 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | Assigned Agency/DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-010 | 2022-02-09 | 8:45 - 10:30AM
11 | Create Contract - Contract Draft - Participants Tab | 2667 | 11950 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | Assigned Agency/DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-010 | 2022-02-09 | 8:45 - 10:30AM
12 | Create Contract - Contract Draft - Lines Tab - Service | 3375 | 11948 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | Assigned Agency/DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-010 | 2022-02-09 | 8:45 - 10:30AM
13 | Create Contract - Contract Draft - Contacts Tab | 3335 | 11940 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | Assigned Agency/DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-010 | 2022-02-09 | 8:45 - 10:30AM
14 | Create Contract - Contract Draft - Releasing a Contract | 7203 | 11930 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | Assigned Agency/DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-010 | 2022-02-09 | 8:45 - 10:30AM
15 | Contract Approval | 8353 | 11939 | Approver | Approve transactions such as requisitions, purchase orders, solicitations, and journal entries. | Assigned Agency | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-010 | 2022-02-09 | 10:30-11AM
16 | Create Contract - Contract Draft - Activating a Contract | 7202 | 11931 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | Assigned Agency/DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-010 | 2022-02-09 | 8:45 - 10:30AM
17 | Create Contract Invoice | 11459 | 11933 | Payables Invoice Processor | Process interface and XM files. Match payables invoices, and vendor list. Process payables payments. Generate 1099. | Assigned Agency | Joshua Rigenhagen | joshua.rigenhagen@isp.idaho.gov |  | MF-070-050 Enter a PO Invoice | 2022-02-09 | 1 - 1:30PM
18 | Approve Invoice | 11460 | 11938 | Payables Manager | Void & cancel payments. Reissue & mail warrants. Process period close. | Assigned Agency | Vanessa Wendland | Vanessa.Wendland@isp.idaho.gov |  | MF-070-056 Invoice Approval Process | 2022-02-09 | 1:30 -3:30 PM
19 | Match Invoice | 11462 | 11946 | Payables Manager | Void & cancel payments. Reissue & mail warrants. Process period close. | Assigned Agency | Vanessa Wendland | Vanessa.Wendland@isp.idaho.gov |  | MF-070-070 Match Invoices | 2022-02-09 | 1:30 -3:30 PM
20 | Process Payment for Invoice | 11442 | 11932 | Payables Manager | Void & cancel payments. Reissue & mail warrants. Process period close. | Assigned Agency | Vanessa Wendland | Vanessa.Wendland@isp.idaho.gov |  | MF-070-100 Process Invoice Payments | 2022-02-09 | 1:30 -3:30 PM
21 | Create Interagency Billing - Basic | 8795 | 11945 | Intercompany Billing Specialist | Handle setup and processing of intercompany billing. | Assigned Agency | Melissa Torres | melissa.torres@isp.idaho.gov |  | MF-260-030ZZ | 2022-02-10 | 8:45-9:30 AM
22 | Identify Unpaid Interagency Billings | 11536 | 11937 | Payables Invoice Processor | Process interface and XM files. Match payables invoices, and vendor list. Process payables payments. Generate 1099. | Assigned Agency | Joshua Rigenhagen | joshua.rigenhagen@isp.idaho.gov |  | MF-070-050 Enter a PO Invoice | 2022-02-10 | 9:30-10AM
23 | Reclassify Interagency Expenditure Coding (AP110 Distribution Changes on Paid Invoice) | 11624 | 11935 | Payables Invoice Processor | Process interface and XM files. Match payables invoices, and vendor list. Process payables payments. Generate 1099. | Assigned Agency | Joshua Rigenhagen | joshua.rigenhagen@isp.idaho.gov |  | MF-070-050 Enter a PO Invoice | 2022-02-10 | 10-11AM
24 | Settle an Interagency Billing | 8794 | 11943 | Intercompany Billing Specialist | Handle setup and processing of intercompany billing. | Assigned Agency | Melissa Torres | melissa.torres@isp.idaho.gov |  | MF-260-030ZZ | 2022-02-10 | 1-1:30PM
Note on J5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard

## Cash Ledger Payment
SIT 3 Scenario - Cash Ledger Payment
Agency:
SIT Week - Week 7 - 2/14 -2/18
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Enter Cash Payment | Cash Payment Entry.xlsx | 12075 | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Ishaq Kayed | ishaq.kayed@isp.idaho.gov | Rotary/Site Draft, L Warrants |  | 2022-02-14 | 8:45 - 10 AM
1A | Record Cash Payment |  | 12525 | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Ishaq Kayed | ishaq.kayed@isp.idaho.gov |  |  | 2022-02-14 | 8:45 - 10 AM
2 | Approve Cash Payment | Cash Approve Cash Payment.xlsx | 12076 | Cash Manager | Manage all cash transactions. Review and update cash management policy as needed. | Assigned Agency | Vanessa Wendland | Vanessa.Wendland@isp.idaho.gov |  |  | 2022-02-14 | 10 - 11:30 AM
3 | Cash Requirements | Cash Requirements.xlsx | 12077 | Payables Payment Processor | Perform Cash Requirements, Schedule Payments, Complete Payment Cycle | Assigned Agency | Vanessa Wendland | Vanessa.Wendland@isp.idaho.gov |  | MF-070-100 Process Invoice Payments | 2022-02-14 | 1 - 2:30 PM
4 | Review Check in Cash | Cash Review Check in Cash Management.xlsx | 12078 | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Ishaq Kayed | ishaq.kayed@isp.idaho.gov | Redeem or Void then Review again |  | 2022-02-14 | 2:30 - 4 PM
5 | Journalize Distributions | Cash Journalize Cash Transaction.xlsx | 12079 | Cash Manager | Manage all cash transactions. Review and update cash management policy as needed. | Assigned Agency | Vanessa Wendland | Vanessa.Wendland@isp.idaho.gov |  |  | 2022-02-15 | 8:45 - 10 AM
6 | Verify Results in Global Ledger Account Analysis |  | 12082 | Staff Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | RaeLynn North | raelynn.north@isp.idaho.gov |  |  | 2022-02-15 | 10 - 11:30 AM
7 | Optional Void Cash Payment for Status Updates | Cash Void Cash Payment.xlsx | 12080 | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Ishaq Kayed | ishaq.kayed@isp.idaho.gov |  |  | 2022-02-15 | 1 - 2:30 PM
8 | Optional Void Cash Payment: Payment Void Stop Pay Update | 12161 | 12161 | Payables Payment Processor | Perform Cash Requirements, Schedule Payments, Complete Payment Cycle | Assigned Agency | Vanessa Wendland | Vanessa.Wendland@isp.idaho.gov |  |  | 2022-02-15 | 1 - 2:30 PM
9 | Optional Redeem Warrant for Status Updates | Cash Redeem Warrant.xlsx | 12081 | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Ishaq Kayed | ishaq.kayed@isp.idaho.gov |  |  | 2022-02-15 | 2:30 - 4 PM
Note on I4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard
Note on K5: Glenda Smith: Cash BPR's are not correct, do not reference.

## Nonstate Billing
SIT 3 Scenario - Non-State Billing_Master
Agency:
SIT Week - Week 7 - 2/14 -2/18
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 TEST ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Create Manual Batch Header | 10963 | 12456 | Billing Manager | Create and maintain bills for Accounts Receivable. | Assigned Agency | RaeAnn Newman, Melissa Torres, or Eileen Allen | raeann.newman@isp.idaho.gov, melissa.torres@isp.idaho.gov, eileen.allen@isp.idaho.gov | Interfaced Invoices, Recurring Invoices | MF-260-030 | 2022-02-14 | 8:45-9:30 AM
2 | Create Billing Invoice | 10962 | 12449 | Billing Manager | Create and maintain bills for Accounts Receivable. | Assigned Agency | RaeAnn Newman, Melissa Torres, or Eileen Allen | raeann.newman@isp.idaho.gov, melissa.torres@isp.idaho.gov, eileen.allen@isp.idaho.gov |  | MF-260-030 | 2022-02-14 | 9:30-10AM
3 | Create Credit Memo | 11562 | 12446 | Billing Manager | Create and maintain bills for Accounts Receivable. | Assigned Agency | RaeAnn Newman, Melissa Torres, or Eileen Allen | raeann.newman@isp.idaho.gov, melissa.torres@isp.idaho.gov, eileen.allen@isp.idaho.gov | Debit Memo | MF-260-100 | 2022-02-14 | 10-10:30 AM
4 | Approve Invoice Batch | 11603 | 12452 | Billing Manager | Create and maintain bills for Accounts Receivable. | Assigned Agency | RaeAnn Newman, Melissa Torres, or Eileen Allen | raeann.newman@isp.idaho.gov, melissa.torres@isp.idaho.gov, eileen.allen@isp.idaho.gov |  | MF-260-060 | 2022-02-14 | 10:30 - 11 AM
5 | Run Invoice Batch Release | 10966 | 12465 | Billing Manager | Create and maintain bills for Accounts Receivable. | Assigned Agency | RaeAnn Newman, Melissa Torres, or Eileen Allen | raeann.newman@isp.idaho.gov, melissa.torres@isp.idaho.gov, eileen.allen@isp.idaho.gov |  | MF-260-060 | 2022-02-14 | 1-1:30PM
6 | Run Invoice Register and Print | 3511 | 12459 | Billing Manager | Create and maintain bills for Accounts Receivable. | Assigned Agency | RaeAnn Newman, Melissa Torres, or Eileen Allen | raeann.newman@isp.idaho.gov, melissa.torres@isp.idaho.gov, eileen.allen@isp.idaho.gov |  | MF-260-060 | 2022-02-14 | 1:30-2PM
7 | Run Sub System Update (Interface Invoices to AR and Journalize) | 10965 | 12463 | Billing Manager | Create and maintain bills for Accounts Receivable. | Assigned Agency | RaeAnn Newman, Melissa Torres, or Eileen Allen | raeann.newman@isp.idaho.gov, melissa.torres@isp.idaho.gov, eileen.allen@isp.idaho.gov |  | MF-260-090 | 2022-02-14 | 2-2:30PM
8 | Create Invoice Batch in AR | 8661 | 12458 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Dessislava Tulilova | Dessislava.Tulilova@isp.idaho.gov |  | MF-260-060 | 2022-02-14 | 2:30-3PM
9 | Create Invoice in AR | 8660 | 12447 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Dessislava Tulilova | Dessislava.Tulilova@isp.idaho.gov | Interfaced Invoices | MF-260-030 | 2022-02-14 | 3 - 3:30 PM
10 | Create Credit Memo in AR | 2812 | 12451 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Dessislava Tulilova | Dessislava.Tulilova@isp.idaho.gov | Debit Memo | MF-260-050 | 2022-02-14 | 3:30 - 4 PM
11 | Approve AR Invoice (if not interfaced from BL) | 11603 | 12472 | Receivables Manager | Reconcile accounts receivables & collections and assess late fees. | Assigned Agency | RaeAnn Newman, Melissa Torres, or Eileen Allen | raeann.newman@isp.idaho.gov, melissa.torres@isp.idaho.gov, eileen.allen@isp.idaho.gov |  | MF-260-ZZ | 2022-02-15 | 8:45-9:30 AM
12 | Run Journalize Preview | 8662 | 12466 | Receivables Manager | Reconcile accounts receivables & collections and assess late fees. | Assigned Agency | RaeAnn Newman, Melissa Torres, or Eileen Allen | raeann.newman@isp.idaho.gov, melissa.torres@isp.idaho.gov, eileen.allen@isp.idaho.gov |  | MF-260-090 | 2022-02-15 | 9:30-10AM
13 | Run Journalize Distributions |  | 12464 | Receivables Manager | Reconcile accounts receivables & collections and assess late fees. | Assigned Agency | RaeAnn Newman, Melissa Torres, or Eileen Allen | raeann.newman@isp.idaho.gov, melissa.torres@isp.idaho.gov, eileen.allen@isp.idaho.gov |  | MF-260-090 | 2022-02-15 | 10-10:30 AM
14 | Create Payment Batch | 8668 | 12457 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Dessislava Tulilova | Dessislava.Tulilova@isp.idaho.gov | Interfaced Payments | MF-260-070 | 2022-02-15 | 10:30 - 11 AM
15 | Create Customer Payment | 8666 | 12448 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Dessislava Tulilova | Dessislava.Tulilova@isp.idaho.gov | Interfaced Payments | MF-260-070 | 2022-02-15 | 1-1:30PM
16 | Create Payment Remittance | 11895 | 12470 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Dessislava Tulilova | Dessislava.Tulilova@isp.idaho.gov |  | MF-260-070 | 2022-02-15 | 1:30-2PM
17 | Create Non AR Cash Payment | 8673 | 12468 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Dessislava Tulilova | Dessislava.Tulilova@isp.idaho.gov | Interfaced Payments | MF-260-070 | 2022-02-15 | 2-2:30PM
18 | Apply Payment to Invoice | 8669 | 12460 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Dessislava Tulilova | Dessislava.Tulilova@isp.idaho.gov | Automatic Cash Application | MF-260-080 | 2022-02-15 | 2:30-3PM
19 | Apply Credit Memo to Invoice | 2513 | 12469 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Dessislava Tulilova | Dessislava.Tulilova@isp.idaho.gov | Automatic Memo Application | MF-260-100 | 2022-02-15 | 3 - 3:30 PM
20 | Approve Payment Batch | 11603 | 12473 | Receivables Manager | Reconcile accounts receivables & collections and assess late fees. | Treasury | RaeAnn Newman, Melissa Torres, or Eileen Allen | raeann.newman@isp.idaho.gov, melissa.torres@isp.idaho.gov, eileen.allen@isp.idaho.gov |  | MF-260-ZZ | 2022-02-15 | 3:30 - 4 PM
21 | Create Payment Application Reversal | 11064 | 12450 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Dessislava Tulilova | Dessislava.Tulilova@isp.idaho.gov |  | MF-260-ZZ | 2022-02-16 | 8:45-9:30 AM
22 | Run Application Reversal Creation | 11065 | 12455 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Dessislava Tulilova | Dessislava.Tulilova@isp.idaho.gov |  | MF-260-ZZ | 2022-02-16 | 9:30-10AM
23 | Application Close | 8670 | 12462 | Receivables Manager | Reconcile accounts receivables & collections and assess late fees. | Assigned Agency | RaeAnn Newman, Melissa Torres, or Eileen Allen | raeann.newman@isp.idaho.gov, melissa.torres@isp.idaho.gov, eileen.allen@isp.idaho.gov |  | MF-260-130 | 2022-02-16 | 10-10:30 AM
24 | Run Journalize Preview | 8671 | 12467 | Receivables Manager | Reconcile accounts receivables & collections and assess late fees. | Assigned Agency | RaeAnn Newman, Melissa Torres, or Eileen Allen | raeann.newman@isp.idaho.gov, melissa.torres@isp.idaho.gov, eileen.allen@isp.idaho.gov |  | MF-260-090 | 2022-02-16 | 10:30 - 11 AM
25 | Run Journalize Distributions | 8672 | 12474 | Receivables Manager | Reconcile accounts receivables & collections and assess late fees. | Assigned Agency | RaeAnn Newman, Melissa Torres, or Eileen Allen | raeann.newman@isp.idaho.gov, melissa.torres@isp.idaho.gov, eileen.allen@isp.idaho.gov |  | MF-260-090 | 2022-02-16 | 1-1:30PM
26 | Reconcile AR module to GL balance (Account Analysis/Reports) | 11672 | 12453 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate, and update allocations. | Assigned Agency | RaeLynn North | raelynn.north@isp.idaho.gov |  | MF-260-090 | 2022-02-16 | 1:30-2PM
27 | View Cash Fund Balance | Cash Fund Balance.lxsx - maybe in ALM already |  | Financial Viewer | View-only access to key financial workstreams and structures, such as Chart of Accounts, financial reports, and financial transaction data. | Assigned Agency | Ken Suchy | ken.suchy@isp.idaho.gov |  | MF-260-090 | 2022-02-16 | 2-2:30PM
28 | Create Return to Maker Payment | 11120 | 12454 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Dessislava Tulilova | Dessislava.Tulilova@isp.idaho.gov |  | MF-260-ZZ | 2022-02-16 | 2:30-3PM
29 | Release Return to Maker Payment | 11124 | 12461 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Dessislava Tulilova | Dessislava.Tulilova@isp.idaho.gov |  | MF-260-ZZ | 2022-02-16 | 3 - 3:30 PM
30 | Create Payment Reversal | 11064 | 12475 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Dessislava Tulilova | Dessislava.Tulilova@isp.idaho.gov |  | MF-260-ZZ | 2022-02-16 | 3:30 - 4 PM
31 | Run Application Reversal Creation | 11065 | 12476 | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Dessislava Tulilova | Dessislava.Tulilova@isp.idaho.gov |  | MF-260-ZZ | 2022-02-17 | 8:45-9:30 AM
Note on J5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard

## Procure to Pay Vendor Mgt Voids
SIT 3 Scenario - Procure to Pay with Void and Vendor Update
Agency:
SIT Week - Week 7 - 2/14 -2/18
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | Luma Role (role switcher) | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Create Requisition - Special | 8324 | Requester | Assigned Agency | Debie Beavers-Rudolph | Debie.beavers-rudolph@isp.idaho.gov |  | PR-020-010 | 2022-02-14 | 8:45-9:30 AM
2 | Approve Requisition | 8539 | Approver | Assigned Agency | .01-1999 RaeLynn 2000-9999 Ken Suchy | raelynn.north@isp.idaho.gov ken.suchy@isp.idaho.gov | Requisition not approved | PR-010-060 | 2022-02-14 | 9:30-10AM
3 | Create Purchase Order | 8170 | Buyer | Assigned Agency | Randy Byrne | randy.byrne@isp.idaho.gov |  | PR-050-040 | 2022-02-14 | 10-10:30 AM
4 | Receive Purchase Order | 4587 | Receiver | Assigned Agency | Stephen Srodawa | stephen.srodawa@isp.idaho.gov |  | PR-050-070 | 2022-02-14 | 10:30 - 11 AM
5 | Create Invoice | 11519 | Payables Invoice Processor | Assigned Agency | Joshua Rigenhagen | joshua.rigenhagen@isp.idaho.gov |  | MF-070-050 Enter a PO Invoice | 2022-02-14 | 1-1:30PM
6 | Approve Invoice | 11520 | Approver | Assigned Agency | Lvl 1 Vanessa Wendland Lvl 2 Ken Suchy | Vanessa.Wendland@isp.idaho.gov ken.suchy@isp.idaho.gov |  | MF-070-056 Invoice Approval Process | 2022-02-14 | 1:30-2PM
7 | Match Invoice | 11458 | Payables Manager | Assigned Agency | Vanessa Wendland | Vanessa.Wendland@isp.idaho.gov |  | MF-070-070 Match Invoices | 2022-02-14 | 2-2:30PM
8 | Process Payment for Invoice | 11442 | Payables Manager | Assigned Agency | Vanessa Wendland | Vanessa.Wendland@isp.idaho.gov |  | MF-070-100 Process Invoice Payments | 2022-02-14 | 2:30-3PM
9 | Journalize | 11440 | Payables Manager |  | Vanessa Wendland | Vanessa.Wendland@isp.idaho.gov |  | MF-070-110 Journalize AP Distributions | 2022-02-14 | 3 - 3:30 PM
10 | Void Payment | 12080 | Cash Accountant | SCO | Ishaq Kayed | ishaq.kayed@isp.idaho.gov |  | MF-200-060 Void Cash Transactions | 2022-02-14 | 3:30 - 4 PM
11 | Cancel Invoice | 11523 | Payables Manager | Assigned Agency | Vanessa Wendland | Vanessa.Wendland@isp.idaho.gov |  | MF-070-050 Enter a PO Invoice | 2022-02-15 | 8:45-9:30 AM
12 | Request a new vendor | 11524 | Payables Invoice Processor | Assigned Agency | Joshua Rigenhagen | joshua.rigenhagen@isp.idaho.gov |  | PR-040-030 Create and Maintain Vendor | 2022-02-15 | 9:30-10AM
13 | Approve and setup new vendor | 11525 - Only SCO staff can do this | Approver | SCO | Lvl 1 Vanessa Wendland Lvl 2 Ken Suchy | Vanessa.Wendland@isp.idaho.gov ken.suchy@isp.idaho.gov | Disapprove vendor | PR-040-030 Create and Maintain Vendor | 2022-02-15 | 10-10:30 AM
14 | Create Invoice | 11519 | Payables Invoice Processor | Assigned Agency | Joshua Rigenhagen | joshua.rigenhagen@isp.idaho.gov |  | MF-070-050 Enter a PO Invoice | 2022-02-15 | 10:30 - 11 AM
15 | Approve Invoice | 11520 | Approver | Assigned Agency | Lvl 1 Vanessa Wendland Lvl 2 Ken Suchy | Vanessa.Wendland@isp.idaho.gov ken.suchy@isp.idaho.gov |  | MF-070-056 Invoice Approval Process | 2022-02-15 | 1-1:30PM
16 | Match Invoice | 11522 | Payables Invoice Processor | Assigned Agency | Joshua Rigenhagen | joshua.rigenhagen@isp.idaho.gov |  | MF-070-070 Match Invoices | 2022-02-15 | 1:30-2PM
17 | Process Payment for Invoice | 11442 | Payables Manager | Assigned Agency | Vanessa Wendland | Vanessa.Wendland@isp.idaho.gov |  | MF-070-100 Process Invoice Payments | 2022-02-15 | 2-2:30PM
18 | Post Transactions - Journalize | 11440 | Payables Manager | Assigned Agency | Vanessa Wendland | Vanessa.Wendland@isp.idaho.gov |  | MF-070-110 Journalize AP Distributions | 2022-02-15 | 2:30-3PM
19 | Cash Ledger Journalize | 12079 | Cash Manager | Assigned Agency | Vanessa Wendland | Vanessa.Wendland@isp.idaho.gov |  | MF-200-050 Reconcile Payments Payables and Disbursements | 2022-02-15 | 3 - 3:30 PM
20 | Verify Voided Payables Checks | 12153 | Cash Accountant | Assigned Agency | Ishaq Kayed | ishaq.kayed@isp.idaho.gov |  | MF-200-060 Void Cash Transactions | 2022-02-15 | 3:30 - 4 PM
21 | View Fund Balance | Cash Fund Balance.xlsx (in ALM?)(in Cash Deposit to Revenue Scenario) | Cash Accountant | Assigned Agency | Ishaq Kayed | ishaq.kayed@isp.idaho.gov |  | MF-200-050 Reconcile Payments Payables and Disbursements | 2022-02-16 | 8:45-9:30 AM
22 | Comparative report from Birst |  | Cash Accountant | Assigned Agency | Ishaq Kayed | ishaq.kayed@isp.idaho.gov |  | MF-200-ZZ | 2022-02-16 | 9:30-10AM
23 | Cash Revenue Daily Report - Birst |  | Cash Manager | Assigned Agency | Vanessa Wendland | Vanessa.Wendland@isp.idaho.gov |  | MF-200-ZZ | 2022-02-16 | 10-10:30 AM
Note on H5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard

## Global Ledger Entries and Analy
SIT 3 Scenario - Global Legder Processing and Analysis
Agency:
SIT Week - Week 8 - 2/21/ - 2/25
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Create a Front-End Split Journal Entry (Front End Split Projects Only) | Refer to Upload Template | 12154 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | RaeLynn North | raelynn.north@isp.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-010 | 2022-02-23 | 8:45-9:30 AM
2 | Create a Journal Entry | Refer to Upload Template | 11668 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | RaeLynn North | raelynn.north@isp.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-010 | 2022-02-23 | 9:30-10AM
3 | Approve a Journal Entry | Refer to Upload Template | 11669 | Approver | Approve transactions such as requisitions, purchase orders, solicitation & journal entries. | Assigned Agency | Vanessa Wendland | Vanessa.Wendland@isp.idaho.gov |  | MF-025-060 | 2022-02-23 | 10-11AM
4 | Create a Journal Entry from an Existing Journal | Refer to Upload Template | 11671 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | RaeLynn North | raelynn.north@isp.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-010 | 2022-02-23 | 1-1:30PM
5 | Create a Journal Entry from a Template | Refer to Upload Template | 11670 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | RaeLynn North | raelynn.north@isp.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-010 | 2022-02-23 | 1:30-2PM
6 | Create a Recurring Journal | Refer to Upload Template | 11673 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | RaeLynn North | raelynn.north@isp.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-020 | 2022-02-23 | 2-2:30PM
7 | Journalize a Recurring Journal Entry | Refer to Upload Template | 12155 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | RaeLynn North | raelynn.north@isp.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-030 | 2022-02-23 | 2:30-3PM
8 | Post Multiple Journal Entries | Refer to Upload Template | 12156 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | RaeLynn North | raelynn.north@isp.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-23 | 3-3:30PM
9 | Post Journals from Subsystems | Refer to Upload Template | 12157 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | RaeLynn North | raelynn.north@isp.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-050 | 2022-02-24 | 8:45-9:30 AM
10 | Validate (here) Reconcile (close) Subsystems to the General Ledger | Bill will put these scripts here and in close scenario | TBD | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | RaeLynn North | raelynn.north@isp.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-24 | 9:30-10AM
11 | Analyze Global Ledger Totals | Refer to Upload Template | 12158 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | RaeLynn North | raelynn.north@isp.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-24 | 10-11AM
12 | Perform Account Analysis | Refer to Upload Template | 11672 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | RaeLynn North | raelynn.north@isp.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-24 | 1-1:30PM
13 | Perform Fund Analysis | Refer to Upload Template | 12159 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | RaeLynn North | raelynn.north@isp.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-24 | 1:30-2PM
14 | Perform Organizational Unit Analysis | Refer to Upload Template | 12160 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | RaeLynn North | raelynn.north@isp.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-24 | 2-2:30PM
15 | View Transactions by Entity-Account | Refer to Upload Template | 11674 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | RaeLynn North | raelynn.north@isp.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-25 | 9- 9:30 AM
16 | BIRST/BI/CSF Analytic Reporting |  | TBD | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | RaeLynn North | raelynn.north@isp.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-25 | 9:30 - 10 AM
17 | Evaluate Encumbrances | Placeholder - Judy and Bill (and Eileen/Cathy) are working on script for this; will have this week (12/23/21) | TBD | Staff Accountant |  | Assigned Agency | RaeLynn North | raelynn.north@isp.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-25 | 10 - 11 AM
Note on J5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard

## Punchout Request to Payment
SIT 3 Scenario - Punchout Request to Payment
Agency:
SIT Week - Week 8 - 2/21 - 2/25
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Create Punchout Requisition using RSS | 3501 | 11924 | Requester | Determines requirements & cost estimates for purchase of goods & services. Submits purchase requisition. | Assigned Agency | Debie Beavers-Rudolph | Debie.beavers-rudolph@isp.idaho.gov |  | PR-020-010 | 2022-02-22 | 8:45-9:30 AM
2 | Approve Requisition | 8539 | 11925 | Approver | Approve transactions such as requisitions, purchase orders, solicitation & journal entries. | Assigned Agency | .01-1999 RaeLynn 2000-9999 Ken Suchy | raelynn.north@isp.idaho.gov ken.suchy@isp.idaho.gov | Deny Requisition - add note - need more information Approve Requisition | PR-010-060 | 2022-02-22 | 9:30-10AM
3 | Locate Punchout PO | Refer to Upload template | 12034 | Requester |  |  | Debie Beavers-Rudolph | Debie.beavers-rudolph@isp.idaho.gov |  | PR-050-040 | 2022-02-22 | 10-11AM
4 | Review Punchout PO | Refer to Upload template | 11927 | Buyer | Review requisitions & create purchase orders. Conduct market research & monitor vendor commitments. Approve vendor returns. | Assigned Agency | Randy Byrne | randy.byrne@isp.idaho.gov | This will be a review of schedule job creating PO. Other variations would be manual creation, or Job run creation submitted as needed. | PR-050-040 | 2022-02-22 | 1-1:30PM
5 | Review Punchout Receipt | Refer to Upload template | 11928 | Receiver | Receive and inspect incoming goods. Pick items for shipment/transfer. Dispose of items. Vendor returns. Document variances. | Assigned Agency | Stephen Srodawa | stephen.srodawa@isp.idaho.gov | Manual release of receipt vs. auto release | PR-050-070 | 2022-02-22 | 1:30-2PM
6 | Review Punchout Invoice | 11610 | 11922 | Payables Invoice Processor | Processes interface and XM files. Match Payables invoices. Manages vendor list. Processes Payables payments. Generates 1099. | Assigned Agency | Joshua Rigenhagen | joshua.rigenhagen@isp.idaho.gov |  | MF-070-050 Enter a PO Invoice | 2022-02-22 | 2-2:30PM
7 | Approve Invoice | 11611 | 11923 | Approver |  |  | Lvl 1 Vanessa Wendland Lvl 2 Ken Suchy | Vanessa.Wendland@isp.idaho.gov ken.suchy@isp.idaho.gov |  | MF-070-056 Invoice Approval Process | 2022-02-22 | 2:30-3PM
8 | Match Invoice | 11613 | 11926 | Payables Manager | Void & cancel payments, reissue & mail warrants. Process period close. | Assigned Agency | Vanessa Wendland | Vanessa.Wendland@isp.idaho.gov |  | MF-070-070 Match Invoices | 2022-02-22 | 3-3:30PM
9 | Process Invoice for Payment | 11442 | 11921 | Payables Manager | Void & cancel payments, reissue & mail warrants. Process period close. | Assigned Agency | Vanessa Wendland | Vanessa.Wendland@isp.idaho.gov |  | MF-070-100 Process Invoice Payments | 2022-02-22 | 3:30 - 4 PM
Note on J5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard

## Custodial Accounts
SIT 3 Scenario - Budget Reporting and Trust Accounting
Agency:
SIT 3 Week - Week 9 - 2/28 - 3/4
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Set up Custodial Accounts |  | TBD | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate, and update allocations. | Assigned Agency | RaeLynn North | raelynn.north@isp.idaho.gov | Associate with project | PR-050-070 | 2022-02-28 | 8:45-9:30 AM
2 | Enter cash receipt for the Custodial Account |  | TBD | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Ishaq Kayed | ishaq.kayed@isp.idaho.gov | Deny Requisition - add note - need more information Approve Requisition | MF-260-070 Enter Cash Receipts | 2022-02-28 | 9:30-10AM
2 | Approve Cash Receipt |  | TBD | Cash Manager | Manage all cash transactions. Review and update cash management policy as needed. | Assigned Agency | Vanessa Wendland | vanessa.wendland@isp.idaho.gov |  | MF-260-070 Enter Cash Receipts | 2022-02-28 | 10-11AM
3 | Final Approval of Cash Receipt |  | TBD | Cash Manager | Manage all cash transactions. Review and update cash management policy as needed. | STO | Vanessa Wendland | vanessa.wendland@isp.idaho.gov |  | MF-260-070 Enter Cash Receipts | 2022-02-28 | 1-1:30PM
4 | Journalize Cash Management |  | TBD | Cash Manager | Manage all cash transactions. Review and update cash management policy as needed. | Assigned Agency | Vanessa Wendland | vanessa.wendland@isp.idaho.gov |  | MF-260-090 Post to General Ledger | 2022-02-28 | 1:30-2PM
5 | View Trust Balance report in Birst |  | TBD | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate, and update allocations. | Assigned Agency | RaeLynn North | raelynn.north@isp.idaho.gov |  |  | 2022-02-28 | 2-2:30PM
6 | Enter Invoice for trust account | 11443 | TBD | Payables Invoice Processor | Process interface and XM files. Match payables invoices, and vendor list. Process payables payments. Generate 1099. | Assigned Agency | Joshua Rigenhagen | joshua.rigenhagen@isp.idaho.gov |  | MF-070-060 Enter a Non-PO invoice | 2022-02-28 | 2:30-3PM
7 | Enter Comments & Attachments | 11445 | TBD | Payables Invoice Processor |  |  | Joshua Rigenhagen | joshua.rigenhagen@isp.idaho.gov |  | MF-070-060 Enter a Non-PO invoice | 2022-02-28 | 3-3:30PM
8 | Approve invoice | 11444 | TBD | Approver | Approve transactions such as requisitions, purchase orders, solicitations, and journal entries. | Assigned Agency | Lvl 1 Vanessa Wendland Lvl 2 Ken Suchy | Vanessa.Wendland@isp.idaho.gov ken.suchy@isp.idaho.gov |  | MF-070-080 Invoice Approval Process | 2022-03-02 | 8:45-9:30 AM
9 | Run Cash Requirements | 11442 | TBD | Payables Manager | Void & cancel payments. Reissue & mail warrants. Process period close. | Assigned Agency | Vanessa Wendland | vanessa.wendland@isp.idaho.gov |  | MF-070-100 Process Invoice Payments | 2022-03-02 | 9:30-10AM
10 | Journalize Payables | 11440 | TBD | Payables Manager | Void & cancel payments. Reissue & mail warrants. Process period close. | Assigned Agency | Vanessa Wendland | vanessa.wendland@isp.idaho.gov |  | MF-070-110 Journalize Distributions | 2022-03-02 | 10-11AM
11 | View Trust Balance Report in Birst |  | TBD | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate, and update allocations. | Assigned Agency | RaeLynn North | raelynn.north@isp.idaho.gov | Receive less/more than ordered |  | 2022-03-02 | 1-1:30PM
12 | Run Average Daily Balance Report |  | TBD | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate, and update allocations. | Assigned Agency | RaeLynn North | raelynn.north@isp.idaho.gov | Inspection Failed, Vendor Return |  | 2022-03-02 | 1:30-2PM
Note on J5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard

## Chart of Accounts Maintenance
SIT 3 Scenario - Chart of Accounts Maintenance
Agency:
SIT Week - Week 10 - 3/7 - 3/11
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | View and Validate an Organizational Unit |  | TBD | Staff Accountant |  |  | RaeLynn North | raelynn.north@isp.idaho.gov |  |  | 2022-03-07 | 8:45-9:30 AM
2 | View and Validate a Project |  | TBD | Staff Accountant |  |  | RaeLynn North | raelynn.north@isp.idaho.gov |  |  | 2022-03-07 | 9:30-10AM
3 | View and Validate a Program |  | TBD | Staff Accountant |  |  | RaeLynn North | raelynn.north@isp.idaho.gov |  |  | 2022-03-07 | 10-11AM
4 | View and Validate a Location |  | TBD | Staff Accountant |  |  | RaeLynn North | raelynn.north@isp.idaho.gov |  |  | 2022-03-07 | 1-1:30PM
5 | View and Validate Additional Reporting |  | TBD | Staff Accountant |  |  | RaeLynn North | raelynn.north@isp.idaho.gov |  |  | 2022-03-07 | 1:30-2PM
6 | View and Validate Custodial Accounts (CAM) |  | TBD | Staff Accountant |  |  | RaeLynn North | raelynn.north@isp.idaho.gov |  |  | 2022-03-07 | 2-2:30PM
7 | Request a new account |  | TBD | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | RaeLynn North | raelynn.north@isp.idaho.gov |  |  | 2022-03-07 | 2:30-3PM
8 | Request a new organizational unit |  | TBD | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | RaeLynn North | raelynn.north@isp.idaho.gov |  |  | 2022-03-07 | 3-3:30PM
9 | View and Validate Beginning Balances |  | TBD | Staff Accountant |  |  | RaeLynn North | raelynn.north@isp.idaho.gov |  |  | 2022-03-08 | 8:45-9:30 AM
10 | Update Summary Conversion Balances to Detail |  | TBD | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. |  | RaeLynn North | raelynn.north@isp.idaho.gov |  |  | 2022-03-08 | 9:30-10AM
Note on J5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard