## SIT 3 Listing & Schedule
SIT 3 End to End Scenarios | SIT 3 Scheduled Week | 352 - Tax Commission
Inventory Management Cycle | Week 4: 1/24 - 1/28
Pcard End to End Process | Week 4: 1/24 - 1/28 | X
Project Processing (RQ, PO, Contract, INV) | Week 4: 1/24 - 1/28
XM Pcard NO Cash Advance | Week 4: 1/24 - 1/28 | X
XM Pcard WITH Cash Advance | Week 4: 1/24 - 1/28 | X
Payroll End to End | Week 4: 1/24 - 1/28
Fixed Asset Acquire to Retire | Week 5: 1/31 - 2/4
Statewide Contract Procure to Pay | Week 5: 1/31 - 2/4 | X
GHR Shell | Week 5: 1/31 - 2/4
Project 1.1 Project Setup and Maintanance | Week 5: 1/31 - 2/4
Project 1.2 Project Processing Master (P&G only) | Week 5: 1/31 - 2/4
AR Credit Monitoring | Week 6: 2/7 - 2/11
Asset Management Maintenance | Week 6: 2/7 - 2/11
Service Contract Interagency Billing | Week 6: 2/7 - 2/11
Project 1.3 Reports and Inquiry Master | Week 6: 2/7 - 2/11 & Week 7: 2/14 - 2/18
Cash Ledger Payment | Week 7: 2/14 - 2/18 | X
Interagency Billing to Settlement | Week 7: 2/14 - 2/18
Non-State Billing | Week 7: 2/14 - 2/18
Procure to Pay Vendor Management Voids | Week 7: 2/14 - 2/18 | X
Vendor Refunds | Week 7: 2/14 - 2/18
Cash Management Deposit to Revenue | Week 8: 2/21 - 2/25 | X
Custodial Accounts Setup | Week 8: 2/21 - 2/25 | X
Global Ledger Entries and Analysis | Week 8: 2/21 - 2/25 | X
Punchout Request to Payment | Week 8: 2/21 - 2/25 | X
Tax Refunds | Week 8: 2/21 - 2/25 | X
Allocations | Week 9: 2/28 - 3/4
Budget | Week 9: 2/28 - 3/4
Custodial Accounts Transaction Processing | Week 9: 2/28 - 3/4 | X
Month End/Year End | Week 9: 2/28 - 3/4
Define and Generate Recurring Invoices | Week 9: 2/28 - 3/4
Chart of Accounts Maintenance | Week 10: 3/7 - 3/11 | X
3rd Party Allocations | TBD

## Instructions
Luma System Integration Testing 3 (SIT 3) Instructions
Agency Functional Testing Dates | January 24 - March 11, 2022 Testing Schedule: Monday -Thursday 8:45 -11 am and 1:45 - 4:00 pm, Friday 9:00 - 11:00 am
Agency Testers Roles and Responsibilities | 1. Execute test scripts per SIT 3 schedule. 2. Review actual results against expected results. 3. Log defects as needed. 4. Retest failed test results to resolve defects. 5. Launch integrations during test cycle per schedule.
Testing Packet | 1. Test Scenario Excel File: Cover Page, Instruction Tab, Scenario Listing, Tab with each steps script detailed instruction to execute the script. 2. Data Sheets. 3. Email Template to use to report your testing results.
Testing Steps | 1. If you are the first step in the scenario, you may begin execution according to the the Date and Time in the Testing packet. If you are not on step 1, please wait for the step before you to complete their script and you receive communication to begin. 2. Execute assigned script(s) using the testing script and data sheet that was provided to you. 3. Sending Testing results via email using to the Test Management Team. (attached email sample) 4. Communicate to the next tester they can begin their script. (Slack or Email works)
What should you do if there are issues or you need assistance while testing? | 1. The Test Management Team will host an all-day SIT 3 Testing Support Hotline (WebEx Meeting). 2. Attendance is optional for SIT testers and testers should only join if they have questions or issues regarding SIT testing. 3. Testers should have an invite on their calendar that includes the WebEx Link.
How to submit a SIT 3 Testing Defect using ServiceNow: | 1. Visit https://auth.sco.idaho.gov/ in your web browser. Google Chrome and Microsoft Edge are recommended. 2. Enter your State ID number as the username and your password. Click the Sign In button. 3. You will be presented with a second page for Multi-Factor Authentication. Select an option and acknowledge the push or call, or enter a passcode from your Duo app. 4. You will see several buttons on your Enterprise Dashboard. One of these will be labeled Service Desk. This button will take you to the Service Portal. 5. There are four main buttons across the center of the page. Click Service Requests to be taken to the service menu. 7. Locate and select LUMA SIT3 Testing Issue from the options listed. 6. Select the SCO IT Services category from the list on the left side of the page. 7. Fill out form with Primary Contact, Short Description, Description, Category, Scenario Name, Script ID, add attachments/screenshots and submit the ticket.
What to do if there is a system outage? | 1. Please join the Testing Support Hotline if you run into any issues with the system and notify the meeting moderator of the issue. 2. If there is a system outage, the Test Management Team will work with the Communications team to notify Agency Testers.

## Email Submission Template
Click on Icon Below to Outlook Email Template

## PCard End to End
SIT 3 Scenario Pcard End to End Process
Agency:
SIT Week - Week 4 - 1/24 - 1/28
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Set up new Users | 11486 | 11913 | Pcard Administrator |  | Assigned Agency | Caryn Hirschi | Caryn.Hirschi@tax.idaho.gov |  | PR-050-130: Obtaining a Purchase Card | 2022-01-24 | 8:45-9:30 AM
2 | Set up new Card Numbers | 11644 | 11916 | Pcard Administrator |  | Assigned Agency | Caryn Hirschi | Caryn.Hirschi@tax.idaho.gov |  | PR-050-130: Obtaining a Purchase Card | 2022-01-24 | 9:30-10AM
3 | Link User to Card Number | 11645 | 11918 | Pcard Administrator |  | Assigned Agency | Caryn Hirschi | Caryn.Hirschi@tax.idaho.gov |  | PR-050-130: Obtaining a Purchase Card | 2022-01-24 | 10-11AM
4 | Request for a Pcard | 11646 | 11917 | Pcard Approver | A state employee authorized to approve goods & services purchased with a pcard. | Assigned Agency | Lisa Kopke | lisa.kopke@tax.idaho.gov |  | PR-050-130: Obtaining a Purchase Card | 2022-01-24 | 1-1:30PM
5 | Approve Pcard Request | 11485 | 11912 | Pcard Administrator |  | Assigned Agency | Caryn Hirschi | Caryn.Hirschi@tax.idaho.gov |  | PR-050-130: Obtaining a Purchase Card | 2022-01-24 | 1:30-2PM
6 | Assumption: Card is used and transactions are interfaced into Luma Pcard module | Statements must be manually created for each agency |  | Pcard Administrator |  | SCO | Caryn Hirschi | Caryn.Hirschi@tax.idaho.gov |  | PR-050-140: Purchasing With Purchase Card | 2022-01-24 | 2-2:30PM
7 | Approving Transactions | 11484 | 11911 | Pcard Approver | A state employee authorized to approve goods & services purchased with a pcard. | Assigned Agency | Lisa Kopke | lisa.kopke@tax.idaho.gov | Add a Project to distribution | PR-050-140: Purchasing With Purchase Card | 2022-01-25 | 8:45 - 10:30AM
8 | Review Pcard charges | 11652 | 11914 | Pcard Approver | A state employee authorized to approve goods & services purchased with a pcard. | Assigned Agency | Lisa Kopke | lisa.kopke@tax.idaho.gov |  | PR-050-140: Purchasing With Purchase Card | 2022-01-25 | 8:45 - 10:30AM
9 | Review Pcard Invoice | 11653 | 11915 | Payables Manager | Void & cancel payments, reissue & mail warrants. Process period close. | Assigned Agency | Lisa Kopke | lisa.kopke@tax.idaho.gov |  | PR-050-140: Purchasing With Purchase Card | 2022-01-25 | 10:30-11AM
10 | Pay Pcard Invoice | 11365 | 11920 | Payables Manager | Void & cancel payments, reissue & mail warrants. Process period close. | Assigned Agency | Lisa Kopke | lisa.kopke@tax.idaho.gov |  | PR-050-140: Purchasing With Purchase Card | 2022-01-25 | 10:30-11AM
11 | Journalize Entries | 11364 | 11919 | Payables Manager | Void & cancel payments, reissue & mail warrants. Process period close. | Assigned Agency | Lisa Kopke | lisa.kopke@tax.idaho.gov |  | PR-050-140: Purchasing With Purchase Card | 2022-01-25 | 10:30-11AM
12 | Deactivate User | 11463 | 11910 | Pcard Administrator |  | Assigned Agency | Caryn Hirschi | Caryn.Hirschi@tax.idaho.gov |  | PR-050-130: Obtaining a Purchase Card | 2022-01-25 | 1 - 1:30 PM

## XM Pcard No Cash Advance
SIT 3 Scenario Expense Management (XM) using Pcard
Agency:
SIT Week - Week 4 - 1/24 - 1/28
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Create & submit Travel Plan | 11470 | 11953 | XM Consumer | Request travel approval. Submit documentation for reimbursement. | Assigned Agency | Toni Nash OR Caryn Hirschi | toni.nash@tax.idaho.gov Caryn.Hirschi@tax.idaho.gov | Add a Project to distribution | MF-075-100: Process Expense Reports | 2022-01-24 | 8:45-9:30 AM
2 | Review & approve Travel Plan | 11473 | 11957 | XM Approver | A state employee authorized to approve travel related expenses. | Assigned Agency | Lisa Kopke | lisa.kopke@tax.idaho.gov |  | MF-075-100: Process Expense Reports | 2022-01-24 | 9:30-10AM
3 | Create & submit Expense Report | 11471 | 11956 | XM Consumer | Request travel approval. Submit documentation for reimbursement. | Assigned Agency | Toni Nash OR Caryn Hirschi | toni.nash@tax.idaho.gov Caryn.Hirschi@tax.idaho.gov | Add a Project to distribution | MF-075-100: Process Expense Reports | 2022-01-24 | 10-11AM
4 | Review & approve Expense Report | 11474 | 11960 | XM Approver | A state employee authorized to approve travel related expenses. | Assigned Agency | Lisa Kopke | lisa.kopke@tax.idaho.gov |  | MF-075-100: Process Expense Reports | 2022-01-24 | 1-1:30PM
5 | Interface from XM to Luma AP (automatic on schedule) | No Test ID - interface process |  | Payables Manager |  | SCO | Lisa Kopke | lisa.kopke@tax.idaho.gov |  |  | 2022-01-24 | 1:30-2PM
6 | Pcard transactions arrives on interface IFS004 (manual upload) | No Test ID - interface process |  | PCARD Administration |  | SCO | Caryn Hirschi | Caryn.Hirschi@tax.idaho.gov |  |  | 2022-01-24 | 2-2:30PM
7 | Approve Pcard charges | 11484 | 11954 | Cardholder | A state employee authorized to purchase goods and services with pcard. | Assigned Agency | Toni Nash | toni.nash@tax.idaho.gov |  | PR-050-140: Purchasing with Pcard | 2022-01-25 | 8:45-9:30 AM
8 | Close Pcard charges | 11484 | 11961 | PCARD Approver | A state employee authorized to approve goods & services purchased with a pcard. | Assigned Agency | Lisa Kopke | lisa.kopke@tax.idaho.gov |  | PR-050-140: Purchasing with Pcard | 2022-01-25 | 9:30-10AM
9 | Review Pcard invoice for payment | 11653 | 11955 | Payables Manager | Void & cancel payments, reissue & mail warrants. Process period close. | Assigned Agency | Lisa Kopke | lisa.kopke@tax.idaho.gov |  | MF-070-100: Process Invoice Payments | 2022-01-25 | 10-11AM
10 | Run Cash Requirements | 11365 | 11959 | Payables Manager | Void & cancel payments, reissue & mail warrants. Process period close. | Assigned Agency | Lisa Kopke | lisa.kopke@tax.idaho.gov |  | MF-070-100: Process Invoice Payments | 2022-01-25 | 1-1:30PM
11 | Journalize the transactions | 11364 | 11958 | Payables Manager | Void & cancel payments, reissue & mail warrants. Process period close. | Assigned Agency | Lisa Kopke | lisa.kopke@tax.idaho.gov |  | MF-070-100: Process Invoice Payments | 2022-01-25 | 1:30-2PM

## XM Pcard With Cash Advance
SIT 3 Scenario Expense Management (XM) using Pcard
Agency:
SIT Week - Week 4 - 1/24 - 1/28
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Create & submit Travel Plan | 11634 | 11962 | XM Consumer | Request travel approval. Submit documentation for reimbursement. | Assigned Agency | Toni Nash OR Caryn Hirschi | toni.nash@tax.idaho.gov Caryn.Hirschi@tax.idaho.gov | Add a Project to distribution | Process Expense Reports MF-075-100 | 2022-01-26 | 8:45-9:30 AM
2 | Review & approve Travel Plan | 11637 | 11966 | XM Approver | A state employee authorized to approve travel related expenses. | Assigned Agency | Lisa Kopke | lisa.kopke@tax.idaho.gov |  | Process Expense Reports MF-075-100 | 2022-01-26 | 9:30-10AM
3 | Create a Cash Advance request | 11641 | 11973 | XM Consumer | Request travel approval. Submit documentation for reimbursement. | Assigned Agency | Toni Nash OR Caryn Hirschi | toni.nash@tax.idaho.gov Caryn.Hirschi@tax.idaho.gov | Add a Project to distribution | Process Expense Reports MF-075-100 | 2022-01-26 | 10-11AM
4 | Approve a Cash Advance | 11642 | 11974 | XM Approver | A state employee authorized to approve travel related expenses. | Assigned Agency | Lisa Kopke | lisa.kopke@tax.idaho.gov |  | Process Expense Reports MF-075-100 | 2022-01-26 | 1-1:30PM
5 | Process the Cash Advance in AP | 11642 | 11976 | Payables Manager | Void & cancel payments, reissue & mail warrants. Process period close. | Assigned Agency | Lisa Kopke | lisa.kopke@tax.idaho.gov |  | Process Expense Reports MF-075-100 | 2022-01-26 | 1:30-2PM
6 | Run Cash Requirements | 11442 | 11972 | Payables Manager | Void & cancel payments, reissue & mail warrants. Process period close. | Assigned Agency | Lisa Kopke | lisa.kopke@tax.idaho.gov |  | MF-070-100 Process Invoice Payments | 2022-01-26 | 2-2:30PM
7 | Journalize the transactions | 11440 | 11971 | Payables Manager | Void & cancel payments, reissue & mail warrants. Process period close. | Assigned Agency | Lisa Kopke | lisa.kopke@tax.idaho.gov |  | MF-070-100 Process Invoice Payments | 2022-01-26 | 2:30 - 3 PM
8 | Create & submit Expense Report | 11635 | 11965 | XM Consumer | Request travel approval. Submit documentation for reimbursement. | Assigned Agency | Toni Nash OR Caryn Hirschi | toni.nash@tax.idaho.gov Caryn.Hirschi@tax.idaho.gov | Add a Project to distribution | Process Expense Reports MF-075-100 | 2022-01-26 | 3 - 3:30 PM
9 | Reconcile Cash Adv with Exp Report | 11643 | 11975 | XM Consumer | Request travel approval. Submit documentation for reimbursement. | Assigned Agency | Toni Nash OR Caryn Hirschi | toni.nash@tax.idaho.gov Caryn.Hirschi@tax.idaho.gov |  | Process Expense Reports MF-075-100 | 2022-01-26 | 3:30 - 4 PM
10 | Review & approve Expense Report | 11638 | 11969 | XM Approver | A state employee authorized to approve travel related expenses. | Assigned Agency | Lisa Kopke | lisa.kopke@tax.idaho.gov |  | Process Expense Reports MF-075-100 | 2022-01-26 | 4 -4:30 PM
11 | Interface from XM to Luma AP (automatic on schedule) | No Test ID - interface process |  | Payables Manager |  | SCO | Lisa Kopke | lisa.kopke@tax.idaho.gov |  |  | 2022-01-26 | Runs on automated schedule
12 | Pcard transactions arrives on interface IFS004 (manual upload) | No Test ID - interface process |  | PCARD Administration |  | SCO | Caryn Hirschi | Caryn.Hirschi@tax.idaho.gov |  |  | 2022-01-26 | 4:30 - 5 PM
13 | Approve Pcard charges | 11484 | 11963 | Cardholder | A state employee authorized to purchase goods and services with pcard. | Assigned Agency | Toni Nash | toni.nash@tax.idaho.gov |  | Purchasing with Pcard PR-050-140 | 2022-01-27 | 8:45-9:30 AM
14 | Close Pcard charges | 11484 | 11970 | PCARD Approver | A state employee authorized to approve goods & services purchased with a pcard. | Assigned Agency | Lisa Kopke | lisa.kopke@tax.idaho.gov |  | Purchasing with Pcard PR-050-140 | 2022-01-27 | 9:30-10AM
15 | Review Pcard invoice | 11653 | 11964 | Payables Manager | Void & cancel payments, reissue & mail warrants. Process period close. | Assigned Agency | Lisa Kopke | lisa.kopke@tax.idaho.gov |  | MF-070-100 Process Invoice Payments | 2022-01-27 | 10-11AM
16 | Run Cash Requirements | 11442 | 11968 | Payables Manager | Void & cancel payments, reissue & mail warrants. Process period close. | Assigned Agency | Lisa Kopke | lisa.kopke@tax.idaho.gov |  | MF-070-100 Process Invoice Payments | 2022-01-27 | 1-1:30PM
17 | Journalize the transactions | 11440 | 11967 | Payables Manager | Void & cancel payments, reissue & mail warrants. Process period close. | Assigned Agency | Lisa Kopke | lisa.kopke@tax.idaho.gov |  | MF-070-100 Process Invoice Payments | 2022-01-27 | 1:30-2PM

## Statewide Contract Procure to P
SIT 3 Scenario - Statewide Contract Procure to Pay
Agency:
SIT 3 Week - Week 5 - 1/31-2/4
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Create Contract with Rebate and Price Breaks Statewide for Envelopes - Create a Contract (Contract Tab) | 7219 | 11992 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-020 | 2022-01-31 | 8:45 - 11 AM
2 | Create Contract with Rebate and Price Breaks Statewide for Envelopes - Contract Draft (Articles) | 7204 | 11987 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-020 | 2022-01-31 | 8:45 - 11 AM
3 | Create Contract with Rebate and Price Breaks Statewide for Envelopes - Contract Draft - Participants | 2667 | 11997 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-020 | 2022-01-31 | 8:45 - 11 AM
4 | Create Contract with Rebate and Price Breaks Statewide for Envelopes - Contract Draft - Lines - Special | 8909 | 11995 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-020 | 2022-01-31 | 8:45 - 11 AM
5 | Create Contract with Rebate and Price Breaks Statewide for Envelopes - Contract Draft - Lines - Purchase Type Detail - Purchase Pricing | 2663 | 11996 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-020 | 2022-01-31 | 8:45 - 11 AM
6 | Create Contract with Rebate and Price Breaks Statewide for Envelopes - Contract Draft - Rebates | 2671 | 11998 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-020 | 2022-01-31 | 8:45 - 11 AM
7 | Create Contract with Rebate and Price Breaks Statewide for Envelopes - Contract Draft - Contacts | 3335 | 11993 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-020 | 2022-01-31 | 8:45 - 11 AM
8 | Create Contract with Rebate and Price Breaks Statewide for Envelopes - Releasing a Contract | 7203 | 11985 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-020 | 2022-01-31 | 8:45 - 11 AM
9 | Contract Approval | 8353 | 11979 | Approver | Compile contract file including entering contract line item details, terms & conditions along with pricing. | DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-020 | 2022-01-31 | 8:45 - 11 AM
10 | Create Contract with Rebate and Price Breaks Statewide for Envelopes - Activating a Contract | 7202 | 11978 | Contract Manager | Approve transactions such as requisitions, purchase orders, solicitation & journal entries. | DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-020 | 2022-01-31 | 1 - 1:30 PM
11 | Requisition - RSS | 8325 | 11988 | Requester | Determines requirements & cost estimates for purchase of goods & services. Submits purchase requisition. | Assigned Agency | Toni Nash | toni.nash@tax.idaho.gov | distribution to multiple org unit and agencies | PR-020-010 | 2022-01-31 | 1:30 - 2:30 PM
12 | Approve Requisition | 8539 | 11984 | Approver | Approve transactions such as requisitions, purchase orders, solicitation & journal entries. | Assigned Agency | (1st approver) Valerie Clark (2nd approver) Kevin Voss | valerie.clark@tax.idaho.gov kevin.voss@tax.idaho.gov |  | PR-020-010 | 2022-01-31 | 2:30 - 3 PM
13 | Create PO from Requisition | 8327 | 11991 | Buyer | Review requisitions & create purchase orders. Conduct market research & monitor vendor commitments. Approve vendor returns. | Assigned Agency | Kevin Voss | kevin.voss@tax.idaho.gov |  | PR-050-040 | 2022-02-01 | 8:45-9:30 AM
14 | Receive Purchase Order | 3064 | 11977 | Receiver | Receive and inspect incoming goods. Pick items for shipment/transfer. Dispose of items. Vendor returns. Document variances. | Assigned Agency | Valerie Clark | valerie.clark@tax.idaho.gov |  | PR-050-070 | 2022-02-01 | 9:30-10AM
15 | Create Invoice | 11606 | 11983 | Payables Invoice Processor | Process interface and XM files. Match payables invoices, and vendor list. Process payables payments. Generate 1099. | Assigned Agency | Caryn Hirschi | Caryn.Hirschi@tax.idaho.gov |  | MF-070-050 Enter a PO Invoice | 2022-02-01 | 10-11AM
16 | Notify Buyer of Discrepancy | 11605 | 11982 | Payables Invoice Processor | Process interface and XM files. Match payables invoices, and vendor list. Process payables payments. Generate 1099. |  | Caryn Hirschi | Caryn.Hirschi@tax.idaho.gov |  | MF-070-050 Enter a PO Invoice | 2022-02-01 | 1-1:30PM
17 | Resolve Cost Discrepancy | New | 12004 | Buyer | Review requisition and create purchase orders. Conduct market research, and monitor vendor commitments. Approve vendor returns. | Assigned Agency | Kevin Voss | kevin.voss@tax.idaho.gov |  |  | 2022-02-01 | 1:30-2PM
18 | Submit Resolved Invoice for Approval | 11607 | 11989 | Payables Invoice Processor | Process interface and XM files. Match payables invoices, and vendor list. Process payables payments. Generate 1099. |  | Caryn Hirschi | Caryn.Hirschi@tax.idaho.gov |  | MF-070-050 Enter a PO Invoice | 2022-02-01 | 2-2:30PM
19 | Approve Invoice | 11608 | 11990 | Approver | Approve transactions such as requisitions, purchase orders, solicitations, and journal entries. | Assigned Agency | (1st approver) Caryn Hirschi (2nd approver) Lisa Kopke | Caryn.Hirschi@tax.idaho.gov lisa.kopke@tax.idaho.gov |  | MF-070-056 Invoice Approval Process | 2022-02-01 | 2:30-3PM
20 | Match Invoice | 11609 | 11994 | Payables Manager | Void & cancel payments. Reissue & mail warrants. Process period close. | Assigned Agency | Lisa Kopke | lisa.kopke@tax.idaho.gov |  | MF-070-070 Match Invoices | 2022-02-01 | 3-3:30PM
21 | Process Payment for Invoice | 11442 | 11981 | Payables Manager | Void & cancel payments. Reissue & mail warrants. Process period close. | Assigned Agency | Lisa Kopke | lisa.kopke@tax.idaho.gov |  | MF-070-100 Process Invoice Payments | 2022-02-01 | 3-3:30PM
22 | Journalize | 11440 | 11980 | Payables Manager | Void & cancel payments. Reissue & mail warrants. Process period close. |  | Lisa Kopke | lisa.kopke@tax.idaho.gov |  | MF-070-110 Journalize AP Distributions | 2022-02-01 | 3-3:30PM
23 | Renew/Addendum Statewide Contract | 2773 | 11986 | Contract Manager | Compile contract file, including entering contract line-item details, terms & conditions, and pricing, and amends and renews contracts. | DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-050-010 | 2022-02-02 | 8:45-9:30 AM
24 | Load Rebate Invoices | New | 11999 | Supply Management Admin or Processor |  | Assigned Agency |  |  |  | PR-050-010 | 2022-02-02 | 9:30-10AM
25 | Calculate Rebate Amounts Due for a Contract | New | 12000 | Supply Management Admin or Processor | [5 empty] | PR-050-010 | 2022-02-02 | 10-11AM
26 | Review Rebate Due Information | New | 12001 | Contract Manager | Compile contract file, including entering contract line-item details, terms & conditions, and pricing, and amends and renews contracts. | Assigned Agency | DOP Tester | contractadmin@adm.idaho.gov |  | PR-050-010 | 2022-02-02 | 1-1:30PM
27 | Apply Rebate (Enter a Rebate Invoice in Payables | New | 12002 | Payables Manager | Void & cancel payments. Reissue & mail warrants. Process period close. |  | Lynn Christian | lynn.christian@adm.idaho.gov | There isn't an invoice type of Rebate Invoice???? | MF-260-070ZZ | 2022-02-03 | 8:45-9:30 AM
28 | Review Rebate Information | New | 12003 | Contract Manager | Compile contract file, including entering contract line-item details, terms & conditions, and pricing, and amends and renews contracts. |  | DOP Tester | contractadmin@adm.idaho.gov |  | PR-050-010 | 2022-02-03 | 9:30-10AM
29 | Verify Rebates posted in Cash Account |  |  | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Genny Casiano | genny.casiano@adm.idaho.gov |  | MF-260-070ZZ | 2022-02-03 | 10-11 AM

## Cash Ledger Payment
SIT 3 Scenario - Cash Ledger Payment
Agency:
SIT Week - Week 7 - 2/14 -2/18
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Enter Cash Payment | Cash Payment Entry.xlsx | 12075 | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Adriana Linares OR Craig Allison OR Ryan Aschraft OR Renee Marsh | adriana.linares@tax.idaho.gov Craig.allison@tax.idaho.gov ryan.ashcraft@tax.idaho.gov Renee.Marsh@tax.idaho.gov | Rotary/Site Draft, L Warrants |  | 2022-02-14 | 8:45 - 10 AM
1A | Record Cash Payment |  | 12525 | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Adriana Linares OR Craig Allison OR Ryan Aschraft OR Renee Marsh | adriana.linares@tax.idaho.gov Craig.allison@tax.idaho.gov ryan.ashcraft@tax.idaho.gov Renee.Marsh@tax.idaho.gov |  |  | 2022-02-14 | 8:45 - 10 AM
2 | Approve Cash Payment | Cash Approve Cash Payment.xlsx | 12076 | Cash Manager | Manage all cash transactions. Review and update cash management policy as needed. | Assigned Agency | Craig Allison OR Adriana Linares OR Lisa Kopke | Craig.allison@tax.idaho.gov adriana.linares@tax.idaho.gov lisa.kopke@tax.idaho.gov |  |  | 2022-02-14 | 10 - 11:30 AM
3 | Cash Requirements | Cash Requirements.xlsx | 12077 | Payables Payment Processor | Perform Cash Requirements, Schedule Payments, Complete Payment Cycle | Assigned Agency | Ryan Ashcraft OR Renee Marsh OR Caryn Hirschi OR Craig Allison | ryan.ashcraft@tax.idaho.gov Renee.Marsh@tax.idaho.gov Caryn.Hirschi@tax.idaho.gov Craig.allison@tax.idaho.gov |  | MF-070-100 Process Invoice Payments | 2022-02-14 | 1 - 2:30 PM
4 | Review Check in Cash | Cash Review Check in Cash Management.xlsx | 12078 | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Adriana Linares OR Craig Allison OR Ryan Aschraft OR Renee Marsh | adriana.linares@tax.idaho.gov Craig.allison@tax.idaho.gov ryan.ashcraft@tax.idaho.gov Renee.Marsh@tax.idaho.gov | Redeem or Void then Review again |  | 2022-02-14 | 2:30 - 4 PM
5 | Journalize Distributions | Cash Journalize Cash Transaction.xlsx | 12079 | Cash Manager | Manage all cash transactions. Review and update cash management policy as needed. | Assigned Agency | Craig Allison OR Adriana Linares OR Lisa Kopke | Craig.allison@tax.idaho.gov adriana.linares@tax.idaho.gov lisa.kopke@tax.idaho.gov |  |  | 2022-02-15 | 8:45 - 10 AM
6 | Verify Results in Global Ledger Account Analysis |  | 12082 | Staff Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Adriana Linares OR Kaia Weiss OR Caryn Hirschi OR Craig Allison | adriana.linares@tax.idaho.gov kaia.weiss@tax.idaho.gov Caryn.Hirschi@tax.idaho.gov Craig.allison@tax.idaho.gov |  |  | 2022-02-15 | 10 - 11:30 AM
7 | Optional Void Cash Payment for Status Updates | Cash Void Cash Payment.xlsx | 12080 | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Adriana Linares OR Craig Allison OR Ryan Aschraft OR Renee Marsh | adriana.linares@tax.idaho.gov Craig.allison@tax.idaho.gov ryan.ashcraft@tax.idaho.gov Renee.Marsh@tax.idaho.gov |  |  | 2022-02-15 | 1 - 2:30 PM
8 | Optional Void Cash Payment: Payment Void Stop Pay Update | 12161 | 12161 | Payables Payment Processor | Perform Cash Requirements, Schedule Payments, Complete Payment Cycle | Assigned Agency | Ryan Ashcraft OR Renee Marsh OR Caryn Hirschi OR Craig Allison | ryan.ashcraft@tax.idaho.gov Renee.Marsh@tax.idaho.gov Caryn.Hirschi@tax.idaho.gov Craig.allison@tax.idaho.gov |  |  | 2022-02-15 | 1 - 2:30 PM
9 | Optional Redeem Warrant for Status Updates | Cash Redeem Warrant.xlsx | 12081 | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Adriana Linares OR Craig Allison OR Ryan Aschraft OR Renee Marsh | adriana.linares@tax.idaho.gov Craig.allison@tax.idaho.gov ryan.ashcraft@tax.idaho.gov Renee.Marsh@tax.idaho.gov |  |  | 2022-02-15 | 2:30 - 4 PM
Note on K5: Glenda Smith: Cash BPR's are not correct, do not reference.

## Procure to Pay Vendor Mgt Voids
SIT 3 Scenario - Procure to Pay with Void and Vendor Update
Agency:
SIT Week - Week 7 - 2/14 -2/18
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | Luma Role (role switcher) | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Create Requisition - Special | 8324 | Requester | Assigned Agency | Toni Nash | toni.nash@tax.idaho.gov |  | PR-020-010 | 2022-02-14 | 8:45-9:30 AM
2 | Approve Requisition | 8539 | Approver | Assigned Agency | (1st approver) Valerie Clark (2nd approver) Kevin Voss | valerie.clark@tax.idaho.gov kevin.voss@tax.idaho.gov | Requisition not approved | PR-010-060 | 2022-02-14 | 9:30-10AM
3 | Create Purchase Order | 8170 | Buyer | Assigned Agency | Kevin Voss | kevin.voss@tax.idaho.gov |  | PR-050-040 | 2022-02-14 | 10-10:30 AM
4 | Receive Purchase Order | 4587 | Receiver | Assigned Agency | Valerie Clark | valerie.clark@tax.idaho.gov |  | PR-050-070 | 2022-02-14 | 10:30 - 11 AM
5 | Create Invoice | 11519 | Payables Invoice Processor | Assigned Agency | Caryn Hirschi | Caryn.Hirschi@tax.idaho.gov |  | MF-070-050 Enter a PO Invoice | 2022-02-14 | 1-1:30PM
6 | Approve Invoice | 11520 | Approver | Assigned Agency | (1st approver) Caryn Hirschi (2nd approver) Lisa Kopke | Caryn.Hirschi@tax.idaho.gov lisa.kopke@tax.idaho.gov |  | MF-070-056 Invoice Approval Process | 2022-02-14 | 1:30-2PM
7 | Match Invoice | 11458 | Payables Manager | Assigned Agency | Kevin Voss | kevin.voss@tax.idaho.gov |  | MF-070-070 Match Invoices | 2022-02-14 | 2-2:30PM
8 | Process Payment for Invoice | 11442 | Payables Manager | Assigned Agency | Kevin Voss | kevin.voss@tax.idaho.gov |  | MF-070-100 Process Invoice Payments | 2022-02-14 | 2:30-3PM
9 | Journalize | 11440 | Payables Manager |  | Kevin Voss | kevin.voss@tax.idaho.gov |  | MF-070-110 Journalize AP Distributions | 2022-02-14 | 3 - 3:30 PM
10 | Void Payment | 12080 | Cash Accountant | SCO | Adriana Linares OR Craig Allison OR Ryan Aschraft OR Renee Marsh | adriana.linares@tax.idaho.gov Craig.allison@tax.idaho.gov ryan.ashcraft@tax.idaho.gov Renee.Marsh@tax.idaho.gov |  | MF-200-060 Void Cash Transactions | 2022-02-14 | 3:30 - 4 PM
11 | Cancel Invoice | 11523 | Payables Manager | Assigned Agency | Lisa Kopke | lisa.kopke@tax.idaho.gov |  | MF-070-050 Enter a PO Invoice | 2022-02-15 | 8:45-9:30 AM
12 | Request a new vendor | 11524 | Payables Invoice Processor | Assigned Agency | Caryn Hirschi | Caryn.Hirschi@tax.idaho.gov |  | PR-040-030 Create and Maintain Vendor | 2022-02-15 | 9:30-10AM
13 | Approve and setup new vendor | 11525 - Only SCO staff can do this | Approver | SCO | (1st approver) Caryn Hirschi (2nd approver) Lisa Kopke | Caryn.Hirschi@tax.idaho.gov lisa.kopke@tax.idaho.gov | Disapprove vendor | PR-040-030 Create and Maintain Vendor | 2022-02-15 | 10-10:30 AM
14 | Create Invoice | 11519 | Payables Invoice Processor | Assigned Agency | Caryn Hirschi | Caryn.Hirschi@tax.idaho.gov |  | MF-070-050 Enter a PO Invoice | 2022-02-15 | 10:30 - 11 AM
15 | Approve Invoice | 11520 | Approver | Assigned Agency | (1st approver) Caryn Hirschi (2nd approver) Lisa Kopke | Caryn.Hirschi@tax.idaho.gov lisa.kopke@tax.idaho.gov |  | MF-070-056 Invoice Approval Process | 2022-02-15 | 1-1:30PM
16 | Match Invoice | 11522 | Payables Invoice Processor | Assigned Agency | Caryn Hirschi | Caryn.Hirschi@tax.idaho.gov |  | MF-070-070 Match Invoices | 2022-02-15 | 1:30-2PM
17 | Process Payment for Invoice | 11442 | Payables Manager | Assigned Agency | Lisa Kopke | lisa.kopke@tax.idaho.gov |  | MF-070-100 Process Invoice Payments | 2022-02-15 | 2-2:30PM
18 | Post Transactions - Journalize | 11440 | Payables Manager | Assigned Agency | Lisa Kopke | lisa.kopke@tax.idaho.gov |  | MF-070-110 Journalize AP Distributions | 2022-02-15 | 2:30-3PM
19 | Cash Ledger Journalize | 12079 | Cash Manager | Assigned Agency | Craig Allison OR Adriana Linares OR Lisa Kopke | Craig.allison@tax.idaho.gov adriana.linares@tax.idaho.gov lisa.kopke@tax.idaho.gov |  | MF-200-050 Reconcile Payments Payables and Disbursements | 2022-02-15 | 3 - 3:30 PM
20 | Verify Voided Payables Checks | 12153 | Cash Accountant | Assigned Agency | Adriana Linares OR Craig Allison OR Ryan Aschraft OR Renee Marsh | adriana.linares@tax.idaho.gov Craig.allison@tax.idaho.gov ryan.ashcraft@tax.idaho.gov Renee.Marsh@tax.idaho.gov |  | MF-200-060 Void Cash Transactions | 2022-02-15 | 3:30 - 4 PM
21 | View Fund Balance | Cash Fund Balance.xlsx (in ALM?)(in Cash Deposit to Revenue Scenario) | Cash Accountant | Assigned Agency | Adriana Linares OR Craig Allison OR Ryan Aschraft OR Renee Marsh | adriana.linares@tax.idaho.gov Craig.allison@tax.idaho.gov ryan.ashcraft@tax.idaho.gov Renee.Marsh@tax.idaho.gov |  | MF-200-050 Reconcile Payments Payables and Disbursements | 2022-02-16 | 8:45-9:30 AM
22 | Comparative report from Birst |  | Cash Accountant | Assigned Agency | Adriana Linares OR Craig Allison OR Ryan Aschraft OR Renee Marsh | adriana.linares@tax.idaho.gov Craig.allison@tax.idaho.gov ryan.ashcraft@tax.idaho.gov Renee.Marsh@tax.idaho.gov |  | MF-200-ZZ | 2022-02-16 | 9:30-10AM
23 | Cash Revenue Daily Report - Birst |  | Cash Manager | Assigned Agency | Craig Allison OR Adriana Linares OR Lisa Kopke | Craig.allison@tax.idaho.gov adriana.linares@tax.idaho.gov lisa.kopke@tax.idaho.gov |  | MF-200-ZZ | 2022-02-16 | 10-10:30 AM

## Cash Managem Deposit to Revenue
SIT 3 Scenario - Deposit to Revenue
Agency:
SIT Week - Week 8 - 2/21/ - 2/25
Sequence | Script ID | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 BPR PROCESSES | Execution date | Window to Complete Script
1 | Cash Fund Balance - Before Processing Transactions | TBD | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Adriana Linares OR Craig Allison OR Ryan Aschraft OR Renee Marsh | adriana.linares@tax.idaho.gov Craig.allison@tax.idaho.gov ryan.ashcraft@tax.idaho.gov Renee.Marsh@tax.idaho.gov |  |  | 2022-02-22 | 8:45-9:30 AM
2 | Create Cash Receipt | TBD | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Adriana Linares OR Craig Allison OR Ryan Aschraft OR Renee Marsh | adriana.linares@tax.idaho.gov Craig.allison@tax.idaho.gov ryan.ashcraft@tax.idaho.gov Renee.Marsh@tax.idaho.gov |  |  | 2022-02-22 | 9:30-10AM
3 | Approve Cash Receipt (Approve Cash Transactions in InBasket) | TBD | Cash Manager | Manage all cash transactions. Review and update cash management policy as needed. | Assigned Agency | Craig Allison OR Adriana Linares OR Lisa Kopke | Craig.allison@tax.idaho.gov adriana.linares@tax.idaho.gov lisa.kopke@tax.idaho.gov |  |  | 2022-02-22 | 10-11AM
4 | Cash Receipt Final Release (Approve Cash Transactions in InBasket) | TBD | Cash Manager | Manage all cash transactions. Review and update cash management policy as needed. | 150 | Craig Allison OR Adriana Linares OR Lisa Kopke | Craig.allison@tax.idaho.gov adriana.linares@tax.idaho.gov lisa.kopke@tax.idaho.gov |  |  | 2022-02-22 | 1-1:30PM
5 | Process NSF | TBD | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Adriana Linares OR Craig Allison OR Ryan Aschraft OR Renee Marsh | adriana.linares@tax.idaho.gov Craig.allison@tax.idaho.gov ryan.ashcraft@tax.idaho.gov Renee.Marsh@tax.idaho.gov |  |  | 2022-02-22 | 1:30-2PM
6 | Approve NSF (Approve Cash Transactions in InBasket) | TBD | Cash Manager | Manage all cash transactions. Review and update cash management policy as needed. | Assigned Agency | Craig Allison OR Adriana Linares OR Lisa Kopke | Craig.allison@tax.idaho.gov adriana.linares@tax.idaho.gov lisa.kopke@tax.idaho.gov |  |  | 2022-02-22 | 2-2:30PM
7 | NSF Final Release (Approve Cash Transactions in InBasket) | TBD | Cash Manager | Manage all cash transactions. Review and update cash management policy as needed. | 150 | Craig Allison OR Adriana Linares OR Lisa Kopke | Craig.allison@tax.idaho.gov adriana.linares@tax.idaho.gov lisa.kopke@tax.idaho.gov |  |  | 2022-02-22 | 2:30-3PM
8 | Reclass From Suspense: No Customer (Cash Receipt Transfer) | TBD | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Adriana Linares OR Craig Allison OR Ryan Aschraft OR Renee Marsh | adriana.linares@tax.idaho.gov Craig.allison@tax.idaho.gov ryan.ashcraft@tax.idaho.gov Renee.Marsh@tax.idaho.gov |  |  | 2022-02-22 | 3-3:30PM
9 | Reclass From Suspense Customer (Go to AR Scenario) | TBD | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency |  |  | Process under development. |  | 2022-02-23 | 8:45-9:30 AM
10 | Operating Transfer (Cash Ledger Transaction Transfer) | TBD | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Adriana Linares OR Craig Allison OR Ryan Aschraft OR Renee Marsh | adriana.linares@tax.idaho.gov Craig.allison@tax.idaho.gov ryan.ashcraft@tax.idaho.gov Renee.Marsh@tax.idaho.gov |  |  | 2022-02-23 | 9:30-10AM
11 | Statutory Transfer (Cash Ledger Transaction Transfer) | TBD | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Adriana Linares OR Craig Allison OR Ryan Aschraft OR Renee Marsh | adriana.linares@tax.idaho.gov Craig.allison@tax.idaho.gov ryan.ashcraft@tax.idaho.gov Renee.Marsh@tax.idaho.gov |  |  | 2022-02-23 | 10-11AM
12 | Approve Cash Transfer (Approve Cash Transactions in InBasket) | TBD | Cash Manager | Manage all cash transactions. Review and update cash management policy as needed. | Assigned Agency | Craig Allison OR Adriana Linares OR Lisa Kopke | Craig.allison@tax.idaho.gov adriana.linares@tax.idaho.gov lisa.kopke@tax.idaho.gov |  |  | 2022-02-23 | 1-1:30PM
13 | Cash Fund Balance - After Processing Transactions | TBD | Cash Manager | Manage all cash transactions. Review and update cash management policy as needed. | Assigned Agency | Craig Allison OR Adriana Linares OR Lisa Kopke | Craig.allison@tax.idaho.gov adriana.linares@tax.idaho.gov lisa.kopke@tax.idaho.gov |  |  | 2022-02-23 | 1:30-2PM
14 | Journalize Cash Transactions | TBD | Cash Manager | Manage all cash transactions. Review and update cash management policy as needed. | Assigned Agency | Craig Allison OR Adriana Linares OR Lisa Kopke | Craig.allison@tax.idaho.gov adriana.linares@tax.idaho.gov lisa.kopke@tax.idaho.gov |  |  | 2022-02-23 | 2-2:30PM
15 | Post GL Journals | TBD | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate, and update allocations. | Assigned Agency | Adriana Linares OR Kaia Weiss OR Caryn Hirschi OR Craig Allison | adriana.linares@tax.idaho.gov kaia.weiss@tax.idaho.gov Caryn.Hirschi@tax.idaho.gov Craig.allison@tax.idaho.gov | Check for autopost |  | 2022-02-23 | 2:30-3PM
16 | Review Global Ledger for Transactions Processed | TBD | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate, and update allocations. | Assigned Agency | Adriana Linares OR Kaia Weiss OR Caryn Hirschi OR Craig Allison | adriana.linares@tax.idaho.gov kaia.weiss@tax.idaho.gov Caryn.Hirschi@tax.idaho.gov Craig.allison@tax.idaho.gov |  |  | 2022-02-23 | 3-3:30PM

## Custodial Account Set Up
SIT 3 Scenario - Custodial Account Set Up
Agency:
SIT Week - Week 8 - 2/21/ - 2/25
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Custodial Account Setup | TBD | 12071 | Custodial Account Manager | Monitor financial structure and Chart of Account dimensions for their Agency and recommendations for updates. Manage all financial processes. | Assigned Agency | Craig Allison | Craig.allison@tax.idaho.gov |  |  | 2022-02-22 | 8:45 - 10AM
2 | CAM Structure Setup | Refer to Upload Template | 12072 | Custodial Account Manager | 0 | Assigned Agency | Craig Allison | Craig.allison@tax.idaho.gov |  |  | 2022-02-22 | 10 - 11:30 AM
3 | Custodial Account Hierarchy Setup | Refer to Upload Template | 12073 | Custodial Account Manager | Monitor financial structure and Chart of Account dimensions for their Agency and recommendations for updates. Manage all financial processes. | Assigned Agency | Craig Allison | Craig.allison@tax.idaho.gov |  |  | 2022-02-22 | 1 - 2:30 PM
4 | Custodial Account Record Setup | Refer to Upload Template | 12074 | Custodial Account Manager | 0 | Assigned Agency | Craig Allison | Craig.allison@tax.idaho.gov |  |  | 2022-02-22 | 2:30 -4 PM

## Global Ledger Entries and Analy
SIT 3 Scenario - Global Legder Processing and Analysis
Agency:
SIT Week - Week 8 - 2/21/ - 2/25
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Create a Front-End Split Journal Entry (Front End Split Projects Only) | Refer to Upload Template | 12154 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency |  |  | May also be performed by CFO or Controller (SCO) | MF-020-010 | 2022-02-23 | 8:45-9:30 AM
2 | Create a Journal Entry | Refer to Upload Template | 11668 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency |  |  | May also be performed by CFO or Controller (SCO) | MF-020-010 | 2022-02-23 | 9:30-10AM
3 | Approve a Journal Entry | Refer to Upload Template | 11669 | Approver | Approve transactions such as requisitions, purchase orders, solicitation & journal entries. | Assigned Agency |  |  |  | MF-025-060 | 2022-02-23 | 10-11AM
4 | Create a Journal Entry from an Existing Journal | Refer to Upload Template | 11671 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency |  |  | May also be performed by CFO or Controller (SCO) | MF-020-010 | 2022-02-23 | 1-1:30PM
5 | Create a Journal Entry from a Template | Refer to Upload Template | 11670 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency |  |  | May also be performed by CFO or Controller (SCO) | MF-020-010 | 2022-02-23 | 1:30-2PM
6 | Create a Recurring Journal | Refer to Upload Template | 11673 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency |  |  | May also be performed by CFO or Controller (SCO) | MF-020-020 | 2022-02-23 | 2-2:30PM
7 | Journalize a Recurring Journal Entry | Refer to Upload Template | 12155 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency |  |  | May also be performed by CFO or Controller (SCO) | MF-020-030 | 2022-02-23 | 2:30-3PM
8 | Post Multiple Journal Entries | Refer to Upload Template | 12156 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency |  |  | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-23 | 3-3:30PM
9 | Post Journals from Subsystems | Refer to Upload Template | 12157 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency |  |  | May also be performed by CFO or Controller (SCO) | MF-020-050 | 2022-02-24 | 8:45-9:30 AM
10 | Validate (here) Reconcile (close) Subsystems to the General Ledger | Bill will put these scripts here and in close scenario | TBD | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency |  |  | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-24 | 9:30-10AM
11 | Analyze Global Ledger Totals | Refer to Upload Template | 12158 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency |  |  | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-24 | 10-11AM
12 | Perform Account Analysis | Refer to Upload Template | 11672 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency |  |  | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-24 | 1-1:30PM
13 | Perform Fund Analysis | Refer to Upload Template | 12159 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency |  |  | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-24 | 1:30-2PM
14 | Perform Organizational Unit Analysis | Refer to Upload Template | 12160 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency |  |  | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-24 | 2-2:30PM
15 | View Transactions by Entity-Account | Refer to Upload Template | 11674 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency |  |  | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-25 | 9- 9:30 AM
16 | BIRST/BI/CSF Analytic Reporting |  | TBD | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency |  |  | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-25 | 9:30 - 10 AM
17 | Evaluate Encumbrances | Placeholder - Judy and Bill (and Eileen/Cathy) are working on script for this; will have this week (12/23/21) | TBD | Staff Accountant |  | Assigned Agency |  |  | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-25 | 10 - 11 AM

## Punchout Request to Payment
SIT 3 Scenario - Punchout Request to Payment
Agency:
SIT Week - Week 8 - 2/21 - 2/25
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Create Punchout Requisition using RSS | 3501 | 11924 | Requester | Determines requirements & cost estimates for purchase of goods & services. Submits purchase requisition. | Assigned Agency |  |  |  | PR-020-010 | 2022-02-22 | 8:45-9:30 AM
2 | Approve Requisition | 8539 | 11925 | Approver | Approve transactions such as requisitions, purchase orders, solicitation & journal entries. | Assigned Agency |  |  | Deny Requisition - add note - need more information Approve Requisition | PR-010-060 | 2022-02-22 | 9:30-10AM
3 | Locate Punchout PO | Refer to Upload template | 12034 | Requester | [5 empty] | PR-050-040 | 2022-02-22 | 10-11AM
4 | Review Punchout PO | Refer to Upload template | 11927 | Buyer | Review requisitions & create purchase orders. Conduct market research & monitor vendor commitments. Approve vendor returns. | Assigned Agency |  |  | This will be a review of schedule job creating PO. Other variations would be manual creation, or Job run creation submitted as needed. | PR-050-040 | 2022-02-22 | 1-1:30PM
5 | Review Punchout Receipt | Refer to Upload template | 11928 | Receiver | Receive and inspect incoming goods. Pick items for shipment/transfer. Dispose of items. Vendor returns. Document variances. | Assigned Agency |  |  | Manual release of receipt vs. auto release | PR-050-070 | 2022-02-22 | 1:30-2PM
6 | Review Punchout Invoice | 11610 | 11922 | Payables Invoice Processor | Processes interface and XM files. Match Payables invoices. Manages vendor list. Processes Payables payments. Generates 1099. | Assigned Agency |  |  |  | MF-070-050 Enter a PO Invoice | 2022-02-22 | 2-2:30PM
7 | Approve Invoice | 11611 | 11923 | Approver | [5 empty] | MF-070-056 Invoice Approval Process | 2022-02-22 | 2:30-3PM
8 | Match Invoice | 11613 | 11926 | Payables Manager | Void & cancel payments, reissue & mail warrants. Process period close. | Assigned Agency |  |  |  | MF-070-070 Match Invoices | 2022-02-22 | 3-3:30PM
9 | Process Invoice for Payment | 11442 | 11921 | Payables Manager | Void & cancel payments, reissue & mail warrants. Process period close. | Assigned Agency |  |  |  | MF-070-100 Process Invoice Payments | 2022-02-22 | 3:30 - 4 PM

## Tax Refunds
SIT 3 Scenario - Tax Refunds
Agency:352
SIT Week - Week 8 - 2/21 - 2/25
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | Level 3 BPR | Execution date | Window to Complete Script
1 | IFS201 - Tax Refund Interface | 8801 | 12491 | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | 352 |  |  |  |  | 2022-02-22 | 8:45-9:30 AM
2 | Cash Requirements | 11442 | 12494 | Payables Payment Processor | Perform Cash Requirements, Schedule Payments, Complete Payment Cycle | 352 |  |  |  | MF-070-100 Process Invoice Payments | 2022-02-22 | 9:30-10AM
3 | IFS517 ACH File | 10936 | 12492 | TBD | Who is generating the single statewide ACH file? | 140 |  |  |  |  | 2022-02-22 | 10-11AM
4 | IFS513 - Review IFS517 Tax Refund Data in ACH File | 11199 | 12493 | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | 352 |  |  |  |  | 2022-02-22 | 1-1:30PM
5 | IFS342 - Warrant numbers to GenTax | 8333 | 12488 | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | 352 |  |  |  |  | 2022-02-23 | LUMA Overnight
6 | IFS373 - Redemtion File | 8204 | 12487 | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | 150 |  |  |  |  | 2022-02-23 | 8:45 AM - 4 PM
7 | IFS514 - Warrant Status Updates to GenTAx | 8417 | 12489 | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | 352 |  |  |  |  | 2022-02-24 | LUMA Overnight
8 | Run GenTax Job Warrant Status Update | n/a | 12497 | GenTax User |  | 352 |  |  |  |  | 2022-02-24 | 8:45-9:30 AM
9 | Cancel Warrants in GenTax Manually | n/a | 12498 | GenTax User |  | 352 |  |  |  |  | 2022-02-24 | 9:30-10AM
10 | Run GenTax Job, Send File for IFS515 | n/a | 12499 | GenTax User |  | 352 |  |  |  |  | 2022-02-24 | 10-11AM
11 | IFS515 - GenTax Warrant Cancelations | 8636 | 12490 | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | 352 |  |  |  |  | 2022-02-24 | 1-1:30PM
12 | Manually Void Tax Refund in LUMA | Cash Void Cash Payment.xlsx (in ALM?) | TBD | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | 352 |  |  |  |  | 2022-02-24 | 1:30 - 4 PM
13 | IFS514 - Warrant Status Updates to GenTAx | 8417 | 12505 | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | 352 |  |  |  |  | 2022-02-25 | LUMA Overnight
14 | Run GenTax Job Warrant Status Update | n/a | 12500 | GenTax User |  | 352 |  |  |  |  | 2022-02-25 | 8:45-9:30 AM
15 | Journalize Cash Transactions | 12079 | 12485 | Cash Manager | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | 352 |  |  |  |  | 2022-02-25 | 9:30-10AM
16 | Post Journalized Transactions | GL Post Journal Entries.xlsx (in ALM?) | TBD | Staff Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | 352 |  |  |  |  | 2022-02-25 | 10-11AM
17 | Review GL for results of Cash transactions | 12082 | 12486 | Staff Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | 352 |  |  |  |  | 2022-02-25 | 1-1:30PM
Note on I4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard

## Custodial Accounts
SIT 3 Scenario - Budget Reporting and Trust Accounting
Agency:
SIT 3 Week - Week 9 - 2/28 - 3/4
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Set up Custodial Accounts |  | TBD | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate, and update allocations. | Assigned Agency |  |  | Associate with project | PR-050-070 | 2022-02-28 | 8:45-9:30 AM
2 | Enter cash receipt for the Custodial Account |  | TBD | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency |  |  | Deny Requisition - add note - need more information Approve Requisition | MF-260-070 Enter Cash Receipts | 2022-02-28 | 9:30-10AM
2 | Approve Cash Receipt |  | TBD | Cash Manager | Manage all cash transactions. Review and update cash management policy as needed. | Assigned Agency |  |  |  | MF-260-070 Enter Cash Receipts | 2022-02-28 | 10-11AM
3 | Final Approval of Cash Receipt |  | TBD | Cash Manager | Manage all cash transactions. Review and update cash management policy as needed. | STO |  |  |  | MF-260-070 Enter Cash Receipts | 2022-02-28 | 1-1:30PM
4 | Journalize Cash Management |  | TBD | Cash Manager | Manage all cash transactions. Review and update cash management policy as needed. | Assigned Agency |  |  |  | MF-260-090 Post to General Ledger | 2022-02-28 | 1:30-2PM
5 | View Trust Balance report in Birst |  | TBD | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate, and update allocations. | Assigned Agency |  |  |  |  | 2022-02-28 | 2-2:30PM
6 | Enter Invoice for trust account | 11443 | TBD | Payables Invoice Processor | Process interface and XM files. Match payables invoices, and vendor list. Process payables payments. Generate 1099. | Assigned Agency |  |  |  | MF-070-060 Enter a Non-PO invoice | 2022-02-28 | 2:30-3PM
7 | Enter Comments & Attachments | 11445 | TBD | Payables Invoice Processor | [5 empty] | MF-070-060 Enter a Non-PO invoice | 2022-02-28 | 3-3:30PM
8 | Approve invoice | 11444 | TBD | Approver | Approve transactions such as requisitions, purchase orders, solicitations, and journal entries. | Assigned Agency |  |  |  | MF-070-080 Invoice Approval Process | 2022-03-02 | 8:45-9:30 AM
9 | Run Cash Requirements | 11442 | TBD | Payables Manager | Void & cancel payments. Reissue & mail warrants. Process period close. | Assigned Agency |  |  |  | MF-070-100 Process Invoice Payments | 2022-03-02 | 9:30-10AM
10 | Journalize Payables | 11440 | TBD | Payables Manager | Void & cancel payments. Reissue & mail warrants. Process period close. | Assigned Agency |  |  |  | MF-070-110 Journalize Distributions | 2022-03-02 | 10-11AM
11 | View Trust Balance Report in Birst |  | TBD | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate, and update allocations. | Assigned Agency |  |  | Receive less/more than ordered |  | 2022-03-02 | 1-1:30PM
12 | Run Average Daily Balance Report |  | TBD | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate, and update allocations. | Assigned Agency |  |  | Inspection Failed, Vendor Return |  | 2022-03-02 | 1:30-2PM

## Chart of Accounts Maintenance
SIT 3 Scenario - Chart of Accounts Maintenance
Agency:
SIT Week - Week 10 - 3/7 - 3/11
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | View and Validate an Organizational Unit |  | TBD | Staff Accountant | [6 empty] | 2022-03-07 | 8:45-9:30 AM
2 | View and Validate a Project |  | TBD | Staff Accountant | [6 empty] | 2022-03-07 | 9:30-10AM
3 | View and Validate a Program |  | TBD | Staff Accountant | [6 empty] | 2022-03-07 | 10-11AM
4 | View and Validate a Location |  | TBD | Staff Accountant | [6 empty] | 2022-03-07 | 1-1:30PM
5 | View and Validate Additional Reporting |  | TBD | Staff Accountant | [6 empty] | 2022-03-07 | 1:30-2PM
6 | View and Validate Custodial Accounts (CAM) |  | TBD | Staff Accountant | [6 empty] | 2022-03-07 | 2-2:30PM
7 | Request a new account |  | TBD | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency |  |  |  |  | 2022-03-07 | 2:30-3PM
8 | Request a new organizational unit |  | TBD | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency |  |  |  |  | 2022-03-07 | 3-3:30PM
9 | View and Validate Beginning Balances |  | TBD | Staff Accountant | [6 empty] | 2022-03-08 | 8:45-9:30 AM
10 | Update Summary Conversion Balances to Detail |  | TBD | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | [5 empty] | 2022-03-08 | 9:30-10AM