## SIT 3 Listing & Schedule
SIT 3 End to End Scenarios | SIT 3 Scheduled Week | 503 - Idaho Division of Career and Technical Education
Inventory Management Cycle | Week 4: 1/24 - 1/28
Pcard End to End Process | Week 4: 1/24 - 1/28 | X
Project Processing (RQ, PO, Contract, INV) | Week 4: 1/24 - 1/28 | X
XM Pcard NO Cash Advance | Week 4: 1/24 - 1/28 | X
XM Pcard WITH Cash Advance | Week 4: 1/24 - 1/28 | X
Payroll End to End | Week 4: 1/24 - 1/28
Fixed Asset Acquire to Retire | Week 5: 1/31 - 2/4
Statewide Contract Procure to Pay | Week 5: 1/31 - 2/4 | X
GHR Shell | Week 5: 1/31 - 2/4
Project 1.1 Project Setup and Maintanance | Week 5: 1/31 - 2/4 | X
Project 1.2 Project Processing Master (P&G only) | Week 5: 1/31 - 2/4 | X
AR Credit Monitoring | Week 6: 2/7 - 2/11
Asset Management Maintenance | Week 6: 2/7 - 2/11
Service Contract Interagency Billing | Week 6: 2/7 - 2/11
Project 1.3 Reports and Inquiry Master | Week 6: 2/7 - 2/11 & Week 7: 2/14 - 2/18 | X
Cash Ledger Payment | Week 7: 2/14 - 2/18
Interagency Billing to Settlement | Week 7: 2/14 - 2/18
Non-State Billing | Week 7: 2/14 - 2/18
Procure to Pay Vendor Management Voids | Week 7: 2/14 - 2/18 | X
Vendor Refunds | Week 7: 2/14 - 2/18 | X
Cash Management Deposit to Revenue | Week 8: 2/21 - 2/25 | X
Custodial Accounts Setup | Week 8: 2/21 - 2/25
Global Ledger Entries and Analysis | Week 8: 2/21 - 2/25 | X
Punchout Request to Payment | Week 8: 2/21 - 2/25 | X
Tax Refunds | Week 8: 2/21 - 2/25
Allocations | Week 9: 2/28 - 3/4
Budget | Week 9: 2/28 - 3/4
Custodial Accounts Transaction Processing | Week 9: 2/28 - 3/4
Month End/Year End | Week 9: 2/28 - 3/4
Define and Generate Recurring Invoices | Week 9: 2/28 - 3/4
Chart of Accounts Maintenance | Week 10: 3/7 - 3/11 | X
3rd Party Allocations | TBD

## Instructions
Luma System Integration Testing 3 (SIT 3) Instructions
Agency Functional Testing Dates | January 24 - March 11, 2022 Testing Schedule: Monday -Thursday 8:45 -11 am and 1:45 - 4:00 pm, Friday 9:00 - 11:00 am
Agency Testers Roles and Responsibilities | 1. Execute test scripts per SIT 3 schedule. 2. Review actual results against expected results. 3. Log defects as needed. 4. Retest failed test results to resolve defects. 5. Launch integrations during test cycle per schedule.
Testing Packet | 1. Test Scenario Excel File: Cover Page, Instruction Tab, Scenario Listing, Tab with each steps script detailed instruction to execute the script. 2. Data Sheets. 3. Email Template to use to report your testing results.
Testing Steps | 1. If you are the first step in the scenario, you may begin execution according to the the Date and Time in the Testing packet. If you are not on step 1, please wait for the step before you to complete their script and you receive communication to begin. 2. Execute assigned script(s) using the testing script and data sheet that was provided to you. 3. Sending Testing results via email using to the Test Management Team. (attached email sample) 4. Communicate to the next tester they can begin their script. (Slack or Email works)
What should you do if there are issues or you need assistance while testing? | 1. The Test Management Team will host an all-day SIT 3 Testing Support Hotline (WebEx Meeting). 2. Attendance is optional for SIT testers and testers should only join if they have questions or issues regarding SIT testing. 3. Testers should have an invite on their calendar that includes the WebEx Link.
How to submit a SIT 3 Testing Defect using ServiceNow: | 1. Visit https://auth.sco.idaho.gov/ in your web browser. Google Chrome and Microsoft Edge are recommended. 2. Enter your State ID number as the username and your password. Click the Sign In button. 3. You will be presented with a second page for Multi-Factor Authentication. Select an option and acknowledge the push or call, or enter a passcode from your Duo app. 4. You will see several buttons on your Enterprise Dashboard. One of these will be labeled Service Desk. This button will take you to the Service Portal. 5. There are four main buttons across the center of the page. Click Service Requests to be taken to the service menu. 7. Locate and select LUMA SIT3 Testing Issue from the options listed. 6. Select the SCO IT Services category from the list on the left side of the page. 7. Fill out form with Primary Contact, Short Description, Description, Category, Scenario Name, Script ID, add attachments/screenshots and submit the ticket.
What to do if there is a system outage? | 1. Please join the Testing Support Hotline if you run into any issues with the system and notify the meeting moderator of the issue. 2. If there is a system outage, the Test Management Team will work with the Communications team to notify Agency Testers.

## Email Submission Template
Click on Icon Below to Outlook Email Template

## PCard End to End
SIT 3 Scenario Pcard End to End Process
Agency:
SIT Week - Week 4 - 1/24 - 1/28
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Set up new Users | 11486 | 11913 | Pcard Administrator |  | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov |  | PR-050-130: Obtaining a Purchase Card | 2022-01-24 | 8:45-9:30 AM
2 | Set up new Card Numbers | 11644 | 11916 | Pcard Administrator |  | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov |  | PR-050-130: Obtaining a Purchase Card | 2022-01-24 | 9:30-10AM
3 | Link User to Card Number | 11645 | 11918 | Pcard Administrator |  | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov |  | PR-050-130: Obtaining a Purchase Card | 2022-01-24 | 10-11AM
4 | Request for a Pcard | 11646 | 11917 | Pcard Approver | A state employee authorized to approve goods & services purchased with a pcard. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov |  | PR-050-130: Obtaining a Purchase Card | 2022-01-24 | 1-1:30PM
5 | Approve Pcard Request | 11485 | 11912 | Pcard Administrator |  | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov |  | PR-050-130: Obtaining a Purchase Card | 2022-01-24 | 1:30-2PM
6 | Assumption: Card is used and transactions are interfaced into Luma Pcard module | Statements must be manually created for each agency |  | Pcard Administrator |  | SCO | Brian Butkus | brian.butkus@cte.idaho.gov |  | PR-050-140: Purchasing With Purchase Card | 2022-01-24 | 2-2:30PM
7 | Approving Transactions | 11484 | 11911 | Pcard Approver | A state employee authorized to approve goods & services purchased with a pcard. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov | Add a Project to distribution | PR-050-140: Purchasing With Purchase Card | 2022-01-25 | 8:45 - 10:30AM
8 | Review Pcard charges | 11652 | 11914 | Pcard Approver | A state employee authorized to approve goods & services purchased with a pcard. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov |  | PR-050-140: Purchasing With Purchase Card | 2022-01-25 | 8:45 - 10:30AM
9 | Review Pcard Invoice | 11653 | 11915 | Payables Manager | Void & cancel payments, reissue & mail warrants. Process period close. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov |  | PR-050-140: Purchasing With Purchase Card | 2022-01-25 | 10:30-11AM
10 | Pay Pcard Invoice | 11365 | 11920 | Payables Manager | Void & cancel payments, reissue & mail warrants. Process period close. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov |  | PR-050-140: Purchasing With Purchase Card | 2022-01-25 | 10:30-11AM
11 | Journalize Entries | 11364 | 11919 | Payables Manager | Void & cancel payments, reissue & mail warrants. Process period close. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov |  | PR-050-140: Purchasing With Purchase Card | 2022-01-25 | 10:30-11AM
12 | Deactivate User | 11463 | 11910 | Pcard Administrator |  | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov |  | PR-050-130: Obtaining a Purchase Card | 2022-01-25 | 1 - 1:30 PM

## Project Processing
SIT 3 Scenario - Project Procurement Processing
Agency:
SIT Week - Week 4 - 1/24 - 1/28
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Create RSS Requisition for a Project Item | 2968 | 12522 | Requester | Determines requirements & cost estimates for purchase of goods & services. Submits purchase requisition. | Assigned Agency | Elvira Lara | elvira.lara@cte.idaho.gov |  | PR-020-010 | 2022-01-25 | 8:45-9:30 AM
2 | Approve Requisition | 8539 | 12528 | Approver | Approve transactions such as requisitions, purchase orders, solicitations, and journal entries. | Assigned Agency | (1st approver) Elvira Lara (2nd approver) Tim Tower (3rd approver) Brian Butkus | elvira.lara@cte.idaho.gov tim.tower@cte.idaho.gov brian.butkus@cte.idaho.gov |  | PR-010-060 | 2022-01-25 | 9:30-10AM
3 | Create a Purchase Order | 8169 | 12523 | Buyer | Review requisition and create purchase orders. Conduct market research, and monitor vendor commitments. Approve vendor returns. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov |  | PR-050-040 | 2022-01-25 | 10-11AM
4 | Create a Receipt | 4581 | 12532 | Receiver | Receive and inspect incoming goods. Pick items for shipment/transfer. Dispose of items. Conduct vendor returns. Document variances. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov | Receiving Messages | PR-050-070 | 2022-01-25 | 1-1:30PM
5 | Create Contract (Sub-Award) with Service Lines | 7219 | 12533 | Contract Manager | Compile contract file, including entering contract line-item details, terms & conditions, and pricing, and amends and renews contracts. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov | First Line = $25,000 Second line = Remainder of the Sub-Award | PR-040-010 | 2022-01-25 | 1:30-2PM
6 | Create Contract - Contract Draft - Articles Tab | 7204 | 12531 | Contract Manager | Compile contract file, including entering contract line-item details, terms & conditions, and pricing, and amends and renews contracts. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov |  | PR-040-010 | 2022-01-25 | 2-2:30PM
7 | Create Contract - Contract Draft - Participants Tab | 2667 | 12537 | Contract Manager | Compile contract file, including entering contract line-item details, terms & conditions, and pricing, and amends and renews contracts. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov |  | PR-040-010 | 2022-01-25 | 2:30-3PM
8 | Create Contract - Contract Draft - Lines Tab - Service | 3375 | 12536 | Contract Manager | Compile contract file, including entering contract line-item details, terms & conditions, and pricing, and amends and renews contracts. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov |  | PR-040-010 | 2022-01-25 | 3-3:30PM
9 | Create Contract - Contract Draft - Contacts Tab | 3335 | 12534 | Contract Manager | Compile contract file, including entering contract line-item details, terms & conditions, and pricing, and amends and renews contracts. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov |  | PR-040-010 | 2022-01-26 | 8:45-9:30 AM
10 | Create Contract - Contract Draft - Releasing a Contract | 7203 | 12530 | Contract Manager | Compile contract file, including entering contract line-item details, terms & conditions, and pricing, and amends and renews contracts. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov |  | PR-040-010 | 2022-01-26 | 9:30-10AM
11 | Create Contract - Contract Draft - Activating a Contract | 7202 | 12540 | Contract Manager | Compile contract file, including entering contract line-item details, terms & conditions, and pricing, and amends and renews contracts. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov |  | PR-040-010 | 2022-01-26 | 10-11AM
12 | Contract Approval | 8353 | 12524 | Approver | Approve transactions such as requisitions, purchase orders, solicitations, and journal entries. | Assigned Agency | (1st approver) Elvira Lara (2nd approver) Tim Tower (3rd approver) Brian Butkus | elvira.lara@cte.idaho.gov tim.tower@cte.idaho.gov brian.butkus@cte.idaho.gov |  | PR-040-010 | 2022-01-26 | 1-1:30PM
13 | Create Requisition - Service Lines from Contract (Sub-Award) | 8323 | 12529 | Requester | Determines requirements & cost estimates for purchase of goods & services. Submits purchase requisition. | Assigned Agency | Elvira Lara | elvira.lara@cte.idaho.gov |  | PR-010-060 | 2022-01-26 | 1:30-2PM
14 | Approve Requisition | 8539 | 12539 | Approver | Approve transactions such as requisitions, purchase orders, solicitations, and journal entries. | Assigned Agency | (1st approver) Elvira Lara (2nd approver) Tim Tower (3rd approver) Brian Butkus | elvira.lara@cte.idaho.gov tim.tower@cte.idaho.gov brian.butkus@cte.idaho.gov |  | PR-020-020 | 2022-01-26 | 2-2:30PM
15 | Create a Purchase Order | 2753 | 12538 | Buyer | Review requisition and create purchase orders. Conduct market research, and monitor vendor commitments. Approve vendor returns. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov |  | PR-050-040 | 2022-01-26 | 2:30-3PM
16 | Create Invoice | 11374 | 12525 | Payables Invoice Processor | Process interface and XM files. Match payables invoices, and vendor list. Process payables payments. Generate 1099. | Assigned Agency | Elvira Lara | elvira.lara@cte.idaho.gov |  | MF-070-050 Enter a PO Invoice | 2022-01-26 | 3-3:30PM
17 | Approve Invoice | 11375 | 12527 | Approver | Approve transactions such as requisitions, purchase orders, solicitations, and journal entries. | Assigned Agency | (1st approver) Elvira Lara (2nd approver) Tim Tower (3rd approver) Brian Butkus | elvira.lara@cte.idaho.gov tim.tower@cte.idaho.gov brian.butkus@cte.idaho.gov |  | MF-070-056 Invoice Approval Process | 2022-01-26 | 3:30 -4 PM
18 | Match Invoice | 11457 | 12535 | Payables Manager | Void & cancel payments. Reissue & mail warrants. Process period close. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov |  | MF-070-070 Match Invoices | 2022-01-27 | 8:45-9:30 AM
19 | Process Payment for Invoice | 11442 | 12526 | Payables Manager | Void & cancel payments. Reissue & mail warrants. Process period close. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov |  | MF-070-100 Process Invoice Payments | 2022-01-27 | 9:30-10AM

## XM Pcard No Cash Advance
SIT 3 Scenario Expense Management (XM) using Pcard
Agency:
SIT Week - Week 4 - 1/24 - 1/28
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Create & submit Travel Plan | 11470 | 11953 | XM Consumer | Request travel approval. Submit documentation for reimbursement. | Assigned Agency | Elvira Lara | elvira.lara@cte.idaho.gov | Add a Project to distribution | MF-075-100: Process Expense Reports | 2022-01-24 | 8:45-9:30 AM
2 | Review & approve Travel Plan | 11473 | 11957 | XM Approver | A state employee authorized to approve travel related expenses. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov |  | MF-075-100: Process Expense Reports | 2022-01-24 | 9:30-10AM
3 | Create & submit Expense Report | 11471 | 11956 | XM Consumer | Request travel approval. Submit documentation for reimbursement. | Assigned Agency | Elvira Lara | elvira.lara@cte.idaho.gov | Add a Project to distribution | MF-075-100: Process Expense Reports | 2022-01-24 | 10-11AM
4 | Review & approve Expense Report | 11474 | 11960 | XM Approver | A state employee authorized to approve travel related expenses. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov |  | MF-075-100: Process Expense Reports | 2022-01-24 | 1-1:30PM
5 | Interface from XM to Luma AP (automatic on schedule) | No Test ID - interface process |  | Payables Manager |  | SCO | Brian Butkus | brian.butkus@cte.idaho.gov |  |  | 2022-01-24 | 1:30-2PM
6 | Pcard transactions arrives on interface IFS004 (manual upload) | No Test ID - interface process |  | PCARD Administration |  | SCO | Brian Butkus | brian.butkus@cte.idaho.gov |  |  | 2022-01-24 | 2-2:30PM
7 | Approve Pcard charges | 11484 | 11954 | Cardholder | A state employee authorized to purchase goods and services with pcard. | Assigned Agency | Elvira Lara | elvira.lara@cte.idaho.gov |  | PR-050-140: Purchasing with Pcard | 2022-01-25 | 8:45-9:30 AM
8 | Close Pcard charges | 11484 | 11961 | PCARD Approver | A state employee authorized to approve goods & services purchased with a pcard. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov |  | PR-050-140: Purchasing with Pcard | 2022-01-25 | 9:30-10AM
9 | Review Pcard invoice for payment | 11653 | 11955 | Payables Manager | Void & cancel payments, reissue & mail warrants. Process period close. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov |  | MF-070-100: Process Invoice Payments | 2022-01-25 | 10-11AM
10 | Run Cash Requirements | 11365 | 11959 | Payables Manager | Void & cancel payments, reissue & mail warrants. Process period close. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov |  | MF-070-100: Process Invoice Payments | 2022-01-25 | 1-1:30PM
11 | Journalize the transactions | 11364 | 11958 | Payables Manager | Void & cancel payments, reissue & mail warrants. Process period close. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov |  | MF-070-100: Process Invoice Payments | 2022-01-25 | 1:30-2PM

## XM Pcard With Cash Advance
SIT 3 Scenario Expense Management (XM) using Pcard
Agency:
SIT Week - Week 4 - 1/24 - 1/28
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Create & submit Travel Plan | 11634 | 11962 | XM Consumer | Request travel approval. Submit documentation for reimbursement. | Assigned Agency | Elvira Lara | elvira.lara@cte.idaho.gov | Add a Project to distribution | Process Expense Reports MF-075-100 | 2022-01-26 | 8:45-9:30 AM
2 | Review & approve Travel Plan | 11637 | 11966 | XM Approver | A state employee authorized to approve travel related expenses. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov |  | Process Expense Reports MF-075-100 | 2022-01-26 | 9:30-10AM
3 | Create a Cash Advance request | 11641 | 11973 | XM Consumer | Request travel approval. Submit documentation for reimbursement. | Assigned Agency | Elvira Lara | elvira.lara@cte.idaho.gov | Add a Project to distribution | Process Expense Reports MF-075-100 | 2022-01-26 | 10-11AM
4 | Approve a Cash Advance | 11642 | 11974 | XM Approver | A state employee authorized to approve travel related expenses. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov |  | Process Expense Reports MF-075-100 | 2022-01-26 | 1-1:30PM
5 | Process the Cash Advance in AP | 11642 | 11976 | Payables Manager | Void & cancel payments, reissue & mail warrants. Process period close. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov |  | Process Expense Reports MF-075-100 | 2022-01-26 | 1:30-2PM
6 | Run Cash Requirements | 11442 | 11972 | Payables Manager | Void & cancel payments, reissue & mail warrants. Process period close. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov |  | MF-070-100 Process Invoice Payments | 2022-01-26 | 2-2:30PM
7 | Journalize the transactions | 11440 | 11971 | Payables Manager | Void & cancel payments, reissue & mail warrants. Process period close. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov |  | MF-070-100 Process Invoice Payments | 2022-01-26 | 2:30 - 3 PM
8 | Create & submit Expense Report | 11635 | 11965 | XM Consumer | Request travel approval. Submit documentation for reimbursement. | Assigned Agency | Elvira Lara | elvira.lara@cte.idaho.gov | Add a Project to distribution | Process Expense Reports MF-075-100 | 2022-01-26 | 3 - 3:30 PM
9 | Reconcile Cash Adv with Exp Report | 11643 | 11975 | XM Consumer | Request travel approval. Submit documentation for reimbursement. | Assigned Agency | Elvira Lara | elvira.lara@cte.idaho.gov |  | Process Expense Reports MF-075-100 | 2022-01-26 | 3:30 - 4 PM
10 | Review & approve Expense Report | 11638 | 11969 | XM Approver | A state employee authorized to approve travel related expenses. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov |  | Process Expense Reports MF-075-100 | 2022-01-26 | 4 -4:30 PM
11 | Interface from XM to Luma AP (automatic on schedule) | No Test ID - interface process |  | Payables Manager |  | SCO | Brian Butkus | brian.butkus@cte.idaho.gov |  |  | 2022-01-26 | Runs on automated schedule
12 | Pcard transactions arrives on interface IFS004 (manual upload) | No Test ID - interface process |  | PCARD Administration |  | SCO | Brian Butkus | brian.butkus@cte.idaho.gov |  |  | 2022-01-26 | 4:30 - 5 PM
13 | Approve Pcard charges | 11484 | 11963 | Cardholder | A state employee authorized to purchase goods and services with pcard. | Assigned Agency | Elvira Lara | elvira.lara@cte.idaho.gov |  | Purchasing with Pcard PR-050-140 | 2022-01-27 | 8:45-9:30 AM
14 | Close Pcard charges | 11484 | 11970 | PCARD Approver | A state employee authorized to approve goods & services purchased with a pcard. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov |  | Purchasing with Pcard PR-050-140 | 2022-01-27 | 9:30-10AM
15 | Review Pcard invoice | 11653 | 11964 | Payables Manager | Void & cancel payments, reissue & mail warrants. Process period close. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov |  | MF-070-100 Process Invoice Payments | 2022-01-27 | 10-11AM
16 | Run Cash Requirements | 11442 | 11968 | Payables Manager | Void & cancel payments, reissue & mail warrants. Process period close. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov |  | MF-070-100 Process Invoice Payments | 2022-01-27 | 1-1:30PM
17 | Journalize the transactions | 11440 | 11967 | Payables Manager | Void & cancel payments, reissue & mail warrants. Process period close. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov |  | MF-070-100 Process Invoice Payments | 2022-01-27 | 1:30-2PM

## Statewide Contract Procure to P
SIT 3 Scenario - Statewide Contract Procure to Pay
Agency:
SIT 3 Week - Week 5 - 1/31-2/4
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Create Contract with Rebate and Price Breaks Statewide for Envelopes - Create a Contract (Contract Tab) | 7219 | 11992 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-020 | 2022-01-31 | 8:45 - 11 AM
2 | Create Contract with Rebate and Price Breaks Statewide for Envelopes - Contract Draft (Articles) | 7204 | 11987 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-020 | 2022-01-31 | 8:45 - 11 AM
3 | Create Contract with Rebate and Price Breaks Statewide for Envelopes - Contract Draft - Participants | 2667 | 11997 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-020 | 2022-01-31 | 8:45 - 11 AM
4 | Create Contract with Rebate and Price Breaks Statewide for Envelopes - Contract Draft - Lines - Special | 8909 | 11995 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-020 | 2022-01-31 | 8:45 - 11 AM
5 | Create Contract with Rebate and Price Breaks Statewide for Envelopes - Contract Draft - Lines - Purchase Type Detail - Purchase Pricing | 2663 | 11996 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-020 | 2022-01-31 | 8:45 - 11 AM
6 | Create Contract with Rebate and Price Breaks Statewide for Envelopes - Contract Draft - Rebates | 2671 | 11998 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-020 | 2022-01-31 | 8:45 - 11 AM
7 | Create Contract with Rebate and Price Breaks Statewide for Envelopes - Contract Draft - Contacts | 3335 | 11993 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-020 | 2022-01-31 | 8:45 - 11 AM
8 | Create Contract with Rebate and Price Breaks Statewide for Envelopes - Releasing a Contract | 7203 | 11985 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-020 | 2022-01-31 | 8:45 - 11 AM
9 | Create Contract with Rebate and Price Breaks Statewide for Envelopes - Activating a Contract | 7202 | 11978 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-020 | 2022-01-31 | 8:45 - 11 AM
10 | Contract Approval | 8353 | 11979 | Approver | Approve transactions such as requisitions, purchase orders, solicitation & journal entries. | DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-020 | 2022-01-31 | 1 - 1:30 PM
11 | Requisition - RSS | 8325 | 11988 | Requester | Determines requirements & cost estimates for purchase of goods & services. Submits purchase requisition. | Assigned Agency | Elvira Lara | elvira.lara@cte.idaho.gov | distribution to multiple org unit and agencies | PR-020-010 | 2022-01-31 | 1:30 - 2:30 PM
12 | Approve Requisition | 8539 | 11984 | Approver | Approve transactions such as requisitions, purchase orders, solicitation & journal entries. | Assigned Agency | (1st Approver) Laura Handley (2nd Approver) Tim Tower | laura.handley@cte.idaho.gov tim.tower@cte.idaho.gov |  | PR-020-010 | 2022-01-31 | 2:30 - 3 PM
13 | Create PO from Requisition | 8327 | 11991 | Buyer | Review requisitions & create purchase orders. Conduct market research & monitor vendor commitments. Approve vendor returns. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov |  | PR-050-040 | 2022-02-01 | 8:45-9:30 AM
14 | Receive Purchase Order | 3064 | 11977 | Receiver | Receive and inspect incoming goods. Pick items for shipment/transfer. Dispose of items. Vendor returns. Document variances. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov |  | PR-050-070 | 2022-02-01 | 9:30-10AM
15 | Create Invoice | 11606 | 11983 | Payables Invoice Processor | Process interface and XM files. Match payables invoices, and vendor list. Process payables payments. Generate 1099. | Assigned Agency | Elvira Lara | elvira.lara@cte.idaho.gov |  | MF-070-050 Enter a PO Invoice | 2022-02-01 | 10-11AM
16 | Notify Buyer of Discrepancy | 11605 | 11982 | Payables Invoice Processor | Process interface and XM files. Match payables invoices, and vendor list. Process payables payments. Generate 1099. |  | Elvira Lara | elvira.lara@cte.idaho.gov |  | MF-070-050 Enter a PO Invoice | 2022-02-01 | 1-1:30PM
17 | Resolve Cost Discrepancy | New | 12004 | Buyer | Review requisition and create purchase orders. Conduct market research, and monitor vendor commitments. Approve vendor returns. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov |  |  | 2022-02-01 | 1:30-2PM
18 | Submit Resolved Invoice for Approval | 11607 | 11989 | Payables Invoice Processor | Process interface and XM files. Match payables invoices, and vendor list. Process payables payments. Generate 1099. |  | Elvira Lara | elvira.lara@cte.idaho.gov |  | MF-070-050 Enter a PO Invoice | 2022-02-01 | 2-2:30PM
19 | Approve Invoice | 11608 | 11990 | Approver | Approve transactions such as requisitions, purchase orders, solicitations, and journal entries. | Assigned Agency | (1st Approver) Laura Handley (2nd Approver) Tim Tower | laura.handley@cte.idaho.gov tim.tower@cte.idaho.gov |  | MF-070-056 Invoice Approval Process | 2022-02-01 | 2:30-3PM
20 | Match Invoice | 11609 | 11994 | Payables Manager | Void & cancel payments. Reissue & mail warrants. Process period close. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov |  | MF-070-070 Match Invoices | 2022-02-01 | 3-3:30PM
21 | Process Payment for Invoice | 11442 | 11981 | Payables Manager | Void & cancel payments. Reissue & mail warrants. Process period close. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov |  | MF-070-100 Process Invoice Payments | 2022-02-01 | 3-3:30PM
22 | Journalize | 11440 | 11980 | Payables Manager | Void & cancel payments. Reissue & mail warrants. Process period close. |  | Brian Butkus | brian.butkus@cte.idaho.gov |  | MF-070-110 Journalize AP Distributions | 2022-02-01 | 3-3:30PM
23 | Renew/Addendum Statewide Contract | 2773 | 11986 | Contract Manager | Compile contract file, including entering contract line-item details, terms & conditions, and pricing, and amends and renews contracts. | DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-050-010 | 2022-02-02 | 8:45-9:30 AM
24 | Load Rebate Invoices | New | 11999 | Supply Management Admin or Processor |  | Assigned Agency |  |  |  | PR-050-010 | 2022-02-02 | 9:30-10AM
25 | Calculate Rebate Amounts Due for a Contract | New | 12000 | Supply Management Admin or Processor | [5 empty] | PR-050-010 | 2022-02-02 | 10-11AM
26 | Review Rebate Due Information | New | 12001 | Contract Manager | Compile contract file, including entering contract line-item details, terms & conditions, and pricing, and amends and renews contracts. | Assigned Agency | DOP Tester | contractadmin@adm.idaho.gov |  | PR-050-010 | 2022-02-02 | 1-1:30PM
27 | Apply Rebate (Enter a Rebate Invoice in Payables | New | 12002 | Payables Manager | Void & cancel payments. Reissue & mail warrants. Process period close. |  | Lynn Christian | lynn.christian@adm.idaho.gov | There isn't an invoice type of Rebate Invoice???? | MF-260-070ZZ | 2022-02-03 | 8:45-9:30 AM
28 | Review Rebate Information | New | 12003 | Contract Manager | Compile contract file, including entering contract line-item details, terms & conditions, and pricing, and amends and renews contracts. |  | DOP Tester | contractadmin@adm.idaho.gov |  | PR-050-010 | 2022-02-03 | 9:30-10AM
29 | Verify Rebates posted in Cash Account |  |  | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Genny Casiano | genny.casiano@adm.idaho.gov |  | MF-260-070ZZ | 2022-02-03 | 10-11 AM

## Project 1.1 Project Setup and M
SIT 3 Scenario - Project Setup
Agency:
SIT 3 Week - Week 5 - 1/31-2/4
Sequence | Script ID | Tab | ALM Test ID # (view tab = "Tests" column A) | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Create Operational Project | FSM.PS001 |  | Project Administrator | Sets up projects and funding sources. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov |  | MF-050-010 | Conference Room Pilot (In Person) 1/31 - 2/4
2 | Create Billable MultiFunded Project - External Grant/External Customer | FSM.PS002 |  | Project Administrator | Sets up projects and funding sources. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov |  | MF-280-020 | Conference Room Pilot (In Person) 1/31 - 2/4
3 | Create Internal Only Project | FSM.PS003 |  | Project Administrator | Sets up projects and funding sources. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov |  | MF-050-010 | Conference Room Pilot (In Person) 1/31 - 2/4
4 | Create MultiFunded Project w Program Income (Additive/ Deductive/ Cost Sharing) or Rebates Income Funding Source | FSM.PS004 |  | Project Administrator | Sets up projects and funding sources. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov |  | MF-280-020 | Conference Room Pilot (In Person) 1/31 - 2/4
5 | Create Milestone Project(w/wo Override) | FSM.PS005 |  | Project Administrator | Sets up projects and funding sources. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov |  | MF-280-020 | Conference Room Pilot (In Person) 1/31 - 2/4
6 | Create Project with Intercompany Funding | FSM.PS006 |  | Project Administrator | Sets up projects and funding sources. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov |  | MF-280-020 | Conference Room Pilot (In Person) 1/31 - 2/4
7 | Create a New Posting Project (child) for existing Contract (new year project) | FSM.PS007 |  | Project Administrator | Sets up projects and funding sources. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov |  | MF-280-020 | Conference Room Pilot (In Person) 1/31 - 2/4
8 | Create New Burden Codes | FSM.PS009 |  | Project Administrator | Sets up projects and funding sources. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov |  | MF-280-000ZZ | Conference Room Pilot (In Person) 1/31 - 2/4
9 | Create New Selection Group | FSM.PS010 |  | Project Administrator | Sets up projects and funding sources. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov |  | MF-280-000ZZ | Conference Room Pilot (In Person) 1/31 - 2/4
10 | Assign Burden Code To Posting Project | FSM.PS011 |  | Project Administrator | Sets up projects and funding sources. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov |  | MF-280-030ZZ | Conference Room Pilot (In Person) 1/31 - 2/4
11 | Attach Burden to Funding Source | FSM.PS012 |  | Project Administrator | Sets up projects and funding sources. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov |  | MF-280-030ZZ | Conference Room Pilot (In Person) 1/31 - 2/4
12 | Program Income Additive | FSM.PM001 |  | Project Administrator | Sets up projects and funding sources. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov |  | MF-280-045ZZ | Conference Room Pilot (In Person) 1/31 - 2/4
13 | Program Income Deductive/Cost Sharing | FSM.PM002 |  | Project Administrator | Sets up projects and funding sources. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov |  | MF-280-045ZZ | Conference Room Pilot (In Person) 1/31 - 2/4

## Project 1.2 Project Processing
| NOTE: Project processing actions take place after Procurement/AP/Payroll Processing. | Other Teams Involvement Identified
SIT 3 Scenario - Project Processing (P&G Only)
Agency:
SIT Week - (dates)
Sequence | Script ID | SIT TEST ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Create Project transactions Journal Entry | FSM.PP001 | Project Accountant |  | Brian Butkus | brian.butkus@cte.idaho.gov |  |  | MF-020-050 | Conference Room Pilot (In Person) 1/31 - 2/4
2 | In-Kind Journal Entry ("on the books"/off books) | FSM.PP002 | Project Accountant |  | Brian Butkus | brian.butkus@cte.idaho.gov |  |  | MF-020-050 | Conference Room Pilot (In Person) 1/31 - 2/4
3 | Copy ( & Copy Reverse) Journal Entry | FSM.PP003 | Project Accountant |  | Brian Butkus | brian.butkus@cte.idaho.gov |  |  | MF-020-050 | Conference Room Pilot (In Person) 1/31 - 2/4
4 | Create I/C Journal Entry | FSM.PP004 | Project Accountant |  | Brian Butkus | brian.butkus@cte.idaho.gov |  |  | MF-020-050 | Conference Room Pilot (In Person) 1/31 - 2/4
5 | Create, Release and Journalize Recurring JE | FSM.PP005 | Project Accountant |  | Brian Butkus | brian.butkus@cte.idaho.gov |  |  | MF-020-050 | Conference Room Pilot (In Person) 1/31 - 2/4
6 | Post Journal |  | GL | [5 empty] | MF-020-090 | Conference Room Pilot (In Person) 1/31 - 2/4
7 | Create and Process Retainer Invoice | FSM.PP010 | Project Accountant |  | Brian Butkus | brian.butkus@cte.idaho.gov |  |  | MF-280-030: Grant Billing Processing | Conference Room Pilot (In Person) 1/31 - 2/4 |  | new process
8 | Generate Indirect Burdens | FSM.PP011 | Project Accountant |  | Brian Butkus | brian.butkus@cte.idaho.gov |  |  | DC-040-090 - Apply Overhead Costs | Conference Room Pilot (In Person) 1/31 - 2/4
9 | Delete Indirect Burden | FSM.PP012 | Project Accountant |  | Brian Butkus | brian.butkus@cte.idaho.gov |  |  | DC-040-090 - Apply Overhead Costs | Conference Room Pilot (In Person) 1/31 - 2/4
10 | Journalize Indirect Burden | FSM.PP013 | Project Accountant |  | Brian Butkus | brian.butkus@cte.idaho.gov |  |  | DC-040-090 - Apply Overhead Costs | Conference Room Pilot (In Person) 1/31 - 2/4
11 | Reverse Indirect Burden | FSM.PP014 | Project Accountant |  | Brian Butkus | brian.butkus@cte.idaho.gov |  |  | DC-040-090 - Apply Overhead Costs | Conference Room Pilot (In Person) 1/31 - 2/4
12 | Post Transaction in GL |  | GL | [5 empty] | DC-030-050 - Allocate Indirect Costs | Conference Room Pilot (In Person) 1/31 - 2/4
13 | Journalize IB Projects Transactions | FSM.PP013 | Project Accountant |  | Brian Butkus | brian.butkus@cte.idaho.gov |  |  | DC-030-050 - Allocate Indirect Costs | Conference Room Pilot (In Person) 1/31 - 2/4
14 | Post Transaction in GL |  | GL | [5 empty] | DC-030-050 - Allocate Indirect Costs | Conference Room Pilot (In Person) 1/31 - 2/4
15 | Create, Generate ,Update Certification Number & Date and Journalize Milestone Invoice | FSM.PP020 | Project Accountant |  | Brian Butkus | brian.butkus@cte.idaho.gov |  |  | MF-280-030: Grant Billing Processing | Conference Room Pilot (In Person) 1/31 - 2/4
16 | Create, Generate ,Update Certification Number & Date and Journalize Cost Reimbursement Invoice | FSM.PP021 | Project Accountant |  | Brian Butkus | brian.butkus@cte.idaho.gov |  |  | MF-280-030: Grant Billing Processing | Conference Room Pilot (In Person) 1/31 - 2/4
17 | Generate Mass Contract Invoice w/wo Billing Group, Mass Journalize and Review AR Transaction | FSM.PP022 | Project Accountant |  | Brian Butkus | brian.butkus@cte.idaho.gov |  |  | MF-280-030: Grant Billing Processing | Conference Room Pilot (In Person) 1/31 - 2/4
27 | Process Project Capitalization | FSM.PP040 | Project Accountant |  | Brian Butkus | brian.butkus@cte.idaho.gov |  |  | DC-050-030 - Capitalize Leased Asset | Conference Room Pilot (In Person) 1/31 - 2/4
28 | Contract Balance Adjustments | FSM.PP050 | Project Accountant |  | Brian Butkus | brian.butkus@cte.idaho.gov |  |  | MF-280-021ZZ | Conference Room Pilot (In Person) 1/31 - 2/4
29 | Reverse Indirect Burden | FSM.PP051 | Project Accountant |  | Brian Butkus | brian.butkus@cte.idaho.gov |  |  | DC-040-090 - Apply Overhead Costs | Conference Room Pilot (In Person) 1/31 - 2/4
30 | Delete Invoice | FSM.PP052 | Project Accountant |  | Brian Butkus | brian.butkus@cte.idaho.gov |  |  | MF-280-031ZZ | Conference Room Pilot (In Person) 1/31 - 2/4
31 | Reverse Journalize Invoice | FSM.PP053 | Project Accountant |  | Brian Butkus | brian.butkus@cte.idaho.gov |  |  | MF-280-032ZZ | Conference Room Pilot (In Person) 1/31 - 2/4
32 | New Burden Rate | FSM.PP054 | Project Accountant |  | Brian Butkus | brian.butkus@cte.idaho.gov |  |  | DC-040-091ZZ | Conference Room Pilot (In Person) 1/31 - 2/4
33 | Retainer Adjustment/ Re Applying Retainers | FSM.PP055 | Project Accountant |  | Brian Butkus | brian.butkus@cte.idaho.gov |  |  | MF-280-022ZZ | Conference Room Pilot (In Person) 1/31 - 2/4
34 | Backout & Reallocate FES Transactions | FSM.PP056 | Project Accountant |  | Brian Butkus | brian.butkus@cte.idaho.gov |  |  | MF-020-051ZZ | Conference Room Pilot (In Person) 1/31 - 2/4
35 | Review Partially Billed Transactions | FSM.PP057 | Project Accountant |  | Brian Butkus | brian.butkus@cte.idaho.gov |  |  | MF-280-030: Grant Billing Processing | Conference Room Pilot (In Person) 1/31 - 2/4
36 | Move Project within Structure | FSM.PP059 | Project Accountant |  | Brian Butkus | brian.butkus@cte.idaho.gov |  |  | MF-050-010: Set up Project | Conference Room Pilot (In Person) 1/31 - 2/4
37 | Copy Posting project | FSM.PP060 | Project Accountant |  | Brian Butkus | brian.butkus@cte.idaho.gov |  |  | MF-050-010: Set up Project | Conference Room Pilot (In Person) 1/31 - 2/4
38 | Copy Project Funding Source | FSM.PP061 | Project Accountant |  | Brian Butkus | brian.butkus@cte.idaho.gov |  |  | MF-050-010: Set up Project | Conference Room Pilot (In Person) 1/31 - 2/4
39 | Change SEFA flag | FSM.PP062 | Project Accountant |  | Brian Butkus | brian.butkus@cte.idaho.gov |  |  | MF-050-010: Set up Project | Conference Room Pilot (In Person) 1/31 - 2/4
40 | Change PoP for Specific System Code on a Posting Project | FSM.PP063 | Project Accountant |  | Brian Butkus | brian.butkus@cte.idaho.gov |  |  | MF-050-010: Set up Project | Conference Room Pilot (In Person) 1/31 - 2/4

## Project 1.3 Reports and Inquiry
Project closing takes place after project processing generally).
SIT 3 Scenario - Closing Projects
Agency:
SIT 3 Week - Week 6: 2/7 - 2/11 & Week 7: 2/14 - 2/18
Sequence | Script ID | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Project Close | FSM.PC001 | Project Accountant | Create, maintain, and close projects and grants, with billing, receiving, and cost allocations. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov |  | MF-050-090 | 2022-02-15 | 8:45-9:30 AM
2 | Review Project | FSM.PIN001 | Project Accountant | Create, maintain, and close projects and grants, with billing, receiving, and cost allocations. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov |  | DC-030-080 | 2022-02-15 | 9:30-10AM
3 | GL Journal Transaction Detail | FSM.PIN002 | Project Accountant | Create, maintain, and close projects and grants, with billing, receiving, and cost allocations. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov |  | DC-030-080 | 2022-02-15 | 10-10:30 AM
4 | Project Searches - Transactions | FSM.PIN003 | Project Accountant | Create, maintain, and close projects and grants, with billing, receiving, and cost allocations. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov |  | DC-030-080 | 2022-02-15 | 10:30 - 11 AM
5 | View all Contact Invoices & all invoices Lines | FSM.PIN004 | Project Accountant | Create, maintain, and close projects and grants, with billing, receiving, and cost allocations. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov |  | DC-030-080 | 2022-02-15 | 1-1:30PM
6 | Assign Reports | FSM.PRP001 | Project Accountant | Create, maintain, and close projects and grants, with billing, receiving, and cost allocations. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov |  | DC-030-080 | 2022-02-15 | 1:30-2PM
7 | View Project Report | FSM.PRP002 | Project Accountant | Create, maintain, and close projects and grants, with billing, receiving, and cost allocations. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov |  | DC-030-080 | 2022-02-15 | 2-2:30PM
8 | Personalize Report | FSM.PRP003 | Project Accountant | Create, maintain, and close projects and grants, with billing, receiving, and cost allocations. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov |  | DC-030-080 | 2022-02-15 | 2:30-3PM
9 | View Funding Source List | FSM.PRA001 | Project Accountant | Create, maintain, and close projects and grants, with billing, receiving, and cost allocations. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov |  | DC-030-080 | 2022-02-15 | 3 - 3:30 PM
10 | View Project Contract Reports | FSM.PRA002 | Project Accountant | Create, maintain, and close projects and grants, with billing, receiving, and cost allocations. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov |  | DC-030-080 | 2022-02-15 | 3:30 - 4 PM
11 | View Payables Reports | FSM.PRA003 | Financials Viewer |  | Assigned Agency |  |  |  | DC-030-080 | 2022-02-16 | 8:45-9:30 AM
12 | View Budget Reports | FSM.PRA004 | Project Accountant | Create, maintain, and close projects and grants, with billing, receiving, and cost allocations. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov |  | DC-030-080 | 2022-02-16 | 9:30-10AM
13 | View Receivables Reports | FSM.PRA005 | Financials Viewer |  | Assigned Agency |  |  |  | DC-030-080 | 2022-02-16 | 10-10:30 AM
14 | View d/EPM Dashboard Reports | FSM.PBI001 | Project Accountant | Create, maintain, and close projects and grants, with billing, receiving, and cost allocations. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov |  | DC-030-080 | 2022-02-16 | 10-10:30 AM

## Procure to Pay Vendor Mgt Voids
SIT 3 Scenario - Procure to Pay with Void and Vendor Update
Agency:
SIT Week - Week 7 - 2/14 -2/18
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | Luma Role (role switcher) | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Create Requisition - Special | 8324 | Requester | Assigned Agency | Elvira Lara | elvira.lara@cte.idaho.gov |  | PR-020-010 | 2022-02-14 | 8:45-9:30 AM
2 | Approve Requisition | 8539 | Approver | Assigned Agency | (1st Approver) Laura Handley (2nd Approver) Tim Tower | laura.handley@cte.idaho.gov tim.tower@cte.idaho.gov | Requisition not approved | PR-010-060 | 2022-02-14 | 9:30-10AM
3 | Create Purchase Order | 8170 | Buyer | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov |  | PR-050-040 | 2022-02-14 | 10-10:30 AM
4 | Receive Purchase Order | 4587 | Receiver | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov |  | PR-050-070 | 2022-02-14 | 10:30 - 11 AM
5 | Create Invoice | 11519 | Payables Invoice Processor | Assigned Agency | Elvira Lara | elvira.lara@cte.idaho.gov |  | MF-070-050 Enter a PO Invoice | 2022-02-14 | 1-1:30PM
6 | Approve Invoice | 11520 | Approver | Assigned Agency | (1st Approver) Laura Handley (2nd Approver) Tim Tower | laura.handley@cte.idaho.gov tim.tower@cte.idaho.gov |  | MF-070-056 Invoice Approval Process | 2022-02-14 | 1:30-2PM
7 | Match Invoice | 11458 | Payables Manager | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov |  | MF-070-070 Match Invoices | 2022-02-14 | 2-2:30PM
8 | Process Payment for Invoice | 11442 | Payables Manager | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov |  | MF-070-100 Process Invoice Payments | 2022-02-14 | 2:30-3PM
9 | Journalize | 11440 | Payables Manager |  | Brian Butkus | brian.butkus@cte.idaho.gov |  | MF-070-110 Journalize AP Distributions | 2022-02-14 | 3 - 3:30 PM
10 | Void Payment | 12080 | Cash Accountant | SCO | Elvira Lara | elvira.lara@cte.idaho.gov |  | MF-200-060 Void Cash Transactions | 2022-02-14 | 3:30 - 4 PM
11 | Cancel Invoice | 11523 | Payables Manager | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov |  | MF-070-050 Enter a PO Invoice | 2022-02-15 | 8:45-9:30 AM
12 | Request a new vendor | 11524 | Payables Invoice Processor | Assigned Agency | Elvira Lara | elvira.lara@cte.idaho.gov |  | PR-040-030 Create and Maintain Vendor | 2022-02-15 | 9:30-10AM
13 | Approve and setup new vendor | 11525 - Only SCO staff can do this | Approver | SCO | (1st Approver) Laura Handley (2nd Approver) Tim Tower | laura.handley@cte.idaho.gov tim.tower@cte.idaho.gov | Disapprove vendor | PR-040-030 Create and Maintain Vendor | 2022-02-15 | 10-10:30 AM
14 | Create Invoice | 11519 | Payables Invoice Processor | Assigned Agency | Elvira Lara | elvira.lara@cte.idaho.gov |  | MF-070-050 Enter a PO Invoice | 2022-02-15 | 10:30 - 11 AM
15 | Approve Invoice | 11520 | Approver | Assigned Agency | (1st Approver) Laura Handley (2nd Approver) Tim Tower | laura.handley@cte.idaho.gov tim.tower@cte.idaho.gov |  | MF-070-056 Invoice Approval Process | 2022-02-15 | 1-1:30PM
16 | Match Invoice | 11522 | Payables Invoice Processor | Assigned Agency | Elvira Lara | elvira.lara@cte.idaho.gov |  | MF-070-070 Match Invoices | 2022-02-15 | 1:30-2PM
17 | Process Payment for Invoice | 11442 | Payables Manager | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov |  | MF-070-100 Process Invoice Payments | 2022-02-15 | 2-2:30PM
18 | Post Transactions - Journalize | 11440 | Payables Manager | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov |  | MF-070-110 Journalize AP Distributions | 2022-02-15 | 2:30-3PM
19 | Cash Ledger Journalize | 12079 | Cash Manager | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov |  | MF-200-050 Reconcile Payments Payables and Disbursements | 2022-02-15 | 3 - 3:30 PM
20 | Verify Voided Payables Checks | 12153 | Cash Accountant | Assigned Agency | Elvira Lara | elvira.lara@cte.idaho.gov |  | MF-200-060 Void Cash Transactions | 2022-02-15 | 3:30 - 4 PM
21 | View Fund Balance | Cash Fund Balance.xlsx (in ALM?)(in Cash Deposit to Revenue Scenario) | Cash Accountant | Assigned Agency | Elvira Lara | elvira.lara@cte.idaho.gov |  | MF-200-050 Reconcile Payments Payables and Disbursements | 2022-02-16 | 8:45-9:30 AM
22 | Comparative report from Birst |  | Cash Accountant | Assigned Agency | Elvira Lara | elvira.lara@cte.idaho.gov |  | MF-200-ZZ | 2022-02-16 | 9:30-10AM
23 | Cash Revenue Daily Report - Birst |  | Cash Manager | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov |  | MF-200-ZZ | 2022-02-16 | 10-10:30 AM

## Vendor Refund
SIT 3 Scenario - Vendor Refund
Agency:
SIT 3 Week - Week 7 - 2/14 - 2/18
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Invoice Entry - Non-PO | 12444 | 12444 | Payables Invoice Processor |  |  | Elvira Lara | elvira.lara@cte.idaho.gov |  | MF-070-060 Enter Non-PO Invoice | 2022-02-15 | 8:45-9:30 AM
2 | Invoice Approver | 12445 | 12445 | Approver |  |  | (1st approver) Elvira Lara (2nd approver) Tim Tower (3rd approver) Brian Butkus | elvira.lara@cte.idaho.gov tim.tower@cte.idaho.gov brian.butkus@cte.idaho.gov |  | MF-070-056 Invoice Approval Process | 2022-02-15 | 9:30-10AM
3 | Cash Requirements | 12442 | 12442 | Payables Manager |  |  | Brian Butkus | brian.butkus@cte.idaho.gov |  | MF-070-100 Process Invoice Payments | 2022-02-15 | 10-10:30 AM
4 | Journalize | 12443 | 12443 | Payables Manager |  |  | Brian Butkus | brian.butkus@cte.idaho.gov |  | MF-070-110 Journalize AP Distributions | 2022-02-15 | 10:30 - 11 AM
5 | Create Cash Receipts |  | TBD | Cash Accountant |  |  | Elvira Lara | elvira.lara@cte.idaho.gov |  |  | 2022-02-15 | 1-1:30PM
6 | Approve Cash Receipt |  | TBD | Approver |  |  | (1st approver) Elvira Lara (2nd approver) Tim Tower (3rd approver) Brian Butkus | elvira.lara@cte.idaho.gov tim.tower@cte.idaho.gov brian.butkus@cte.idaho.gov |  |  | 2022-02-15 | 1:30-2PM
7 | Cash Receipt Final Release |  | TBD | Cash Manager |  |  | Brian Butkus | brian.butkus@cte.idaho.gov |  |  | 2022-02-15 | 2-2:30PM
8 | Jornalize Cash Transactions |  | TBD | Staff Accountant |  |  | Brian Butkus | brian.butkus@cte.idaho.gov |  |  | 2022-02-15 | 2:30-3PM
9 | Post GL Journals |  | TBD | Staff Accountant |  |  | Brian Butkus | brian.butkus@cte.idaho.gov |  |  | 2022-02-15 | 3 - 3:30 PM
10 | Adjust Reportable Income | 11837 | 12047 | Payables Manager | Void & cancel payments. Reissue & mail warrants. Process period close. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov |  | MF-070-020 Maintain Invoice | 2022-02-15 | 3:30 - 4 PM

## Cash Managem Deposit to Revenue
SIT 3 Scenario - Deposit to Revenue
Agency:
SIT Week - Week 8 - 2/21/ - 2/25
Sequence | Script ID | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 BPR PROCESSES | Execution date | Window to Complete Script
1 | Cash Fund Balance - Before Processing Transactions | TBD | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Elvira Lara | elvira.lara@cte.idaho.gov |  |  | 2022-02-22 | 8:45-9:30 AM
2 | Create Cash Receipt | TBD | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Elvira Lara | elvira.lara@cte.idaho.gov |  |  | 2022-02-22 | 9:30-10AM
3 | Approve Cash Receipt (Approve Cash Transactions in InBasket) | TBD | Cash Manager | Manage all cash transactions. Review and update cash management policy as needed. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov |  |  | 2022-02-22 | 10-11AM
4 | Cash Receipt Final Release (Approve Cash Transactions in InBasket) | TBD | Cash Manager | Manage all cash transactions. Review and update cash management policy as needed. | 150 | Brian Butkus | brian.butkus@cte.idaho.gov |  |  | 2022-02-22 | 1-1:30PM
5 | Process NSF | TBD | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Elvira Lara | elvira.lara@cte.idaho.gov |  |  | 2022-02-22 | 1:30-2PM
6 | Approve NSF (Approve Cash Transactions in InBasket) | TBD | Cash Manager | Manage all cash transactions. Review and update cash management policy as needed. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov |  |  | 2022-02-22 | 2-2:30PM
7 | NSF Final Release (Approve Cash Transactions in InBasket) | TBD | Cash Manager | Manage all cash transactions. Review and update cash management policy as needed. | 150 | Brian Butkus | brian.butkus@cte.idaho.gov |  |  | 2022-02-22 | 2:30-3PM
8 | Reclass From Suspense: No Customer (Cash Receipt Transfer) | TBD | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Elvira Lara | elvira.lara@cte.idaho.gov |  |  | 2022-02-22 | 3-3:30PM
9 | Reclass From Suspense Customer (Go to AR Scenario) | TBD | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov | Process under development. |  | 2022-02-23 | 8:45-9:30 AM
10 | Operating Transfer (Cash Ledger Transaction Transfer) | TBD | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Elvira Lara | elvira.lara@cte.idaho.gov |  |  | 2022-02-23 | 9:30-10AM
11 | Statutory Transfer (Cash Ledger Transaction Transfer) | TBD | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Elvira Lara | elvira.lara@cte.idaho.gov |  |  | 2022-02-23 | 10-11AM
12 | Approve Cash Transfer (Approve Cash Transactions in InBasket) | TBD | Cash Manager | Manage all cash transactions. Review and update cash management policy as needed. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov |  |  | 2022-02-23 | 1-1:30PM
13 | Cash Fund Balance - After Processing Transactions | TBD | Cash Manager | Manage all cash transactions. Review and update cash management policy as needed. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov |  |  | 2022-02-23 | 1:30-2PM
14 | Journalize Cash Transactions | TBD | Cash Manager | Manage all cash transactions. Review and update cash management policy as needed. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov |  |  | 2022-02-23 | 2-2:30PM
15 | Post GL Journals | TBD | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate, and update allocations. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov | Check for autopost |  | 2022-02-23 | 2:30-3PM
16 | Review Global Ledger for Transactions Processed | TBD | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate, and update allocations. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov |  |  | 2022-02-23 | 3-3:30PM

## Global Ledger Entries and Analy
SIT 3 Scenario - Global Legder Processing and Analysis
Agency:
SIT Week - Week 8 - 2/21/ - 2/25
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Create a Front-End Split Journal Entry (Front End Split Projects Only) | Refer to Upload Template | 12154 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-010 | 2022-02-23 | 8:45-9:30 AM
2 | Create a Journal Entry | Refer to Upload Template | 11668 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-010 | 2022-02-23 | 9:30-10AM
3 | Approve a Journal Entry | Refer to Upload Template | 11669 | Approver | Approve transactions such as requisitions, purchase orders, solicitation & journal entries. | Assigned Agency | Tim Tower | tim.tower@cte.idaho.gov |  | MF-025-060 | 2022-02-23 | 10-11AM
4 | Create a Journal Entry from an Existing Journal | Refer to Upload Template | 11671 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-010 | 2022-02-23 | 1-1:30PM
5 | Create a Journal Entry from a Template | Refer to Upload Template | 11670 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-010 | 2022-02-23 | 1:30-2PM
6 | Create a Recurring Journal | Refer to Upload Template | 11673 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-020 | 2022-02-23 | 2-2:30PM
7 | Journalize a Recurring Journal Entry | Refer to Upload Template | 12155 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-030 | 2022-02-23 | 2:30-3PM
8 | Post Multiple Journal Entries | Refer to Upload Template | 12156 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-23 | 3-3:30PM
9 | Post Journals from Subsystems | Refer to Upload Template | 12157 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-050 | 2022-02-24 | 8:45-9:30 AM
10 | Validate (here) Reconcile (close) Subsystems to the General Ledger | Bill will put these scripts here and in close scenario | TBD | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-24 | 9:30-10AM
11 | Analyze Global Ledger Totals | Refer to Upload Template | 12158 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-24 | 10-11AM
12 | Perform Account Analysis | Refer to Upload Template | 11672 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-24 | 1-1:30PM
13 | Perform Fund Analysis | Refer to Upload Template | 12159 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-24 | 1:30-2PM
14 | Perform Organizational Unit Analysis | Refer to Upload Template | 12160 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-24 | 2-2:30PM
15 | View Transactions by Entity-Account | Refer to Upload Template | 11674 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-25 | 9- 9:30 AM
16 | BIRST/BI/CSF Analytic Reporting |  | TBD | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-25 | 9:30 - 10 AM
17 | Evaluate Encumbrances | Placeholder - Judy and Bill (and Eileen/Cathy) are working on script for this; will have this week (12/23/21) | TBD | Staff Accountant |  | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-25 | 10 - 11 AM

## Punchout Request to Payment
SIT 3 Scenario - Punchout Request to Payment
Agency:
SIT Week - Week 8 - 2/21 - 2/25
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Create Punchout Requisition using RSS | 3501 | 11924 | Requester | Determines requirements & cost estimates for purchase of goods & services. Submits purchase requisition. | Assigned Agency | Elvira Lara | elvira.lara@cte.idaho.gov |  | PR-020-010 | 2022-02-22 | 8:45-9:30 AM
2 | Approve Requisition | 8539 | 11925 | Approver | Approve transactions such as requisitions, purchase orders, solicitation & journal entries. | Assigned Agency | (1st approver) Elvira Lara (2nd approver) Tim Tower (3rd approver) Brian Butkus | elvira.lara@cte.idaho.gov tim.tower@cte.idaho.gov brian.butkus@cte.idaho.gov | Deny Requisition - add note - need more information Approve Requisition | PR-010-060 | 2022-02-22 | 9:30-10AM
3 | Locate Punchout PO | Refer to Upload template | 12034 | Requester |  |  | Elvira Lara | elvira.lara@cte.idaho.gov |  | PR-050-040 | 2022-02-22 | 10-11AM
4 | Review Punchout PO | Refer to Upload template | 11927 | Buyer | Review requisitions & create purchase orders. Conduct market research & monitor vendor commitments. Approve vendor returns. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov | This will be a review of schedule job creating PO. Other variations would be manual creation, or Job run creation submitted as needed. | PR-050-040 | 2022-02-22 | 1-1:30PM
5 | Review Punchout Receipt | Refer to Upload template | 11928 | Receiver | Receive and inspect incoming goods. Pick items for shipment/transfer. Dispose of items. Vendor returns. Document variances. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov | Manual release of receipt vs. auto release | PR-050-070 | 2022-02-22 | 1:30-2PM
6 | Review Punchout Invoice | 11610 | 11922 | Payables Invoice Processor | Processes interface and XM files. Match Payables invoices. Manages vendor list. Processes Payables payments. Generates 1099. | Assigned Agency | Elvira Lara | elvira.lara@cte.idaho.gov |  | MF-070-050 Enter a PO Invoice | 2022-02-22 | 2-2:30PM
7 | Approve Invoice | 11611 | 11923 | Approver |  |  | (1st approver) Elvira Lara (2nd approver) Tim Tower (3rd approver) Brian Butkus | elvira.lara@cte.idaho.gov tim.tower@cte.idaho.gov brian.butkus@cte.idaho.gov |  | MF-070-056 Invoice Approval Process | 2022-02-22 | 2:30-3PM
8 | Match Invoice | 11613 | 11926 | Payables Manager | Void & cancel payments, reissue & mail warrants. Process period close. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov |  | MF-070-070 Match Invoices | 2022-02-22 | 3-3:30PM
9 | Process Invoice for Payment | 11442 | 11921 | Payables Manager | Void & cancel payments, reissue & mail warrants. Process period close. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov |  | MF-070-100 Process Invoice Payments | 2022-02-22 | 3:30 - 4 PM

## Chart of Accounts Maintenance
SIT 3 Scenario - Chart of Accounts Maintenance
Agency:
SIT Week - Week 10 - 3/7 - 3/11
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | View and Validate an Organizational Unit |  | TBD | Staff Accountant |  |  | Brian Butkus | brian.butkus@cte.idaho.gov |  |  | 2022-03-07 | 8:45-9:30 AM
2 | View and Validate a Project |  | TBD | Staff Accountant |  |  | Brian Butkus | brian.butkus@cte.idaho.gov |  |  | 2022-03-07 | 9:30-10AM
3 | View and Validate a Program |  | TBD | Staff Accountant |  |  | Brian Butkus | brian.butkus@cte.idaho.gov |  |  | 2022-03-07 | 10-11AM
4 | View and Validate a Location |  | TBD | Staff Accountant |  |  | Brian Butkus | brian.butkus@cte.idaho.gov |  |  | 2022-03-07 | 1-1:30PM
5 | View and Validate Additional Reporting |  | TBD | Staff Accountant |  |  | Brian Butkus | brian.butkus@cte.idaho.gov |  |  | 2022-03-07 | 1:30-2PM
6 | View and Validate Custodial Accounts (CAM) |  | TBD | Staff Accountant |  |  | Brian Butkus | brian.butkus@cte.idaho.gov |  |  | 2022-03-07 | 2-2:30PM
7 | Request a new account |  | TBD | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov |  |  | 2022-03-07 | 2:30-3PM
8 | Request a new organizational unit |  | TBD | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Brian Butkus | brian.butkus@cte.idaho.gov |  |  | 2022-03-07 | 3-3:30PM
9 | View and Validate Beginning Balances |  | TBD | Staff Accountant |  |  | Brian Butkus | brian.butkus@cte.idaho.gov |  |  | 2022-03-08 | 8:45-9:30 AM
10 | Update Summary Conversion Balances to Detail |  | TBD | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. |  | Brian Butkus | brian.butkus@cte.idaho.gov |  |  | 2022-03-08 | 9:30-10AM