## SIT 3 Listing & Schedule
SIT 3 End to End Scenarios | SIT 3 Scheduled Week | 520 - Public Television
Inventory Management Cycle | Week 4: 1/24 - 1/28
Pcard End to End Process | Week 4: 1/24 - 1/28 | X
Project Processing (RQ, PO, Contract, INV) | Week 4: 1/24 - 1/28 | X
XM Pcard NO Cash Advance | Week 4: 1/24 - 1/28 | X
XM Pcard WITH Cash Advance | Week 4: 1/24 - 1/28 | X
Payroll End to End | Week 4: 1/24 - 1/28
Fixed Asset Acquire to Retire | Week 5: 1/31 - 2/4 | X
Statewide Contract Procure to Pay | Week 5: 1/31 - 2/4 | X
GHR Shell | Week 5: 1/31 - 2/4
Project 1.1 Project Setup and Maintanance | Week 5: 1/31 - 2/4 | X
Project 1.2 Project Processing Master (P&G only) | Week 5: 1/31 - 2/4 | X
AR Credit Monitoring | Week 6: 2/7 - 2/11
Asset Management Maintenance | Week 6: 2/7 - 2/11 | X
Service Contract Interagency Billing | Week 6: 2/7 - 2/11
Project 1.3 Reports and Inquiry Master | Week 6: 2/7 - 2/11 & Week 7: 2/14 - 2/18 | X
Cash Ledger Payment | Week 7: 2/14 - 2/18
Interagency Billing to Settlement | Week 7: 2/14 - 2/18
Non-State Billing | Week 7: 2/14 - 2/18
Procure to Pay Vendor Management Voids | Week 7: 2/14 - 2/18 | X
Vendor Refunds | Week 7: 2/14 - 2/18
Cash Management Deposit to Revenue | Week 8: 2/21 - 2/25
Custodial Accounts Setup | Week 8: 2/21 - 2/25
Global Ledger Entries and Analysis | Week 8: 2/21 - 2/25 | X
Punchout Request to Payment | Week 8: 2/21 - 2/25 | X
Tax Refunds | Week 8: 2/21 - 2/25
Allocations | Week 9: 2/28 - 3/4
Budget | Week 9: 2/28 - 3/4
Custodial Accounts Transaction Processing | Week 9: 2/28 - 3/4
Month End/Year End | Week 9: 2/28 - 3/4
Define and Generate Recurring Invoices | Week 9: 2/28 - 3/4
Chart of Accounts Maintenance | Week 10: 3/7 - 3/11 | X
3rd Party Allocations | TBD

## Instructions
Luma System Integration Testing 3 (SIT 3) Instructions
Agency Functional Testing Dates | January 24 - March 11, 2022 Testing Schedule: Monday -Thursday 8:45 -11 am and 1:45 - 4:00 pm, Friday 9:00 - 11:00 am
Agency Testers Roles and Responsibilities | 1. Execute test scripts per SIT 3 schedule. 2. Review actual results against expected results. 3. Log defects as needed. 4. Retest failed test results to resolve defects. 5. Launch integrations during test cycle per schedule.
Testing Packet | 1. Test Scenario Excel File: Cover Page, Instruction Tab, Scenario Listing, Tab with each steps script detailed instruction to execute the script. 2. Data Sheets. 3. Email Template to use to report your testing results.
Testing Steps | 1. If you are the first step in the scenario, you may begin execution according to the the Date and Time in the Testing packet. If you are not on step 1, please wait for the step before you to complete their script and you receive communication to begin. 2. Execute assigned script(s) using the testing script and data sheet that was provided to you. 3. Sending Testing results via email using to the Test Management Team. (attached email sample) 4. Communicate to the next tester they can begin their script. (Slack or Email works)
What should you do if there are issues or you need assistance while testing? | 1. The Test Management Team will host an all-day SIT 3 Testing Support Hotline (WebEx Meeting). 2. Attendance is optional for SIT testers and testers should only join if they have questions or issues regarding SIT testing. 3. Testers should have an invite on their calendar that includes the WebEx Link.
How to submit a SIT 3 Testing Defect using ServiceNow: | 1. Visit https://auth.sco.idaho.gov/ in your web browser. Google Chrome and Microsoft Edge are recommended. 2. Enter your State ID number as the username and your password. Click the Sign In button. 3. You will be presented with a second page for Multi-Factor Authentication. Select an option and acknowledge the push or call, or enter a passcode from your Duo app. 4. You will see several buttons on your Enterprise Dashboard. One of these will be labeled Service Desk. This button will take you to the Service Portal. 5. There are four main buttons across the center of the page. Click Service Requests to be taken to the service menu. 7. Locate and select LUMA SIT3 Testing Issue from the options listed. 6. Select the SCO IT Services category from the list on the left side of the page. 7. Fill out form with Primary Contact, Short Description, Description, Category, Scenario Name, Script ID, add attachments/screenshots and submit the ticket.
What to do if there is a system outage? | 1. Please join the Testing Support Hotline if you run into any issues with the system and notify the meeting moderator of the issue. 2. If there is a system outage, the Test Management Team will work with the Communications team to notify Agency Testers.

## Email Submission Template
Double-Click on Icon Below to Outlook Email Template

## PCard End to End
SIT 3 Scenario Pcard End to End Process
Agency:
SIT Week - Week 4 - 1/24 - 1/28
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Set up new Users | 11486 | 11913 | Pcard Administrator |  | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org |  | PR-050-130: Obtaining a Purchase Card | 2022-01-24 | 8:45-9:30 AM
2 | Set up new Card Numbers | 11644 | 11916 | Pcard Administrator |  | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org |  | PR-050-130: Obtaining a Purchase Card | 2022-01-24 | 9:30-10AM
3 | Link User to Card Number | 11645 | 11918 | Pcard Administrator |  | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org |  | PR-050-130: Obtaining a Purchase Card | 2022-01-24 | 10-11AM
4 | Request for a Pcard | 11646 | 11917 | Pcard Approver | A state employee authorized to approve goods & services purchased with a pcard. | Assigned Agency | Debbie Siddoway | debbie.siddoway@idahoptv.org |  | PR-050-130: Obtaining a Purchase Card | 2022-01-24 | 1-1:30PM
5 | Approve Pcard Request | 11485 | 11912 | Pcard Administrator |  | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org |  | PR-050-130: Obtaining a Purchase Card | 2022-01-24 | 1:30-2PM
6 | Assumption: Card is used and transactions are interfaced into Luma Pcard module | Statements must be manually created for each agency |  | Pcard Administrator |  | SCO | Michelle Koehler | michelle.koehler@idahoptv.org |  | PR-050-140: Purchasing With Purchase Card | 2022-01-24 | 2-2:30PM
7 | Approving Transactions | 11484 | 11911 | Pcard Approver | A state employee authorized to approve goods & services purchased with a pcard. | Assigned Agency | Debbie Siddoway | debbie.siddoway@idahoptv.org | Add a Project to distribution | PR-050-140: Purchasing With Purchase Card | 2022-01-25 | 8:45 - 10:30AM
8 | Review Pcard charges | 11652 | 11914 | Pcard Approver | A state employee authorized to approve goods & services purchased with a pcard. | Assigned Agency | Debbie Siddoway | debbie.siddoway@idahoptv.org |  | PR-050-140: Purchasing With Purchase Card | 2022-01-25 | 8:45 - 10:30AM
9 | Review Pcard Invoice | 11653 | 11915 | Payables Manager | Void & cancel payments, reissue & mail warrants. Process period close. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org |  | PR-050-140: Purchasing With Purchase Card | 2022-01-25 | 10:30-11AM
10 | Pay Pcard Invoice | 11365 | 11920 | Payables Manager | Void & cancel payments, reissue & mail warrants. Process period close. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org |  | PR-050-140: Purchasing With Purchase Card | 2022-01-25 | 10:30-11AM
11 | Journalize Entries | 11364 | 11919 | Payables Manager | Void & cancel payments, reissue & mail warrants. Process period close. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org |  | PR-050-140: Purchasing With Purchase Card | 2022-01-25 | 10:30-11AM
12 | Deactivate User | 11463 | 11910 | Pcard Administrator |  | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org |  | PR-050-130: Obtaining a Purchase Card | 2022-01-25 | 1 - 1:30 PM
Note on J5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard

## Project Processing
SIT 3 Scenario - Project Procurement Processing
Agency:
SIT Week - Week 4 - 1/24 - 1/28
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Create RSS Requisition for a Project Item | 2968 | 12522 | Requester | Determines requirements & cost estimates for purchase of goods & services. Submits purchase requisition. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org |  | PR-020-010 | 2022-01-25 | 8:45-9:30 AM
2 | Approve Requisition | 8539 | 12528 | Approver | Approve transactions such as requisitions, purchase orders, solicitations, and journal entries. | Assigned Agency | Dave Taylor | Dave.Taylor@idahoptv.org |  | PR-010-060 | 2022-01-25 | 9:30-10AM
3 | Create a Purchase Order | 8169 | 12523 | Buyer | Review requisition and create purchase orders. Conduct market research, and monitor vendor commitments. Approve vendor returns. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org |  | PR-050-040 | 2022-01-25 | 10-11AM
4 | Create a Receipt | 4581 | 12532 | Receiver | Receive and inspect incoming goods. Pick items for shipment/transfer. Dispose of items. Conduct vendor returns. Document variances. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org | Receiving Messages | PR-050-070 | 2022-01-25 | 1-1:30PM
5 | Create Contract (Sub-Award) with Service Lines | 7219 | 12533 | Contract Manager | Compile contract file, including entering contract line-item details, terms & conditions, and pricing, and amends and renews contracts. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org | First Line = $25,000 Second line = Remainder of the Sub-Award | PR-040-010 | 2022-01-25 | 1:30-2PM
6 | Create Contract - Contract Draft - Articles Tab | 7204 | 12531 | Contract Manager | Compile contract file, including entering contract line-item details, terms & conditions, and pricing, and amends and renews contracts. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org |  | PR-040-010 | 2022-01-25 | 2-2:30PM
7 | Create Contract - Contract Draft - Participants Tab | 2667 | 12537 | Contract Manager | Compile contract file, including entering contract line-item details, terms & conditions, and pricing, and amends and renews contracts. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org |  | PR-040-010 | 2022-01-25 | 2:30-3PM
8 | Create Contract - Contract Draft - Lines Tab - Service | 3375 | 12536 | Contract Manager | Compile contract file, including entering contract line-item details, terms & conditions, and pricing, and amends and renews contracts. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org |  | PR-040-010 | 2022-01-25 | 3-3:30PM
9 | Create Contract - Contract Draft - Contacts Tab | 3335 | 12534 | Contract Manager | Compile contract file, including entering contract line-item details, terms & conditions, and pricing, and amends and renews contracts. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org |  | PR-040-010 | 2022-01-26 | 8:45-9:30 AM
10 | Create Contract - Contract Draft - Releasing a Contract | 7203 | 12530 | Contract Manager | Compile contract file, including entering contract line-item details, terms & conditions, and pricing, and amends and renews contracts. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org |  | PR-040-010 | 2022-01-26 | 9:30-10AM
11 | Contract Approval | 8353 | 12524 | Approver | Approve transactions such as requisitions, purchase orders, solicitations, and journal entries. | Assigned Agency | Dave Taylor | Dave.Taylor@idahoptv.org |  | PR-040-010 | 2022-01-26 | 10-11AM
12 | Create Contract - Contract Draft - Activating a Contract | 7202 | 12540 | Contract Manager | Compile contract file, including entering contract line-item details, terms & conditions, and pricing, and amends and renews contracts. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org |  | PR-040-010 | 2022-01-26 | 1-1:30PM
13 | Create Requisition - Service Lines from Contract (Sub-Award) | 8323 | 12529 | Requester | Determines requirements & cost estimates for purchase of goods & services. Submits purchase requisition. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org |  | PR-010-060 | 2022-01-26 | 1:30-2PM
14 | Approve Requisition | 8539 | 12539 | Approver | Approve transactions such as requisitions, purchase orders, solicitations, and journal entries. | Assigned Agency | Dave Taylor | Dave.Taylor@idahoptv.org |  | PR-020-020 | 2022-01-26 | 2-2:30PM
15 | Create a Purchase Order | 2753 | 12538 | Buyer | Review requisition and create purchase orders. Conduct market research, and monitor vendor commitments. Approve vendor returns. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org |  | PR-050-040 | 2022-01-26 | 2:30-3PM
16 | Create Invoice | 11374 | 12525 | Payables Invoice Processor | Process interface and XM files. Match payables invoices, and vendor list. Process payables payments. Generate 1099. | Assigned Agency | Debbie Siddoway | debbie.siddoway@idahoptv.org |  | MF-070-050 Enter a PO Invoice | 2022-01-26 | 3-3:30PM
17 | Approve Invoice | 11375 | 12527 | Approver | Approve transactions such as requisitions, purchase orders, solicitations, and journal entries. | Assigned Agency | Dave Taylor | Dave.Taylor@idahoptv.org |  | MF-070-056 Invoice Approval Process | 2022-01-26 | 3:30 -4 PM
18 | Match Invoice | 11457 | 12535 | Payables Manager | Void & cancel payments. Reissue & mail warrants. Process period close. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org |  | MF-070-070 Match Invoices | 2022-01-27 | 8:45-9:30 AM
19 | Process Payment for Invoice | 11442 | 12526 | Payables Manager | Void & cancel payments. Reissue & mail warrants. Process period close. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org |  | MF-070-100 Process Invoice Payments | 2022-01-27 | 9:30-10AM
Note on J4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard

## XM Pcard No Cash Advance
SIT 3 Scenario Expense Management (XM) using Pcard
Agency:
SIT Week - Week 4 - 1/24 - 1/28
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Create & submit Travel Plan | 11470 | 11953 | XM Consumer | Request travel approval. Submit documentation for reimbursement. | Assigned Agency | Kari Wardle | Kari.Wardle@idahoptv.org | Add a Project to distribution | MF-075-100: Process Expense Reports | 2022-01-24 | 8:45-9:30 AM
2 | Review & approve Travel Plan | 11473 | 11957 | XM Approver | A state employee authorized to approve travel related expenses. | Assigned Agency | Dave Taylor | Dave.Taylor@idahoptv.org |  | MF-075-100: Process Expense Reports | 2022-01-24 | 9:30-10AM
3 | Create & submit Expense Report | 11471 | 11956 | XM Consumer | Request travel approval. Submit documentation for reimbursement. | Assigned Agency | Kari Wardle | Kari.Wardle@idahoptv.org | Add a Project to distribution | MF-075-100: Process Expense Reports | 2022-01-24 | 10-11AM
4 | Review & approve Expense Report | 11474 | 11960 | XM Approver | A state employee authorized to approve travel related expenses. | Assigned Agency | Dave Taylor | Dave.Taylor@idahoptv.org |  | MF-075-100: Process Expense Reports | 2022-01-24 | 1-1:30PM
5 | Interface from XM to Luma AP (automatic on schedule) | No Test ID - interface process |  | Payables Manager |  | SCO | Michelle Koehler | michelle.koehler@idahoptv.org |  |  | 2022-01-24 | 1:30-2PM
6 | Pcard transactions arrives on interface IFS004 (manual upload) | No Test ID - interface process |  | PCARD Administration |  | SCO | Michelle Koehler | michelle.koehler@idahoptv.org |  |  | 2022-01-24 | 2-2:30PM
7 | Approve Pcard charges | 11484 | 11954 | Cardholder | A state employee authorized to purchase goods and services with pcard. | Assigned Agency | Florina Ruvio | Florina.Ruvio@idahoptv.org |  | PR-050-140: Purchasing with Pcard | 2022-01-25 | 8:45-9:30 AM
8 | Close Pcard charges | 11484 | 11961 | PCARD Approver | A state employee authorized to approve goods & services purchased with a pcard. | Assigned Agency | Dave Taylor | Dave.Taylor@idahoptv.org |  | PR-050-140: Purchasing with Pcard | 2022-01-25 | 9:30-10AM
9 | Review Pcard invoice for payment | 11653 | 11955 | Payables Manager | Void & cancel payments, reissue & mail warrants. Process period close. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org |  | MF-070-100: Process Invoice Payments | 2022-01-25 | 10-11AM
10 | Run Cash Requirements | 11365 | 11959 | Payables Manager | Void & cancel payments, reissue & mail warrants. Process period close. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org |  | MF-070-100: Process Invoice Payments | 2022-01-25 | 1-1:30PM
11 | Journalize the transactions | 11364 | 11958 | Payables Manager | Void & cancel payments, reissue & mail warrants. Process period close. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org |  | MF-070-100: Process Invoice Payments | 2022-01-25 | 1:30-2PM
Note on J5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard

## XM Pcard With Cash Advance
SIT 3 Scenario Expense Management (XM) using Pcard
Agency:
SIT Week - Week 4 - 1/24 - 1/28
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Create & submit Travel Plan | 11634 | 11962 | XM Consumer | Request travel approval. Submit documentation for reimbursement. | Assigned Agency | Kari Wardle | Kari.Wardle@idahoptv.org | Add a Project to distribution | Process Expense Reports MF-075-100 | 2022-01-26 | 8:45-9:30 AM
2 | Review & approve Travel Plan | 11637 | 11966 | XM Approver | A state employee authorized to approve travel related expenses. | Assigned Agency | Dave Taylor | Dave.Taylor@idahoptv.org |  | Process Expense Reports MF-075-100 | 2022-01-26 | 9:30-10AM
3 | Create a Cash Advance request | 11641 | 11973 | XM Consumer | Request travel approval. Submit documentation for reimbursement. | Assigned Agency | Kari Wardle | Kari.Wardle@idahoptv.org | Add a Project to distribution | Process Expense Reports MF-075-100 | 2022-01-26 | 10-11AM
4 | Approve a Cash Advance | 11642 | 11974 | XM Approver | A state employee authorized to approve travel related expenses. | Assigned Agency | Dave Taylor | Dave.Taylor@idahoptv.org |  | Process Expense Reports MF-075-100 | 2022-01-26 | 1-1:30PM
5 | Process the Cash Advance in AP | 11642 | 11976 | Payables Manager | Void & cancel payments, reissue & mail warrants. Process period close. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org |  | Process Expense Reports MF-075-100 | 2022-01-26 | 1:30-2PM
6 | Run Cash Requirements | 11442 | 11972 | Payables Manager | Void & cancel payments, reissue & mail warrants. Process period close. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org |  | MF-070-100 Process Invoice Payments | 2022-01-26 | 2-2:30PM
7 | Journalize the transactions | 11440 | 11971 | Payables Manager | Void & cancel payments, reissue & mail warrants. Process period close. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org |  | MF-070-100 Process Invoice Payments | 2022-01-26 | 2:30 - 3 PM
8 | Create & submit Expense Report | 11635 | 11965 | XM Consumer | Request travel approval. Submit documentation for reimbursement. | Assigned Agency | Kari Wardle | Kari.Wardle@idahoptv.org | Add a Project to distribution | Process Expense Reports MF-075-100 | 2022-01-26 | 3 - 3:30 PM
9 | Reconcile Cash Adv with Exp Report | 11643 | 11975 | XM Consumer | Request travel approval. Submit documentation for reimbursement. | Assigned Agency | Kari Wardle | Kari.Wardle@idahoptv.org |  | Process Expense Reports MF-075-100 | 2022-01-26 | 3:30 - 4 PM
10 | Review & approve Expense Report | 11638 | 11969 | XM Approver | A state employee authorized to approve travel related expenses. | Assigned Agency | Dave Taylor | Dave.Taylor@idahoptv.org |  | Process Expense Reports MF-075-100 | 2022-01-26 | 4 -4:30 PM
11 | Interface from XM to Luma AP (automatic on schedule) | No Test ID - interface process |  | Payables Manager |  | SCO | Michelle Koehler | michelle.koehler@idahoptv.org |  |  | 2022-01-26 | Runs on automated schedule
12 | Pcard transactions arrives on interface IFS004 (manual upload) | No Test ID - interface process |  | PCARD Administration |  | SCO | Michelle Koehler | michelle.koehler@idahoptv.org |  |  | 2022-01-26 | 4:30 - 5 PM
13 | Approve Pcard charges | 11484 | 11963 | Cardholder | A state employee authorized to purchase goods and services with pcard. | Assigned Agency | Florina Ruvio | Florina.Ruvio@idahoptv.org |  | Purchasing with Pcard PR-050-140 | 2022-01-27 | 8:45-9:30 AM
14 | Close Pcard charges | 11484 | 11970 | PCARD Approver | A state employee authorized to approve goods & services purchased with a pcard. | Assigned Agency | Dave Taylor | Dave.Taylor@idahoptv.org |  | Purchasing with Pcard PR-050-140 | 2022-01-27 | 9:30-10AM
15 | Review Pcard invoice | 11653 | 11964 | Payables Manager | Void & cancel payments, reissue & mail warrants. Process period close. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org |  | MF-070-100 Process Invoice Payments | 2022-01-27 | 10-11AM
16 | Run Cash Requirements | 11442 | 11968 | Payables Manager | Void & cancel payments, reissue & mail warrants. Process period close. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org |  | MF-070-100 Process Invoice Payments | 2022-01-27 | 1-1:30PM
17 | Journalize the transactions | 11440 | 11967 | Payables Manager | Void & cancel payments, reissue & mail warrants. Process period close. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org |  | MF-070-100 Process Invoice Payments | 2022-01-27 | 1:30-2PM
Note on J5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard

## Fixed Assets Acquire To Retire
SIT 3 Scenario - Acquire Fixed Asset to Retire
Agency:
SIT 3 Week - Week 5 - 1/31-2/4
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | NEW SIT 3 ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Create Fixed Asset Requisition | 3041 | 11563 | Requester | Determines requirements & cost estimates for purchase of goods & services. Submits purchase requisition. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org | Associate with project | PR-010-060 | 2022-01-31 | 8:45-9:30 AM
2 | Approve Requisition | 8539 | 11564 | Approver | Approve transactions such as requisitions, purchase orders, solicitations, and journal entries. | Assigned Agency | Dave Taylor | Dave.Taylor@idahoptv.org | Deny Requisition - add note - need more information Approve Requisition | PR-020-020 | 2022-01-31 | 9:30-10AM
3 | Identify Requistions to send to Sourcing Event | 2896 | 11565 | Buyer | Review requisition and create purchase orders. Conduct market research, and monitor vendor commitments. Approve vendor returns. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org |  | PR-030-020 | 2022-01-31 | 10-11AM
4 | Create Sourcing Event RFQ | 7186 | 11566 | Sourcing Manager | Create souring events, evaluate supplier responses, and oversee selection & award of sourcing events. | Assigned Agency | Michelle Koehler and DOP Tester | michelle.koehler@idahoptv.org - contractadmin@adm.idaho.gov |  | PR-030-030 | 2022-01-31 | 1-1:30PM
5 | Approve Sourcing Event to Post | 8439 | 11567 | Approver | Approve transactions such as requisitions, purchase orders, solicitations, and journal entries. | Assigned Agency | DOP Tester | contractadmin@adm.idaho.gov | Approve/Deny/Reject Sourcing Event to Post | PR-030-010 | 2022-01-31 | 1:30-2PM
6 | Enter A Manual response | 7187 | 11568 | Sourcing Manager | Develop/oversee supplier list; monitor & evaluate vendors. Evaluate proposals; create souring events, oversee selection & award contracts. | Assigned Agency | DOP Tester | contractadmin@adm.idaho.gov |  | PR-030-050 | 2022-01-31 | 2-2:30PM
7 | Analyze and Award an Event to Contract | 7189 | 11569 | Sourcing Manager | Develop/oversee supplier list; monitor & evaluate vendors. Evaluate proposals; create souring events, oversee selection & award contracts. | Assigned Agency | DOP Tester | contractadmin@adm.idaho.gov | Split Award by Line | PR-030-050 | 2022-01-31 | 2:30-3PM
8 | Sourcing Event Award Approval | 8440 | 11570 | Approver | Approve transactions such as requisitions, purchase orders, solicitations, and journal entries. | Assigned Agency | DOP Tester | contractadmin@adm.idaho.gov | Approve/Deny/Reject | PR-030-050 | 2022-01-31 | 3-3:30PM
9 | Create Contract - Create a Contract - Contract Tab | 7219 | 11571 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | Assigned Agency | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-010 | 2022-02-01 | 8:45 - 10:30AM
10 | Create Contract - Contract Draft - Articles Tab | 7204 | 11572 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | Assigned Agency | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-010 | 2022-02-01 | 8:45 - 10:30AM
11 | Create Contract - Contract Draft - Participants Tab | 2667 | 11573 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | Assigned Agency | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-010 | 2022-02-01 | 8:45 - 10:30AM
12 | Create Contract - Contract Draft - Lines Tab - Special | 8909 | 11574 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | Assigned Agency | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-010 | 2022-02-01 | 8:45 - 10:30AM
13 | Create Contract - Contract Draft - Contacts Tab | 3335 | 11575 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | Assigned Agency | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-010 | 2022-02-01 | 8:45 - 10:30AM
14 | Create Contract - Contract Draft - Releasing a Contract | 7203 | 11576 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | Assigned Agency | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-010 | 2022-02-01 | 8:45 - 10:30AM
15 | Contract Approval | 8353 | 11578 | Approver | Approve transactions such as requisitions, purchase orders, solicitation & journal entries. | Assigned Agency | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-010 | 2022-02-01 | 8:45 - 10:30AM
16 | Create Contract - Contract Draft - Activating a Contract | 7202 | 11577 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | Assigned Agency | DOP Tester | contractadmin@adm.idaho.gov | Approve/Deny/Reject | PR-040-010 | 2022-02-01 | 10:30-11AM
17 | Create Fixed Asset Requisition | 3041 | 11579 | Requester | Determines requirements & cost estimates for purchase of goods & services. Submits purchase requisition. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org |  | PR-010-060 | 2022-02-01 | 1-1:30PM
18 | Approve Requisition | 8539 | 11580 | Approver | Approve transactions such as requisitions, purchase orders, solicitations, and journal entries. | Assigned Agency | Dave Taylor | Dave.Taylor@idahoptv.org |  | PR-020-020 | 2022-02-01 | 1:30-2PM
19 | Create Purchase Order | 2753 | 11581 | Buyer | Review requisition and create purchase orders. Conduct market research, and monitor vendor commitments. Approve vendor returns. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org |  | PR-050-040 | 2022-02-01 | 2-2:30PM
20 | Receive Purchase Order | 2178 | 11582 | Receiver | Receive and inspect incoming goods. Pick items for shipment/transfer. Dispose of items. Conduct vendor returns. Document variances. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org | Receive less/more than ordered | PR-050-070 | 2022-02-01 | 2:30-3PM
21 | Inspect Item | 2181 | 11583 | Receiver | Receive and inspect incoming goods. Pick items for shipment/transfer. Dispose of items. Conduct vendor returns. Document variances. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org | Inspection Failed, Vendor Return | PR-050-070 | 2022-02-01 | 3-3:30PM
22 | Create Invoice | 11447 | 11584 | Payables Invoice Processor | Process interface and XM files. Match payables invoices, and vendor list. Process payables payments. Generate 1099. | Assigned Agency | Debbie Siddoway | debbie.siddoway@idahoptv.org |  | MF-070-050 Enter a PO Invoice | 2022-02-02 | 8:45-9:30 AM
23 | Approve Invoice | 11448 | 11585 | Approver | Approve transactions such as requisitions, purchase orders, solicitations, and journal entries. | Assigned Agency | Dave Taylor | Dave.Taylor@idahoptv.org |  | MF-070-056 Invoice Approval Process | 2022-02-02 | 9:30-10AM
24 | Match Invoice | 11455 | 11586 | Payables Manager | Void & cancel payments. Reissue & mail warrants. Process period close. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org |  | MF-070-070 Match Invoices | 2022-02-02 | 10-10:30AM
25 | Process Payment for Invoice | 11442 | 11587 | Payables Manager | Void & cancel payments. Reissue & mail warrants. Process period close. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org |  | MF-070-100 Process Invoice Payments | 2022-02-02 | 10:30-11AM
26 | Interface AP Asset to Asset Management | 2713 | 11900 | Asset Analyst | Create, add, transfer, adjust, retire, or dispose of assets, including privileges to run depreciation. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org |  | MF-040-030-010 | 2022-02-02 | 1-1:30PM
27 | Run Release Assets - Update | 8524 | 11905 | Asset Analyst | Create, add, transfer, adjust, retire, or dispose of assets, including privileges to run depreciation. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org | Associate with project | MF-040-030-020 | 2022-02-02 | 1:30-2PM
28 | Run Depreciation | 8522 | 11904 | Asset Manager | Manage the process to tract fixed asset activity: create, transfer, and retire fixed assets. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org |  | MF-040-070-020 | 2022-02-02 | 2-2:30PM
29 | Review Fixed Asset GL Account Transactions |  |  | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate, and update allocations. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org |  | MF-020-010 | 2022-02-02 | 2:30-3PM
30 | Asset Surplus Disposal | 11062 | 11902 | Asset Analyst | Create, add, transfer, adjust, retire, or dispose of assets, including privileges to run depreciation. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org | Transfer, retire | MF-040-060-020 | 2022-02-02 | 3-3:30PM
31 | Approve Disposal | 11263 | 11903 | Asset Manager | Manage the process to tract fixed asset activity: create, transfer, and retire fixed assets. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org | Transfer | MF-040-060-020 | 2022-02-02 | 3:30-4PM
32 | Close Contract | 2636 | 11901 | Contract Manager | Compile contract file, including entering contract line-item details, terms & conditions, and pricing, and amends and renews contracts. | Assigned Agency | DOP Tester | contractadmin@adm.idaho.gov |  | PR-050-030 | 2022-02-03 | 8:45-9:30 AM
Note on J5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard

## Statewide Contract Procure to P
SIT 3 Scenario - Statewide Contract Procure to Pay
Agency:
SIT 3 Week - Week 5 - 1/31-2/4
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Create Contract with Rebate and Price Breaks Statewide for Envelopes - Create a Contract (Contract Tab) | 7219 | 11992 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-020 | 2022-01-31 | 8:45 - 11 AM
2 | Create Contract with Rebate and Price Breaks Statewide for Envelopes - Contract Draft (Articles) | 7204 | 11987 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-020 | 2022-01-31 | 8:45 - 11 AM
3 | Create Contract with Rebate and Price Breaks Statewide for Envelopes - Contract Draft - Participants | 2667 | 11997 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-020 | 2022-01-31 | 8:45 - 11 AM
4 | Create Contract with Rebate and Price Breaks Statewide for Envelopes - Contract Draft - Lines - Special | 8909 | 11995 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-020 | 2022-01-31 | 8:45 - 11 AM
5 | Create Contract with Rebate and Price Breaks Statewide for Envelopes - Contract Draft - Lines - Purchase Type Detail - Purchase Pricing | 2663 | 11996 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-020 | 2022-01-31 | 8:45 - 11 AM
6 | Create Contract with Rebate and Price Breaks Statewide for Envelopes - Contract Draft - Rebates | 2671 | 11998 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-020 | 2022-01-31 | 8:45 - 11 AM
7 | Create Contract with Rebate and Price Breaks Statewide for Envelopes - Contract Draft - Contacts | 3335 | 11993 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-020 | 2022-01-31 | 8:45 - 11 AM
8 | Create Contract with Rebate and Price Breaks Statewide for Envelopes - Releasing a Contract | 7203 | 11985 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-020 | 2022-01-31 | 8:45 - 11 AM
9 | Contract Approval | 8353 | 11979 | Approver | Approve transactions such as requisitions, purchase orders, solicitation & journal entries. | DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-020 | 2022-01-31 | 8:45 - 11 AM
10 | Create Contract with Rebate and Price Breaks Statewide for Envelopes - Activating a Contract | 7202 | 11978 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-020 | 2022-01-31 | 1 - 1:30 PM
11 | Requisition - RSS | 8325 | 11988 | Requester | Determines requirements & cost estimates for purchase of goods & services. Submits purchase requisition. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org | distribution to multiple org unit and agencies | PR-020-010 | 2022-01-31 | 1:30 - 2:30 PM
12 | Approve Requisition | 8539 | 11984 | Approver | Approve transactions such as requisitions, purchase orders, solicitation & journal entries. | Assigned Agency | Dave Taylor | Dave.Taylor@idahoptv.org |  | PR-020-010 | 2022-01-31 | 2:30 - 3 PM
13 | Create PO from Requisition | 8327 | 11991 | Buyer | Review requisitions & create purchase orders. Conduct market research & monitor vendor commitments. Approve vendor returns. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org |  | PR-050-040 | 2022-02-01 | 8:45-9:30 AM
14 | Receive Purchase Order | 3064 | 11977 | Receiver | Receive and inspect incoming goods. Pick items for shipment/transfer. Dispose of items. Vendor returns. Document variances. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org |  | PR-050-070 | 2022-02-01 | 9:30-10AM
15 | Create Invoice | 11606 | 11983 | Payables Invoice Processor | Process interface and XM files. Match payables invoices, and vendor list. Process payables payments. Generate 1099. | Assigned Agency | Debbie Siddoway | debbie.siddoway@idahoptv.org |  | MF-070-050 Enter a PO Invoice | 2022-02-01 | 10-11AM
16 | Notify Buyer of Discrepancy | 11605 | 11982 | Payables Invoice Processor | Process interface and XM files. Match payables invoices, and vendor list. Process payables payments. Generate 1099. |  | Debbie Siddoway | debbie.siddoway@idahoptv.org |  | MF-070-050 Enter a PO Invoice | 2022-02-01 | 1-1:30PM
17 | Resolve Cost Discrepancy | New | 12004 | Buyer | Review requisition and create purchase orders. Conduct market research, and monitor vendor commitments. Approve vendor returns. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org |  |  | 2022-02-01 | 1:30-2PM
18 | Submit Resolved Invoice for Approval | 11607 | 11989 | Payables Invoice Processor | Process interface and XM files. Match payables invoices, and vendor list. Process payables payments. Generate 1099. |  | Debbie Siddoway | debbie.siddoway@idahoptv.org |  | MF-070-050 Enter a PO Invoice | 2022-02-01 | 2-2:30PM
19 | Approve Invoice | 11608 | 11990 | Approver | Approve transactions such as requisitions, purchase orders, solicitations, and journal entries. | Assigned Agency | Dave Taylor | Dave.Taylor@idahoptv.org |  | MF-070-056 Invoice Approval Process | 2022-02-01 | 2:30-3PM
20 | Match Invoice | 11609 | 11994 | Payables Manager | Void & cancel payments. Reissue & mail warrants. Process period close. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org |  | MF-070-070 Match Invoices | 2022-02-01 | 3-3:30PM
21 | Process Payment for Invoice | 11442 | 11981 | Payables Manager | Void & cancel payments. Reissue & mail warrants. Process period close. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org |  | MF-070-100 Process Invoice Payments | 2022-02-01 | 3-3:30PM
22 | Journalize | 11440 | 11980 | Payables Manager | Void & cancel payments. Reissue & mail warrants. Process period close. |  | Michelle Koehler | michelle.koehler@idahoptv.org |  | MF-070-110 Journalize AP Distributions | 2022-02-01 | 3-3:30PM
23 | Renew/Addendum Statewide Contract | 2773 | 11986 | Contract Manager | Compile contract file, including entering contract line-item details, terms & conditions, and pricing, and amends and renews contracts. | DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-050-010 | 2022-02-02 | 8:45-9:30 AM
24 | Load Rebate Invoices | New | 11999 | Supply Management Admin or Processor |  | Assigned Agency |  |  |  | PR-050-010 | 2022-02-02 | 9:30-10AM
25 | Calculate Rebate Amounts Due for a Contract | New | 12000 | Supply Management Admin or Processor | [5 empty] | PR-050-010 | 2022-02-02 | 10-11AM
26 | Review Rebate Due Information | New | 12001 | Contract Manager | Compile contract file, including entering contract line-item details, terms & conditions, and pricing, and amends and renews contracts. | Assigned Agency | DOP Tester | contractadmin@adm.idaho.gov |  | PR-050-010 | 2022-02-02 | 1-1:30PM
27 | Apply Rebate (Enter a Rebate Invoice in Payables | New | 12002 | Payables Manager | Void & cancel payments. Reissue & mail warrants. Process period close. |  | Lynn Christian | lynn.christian@adm.idaho.gov | There isn't an invoice type of Rebate Invoice???? | MF-260-070ZZ | 2022-02-03 | 8:45-9:30 AM
28 | Review Rebate Information | New | 12003 | Contract Manager | Compile contract file, including entering contract line-item details, terms & conditions, and pricing, and amends and renews contracts. |  | DOP Tester | contractadmin@adm.idaho.gov |  | PR-050-010 | 2022-02-03 | 9:30-10AM
29 | Verify Rebates posted in Cash Account |  |  | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Genny Casiano | genny.casiano@adm.idaho.gov |  | MF-260-070ZZ | 2022-02-03 | 10-11 AM
Note on J5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard

## Project 1.1 Project Setup and M
SIT 3 Scenario - Project Setup
Agency:
SIT 3 Week - Week 5 - 1/31-2/4
Sequence | Script ID | Tab | ALM Test ID # (view tab = "Tests" column A) | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Create Operational Project | FSM.PS001 |  | Project Administrator | Sets up projects and funding sources. | Assigned Agency | Dave Taylor | Dave.Taylor@idahoptv.org |  | MF-050-010 | Conference Room Pilot (In Person) 1/31 - 2/4
2 | Create Billable MultiFunded Project - External Grant/External Customer | FSM.PS002 |  | Project Administrator | Sets up projects and funding sources. | Assigned Agency | Dave Taylor | Dave.Taylor@idahoptv.org |  | MF-280-020 | Conference Room Pilot (In Person) 1/31 - 2/4
3 | Create Internal Only Project | FSM.PS003 |  | Project Administrator | Sets up projects and funding sources. | Assigned Agency | Dave Taylor | Dave.Taylor@idahoptv.org |  | MF-050-010 | Conference Room Pilot (In Person) 1/31 - 2/4
4 | Create MultiFunded Project w Program Income (Additive/ Deductive/ Cost Sharing) or Rebates Income Funding Source | FSM.PS004 |  | Project Administrator | Sets up projects and funding sources. | Assigned Agency | Dave Taylor | Dave.Taylor@idahoptv.org |  | MF-280-020 | Conference Room Pilot (In Person) 1/31 - 2/4
5 | Create Milestone Project(w/wo Override) | FSM.PS005 |  | Project Administrator | Sets up projects and funding sources. | Assigned Agency | Dave Taylor | Dave.Taylor@idahoptv.org |  | MF-280-020 | Conference Room Pilot (In Person) 1/31 - 2/4
6 | Create Project with Intercompany Funding | FSM.PS006 |  | Project Administrator | Sets up projects and funding sources. | Assigned Agency | Dave Taylor | Dave.Taylor@idahoptv.org |  | MF-280-020 | Conference Room Pilot (In Person) 1/31 - 2/4
7 | Create a New Posting Project (child) for existing Contract (new year project) | FSM.PS007 |  | Project Administrator | Sets up projects and funding sources. | Assigned Agency | Dave Taylor | Dave.Taylor@idahoptv.org |  | MF-280-020 | Conference Room Pilot (In Person) 1/31 - 2/4
8 | Create New Burden Codes | FSM.PS009 |  | Project Administrator | Sets up projects and funding sources. | Assigned Agency | Dave Taylor | Dave.Taylor@idahoptv.org |  | MF-280-000ZZ | Conference Room Pilot (In Person) 1/31 - 2/4
9 | Create New Selection Group | FSM.PS010 |  | Project Administrator | Sets up projects and funding sources. | Assigned Agency | Dave Taylor | Dave.Taylor@idahoptv.org |  | MF-280-000ZZ | Conference Room Pilot (In Person) 1/31 - 2/4
10 | Assign Burden Code To Posting Project | FSM.PS011 |  | Project Administrator | Sets up projects and funding sources. | Assigned Agency | Dave Taylor | Dave.Taylor@idahoptv.org |  | MF-280-030ZZ | Conference Room Pilot (In Person) 1/31 - 2/4
11 | Attach Burden to Funding Source | FSM.PS012 |  | Project Administrator | Sets up projects and funding sources. | Assigned Agency | Dave Taylor | Dave.Taylor@idahoptv.org |  | MF-280-030ZZ | Conference Room Pilot (In Person) 1/31 - 2/4
12 | Program Income Additive | FSM.PM001 |  | Project Administrator | Sets up projects and funding sources. | Assigned Agency | Dave Taylor | Dave.Taylor@idahoptv.org |  | MF-280-045ZZ | Conference Room Pilot (In Person) 1/31 - 2/4
13 | Program Income Deductive/Cost Sharing | FSM.PM002 |  | Project Administrator | Sets up projects and funding sources. | Assigned Agency | Dave Taylor | Dave.Taylor@idahoptv.org |  | MF-280-045ZZ | Conference Room Pilot (In Person) 1/31 - 2/4
Note on J5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard

## Project 1.2 Project Processing
| NOTE: Project processing actions take place after Procurement/AP/Payroll Processing. | Other Teams Involvement Identified
SIT 3 Scenario - Project Processing (P&G Only)
Agency:
SIT Week - (dates)
Sequence | Script ID | SIT TEST ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Create Project transactions Journal Entry | FSM.PP001 | Project Accountant |  | Dave Taylor | Dave.Taylor@idahoptv.org |  |  | MF-020-050 | Conference Room Pilot (In Person) 1/31 - 2/4
2 | In-Kind Journal Entry ("on the books"/off books) | FSM.PP002 | Project Accountant |  | Dave Taylor | Dave.Taylor@idahoptv.org |  |  | MF-020-050 | Conference Room Pilot (In Person) 1/31 - 2/4
3 | Copy ( & Copy Reverse) Journal Entry | FSM.PP003 | Project Accountant |  | Dave Taylor | Dave.Taylor@idahoptv.org |  |  | MF-020-050 | Conference Room Pilot (In Person) 1/31 - 2/4
4 | Create I/C Journal Entry | FSM.PP004 | Project Accountant |  | Dave Taylor | Dave.Taylor@idahoptv.org |  |  | MF-020-050 | Conference Room Pilot (In Person) 1/31 - 2/4
5 | Create, Release and Journalize Recurring JE | FSM.PP005 | Project Accountant |  | Dave Taylor | Dave.Taylor@idahoptv.org |  |  | MF-020-050 | Conference Room Pilot (In Person) 1/31 - 2/4
6 | Post Journal |  | GL | [5 empty] | MF-020-090 | Conference Room Pilot (In Person) 1/31 - 2/4
7 | Create and Process Retainer Invoice | FSM.PP010 | Project Accountant |  | Dave Taylor | Dave.Taylor@idahoptv.org |  |  | MF-280-030: Grant Billing Processing | Conference Room Pilot (In Person) 1/31 - 2/4 |  | new process
8 | Generate Indirect Burdens | FSM.PP011 | Project Accountant |  | Dave Taylor | Dave.Taylor@idahoptv.org |  |  | DC-040-090 - Apply Overhead Costs | Conference Room Pilot (In Person) 1/31 - 2/4
9 | Delete Indirect Burden | FSM.PP012 | Project Accountant |  | Dave Taylor | Dave.Taylor@idahoptv.org |  |  | DC-040-090 - Apply Overhead Costs | Conference Room Pilot (In Person) 1/31 - 2/4
10 | Journalize Indirect Burden | FSM.PP013 | Project Accountant |  | Dave Taylor | Dave.Taylor@idahoptv.org |  |  | DC-040-090 - Apply Overhead Costs | Conference Room Pilot (In Person) 1/31 - 2/4
11 | Reverse Indirect Burden | FSM.PP014 | Project Accountant |  | Dave Taylor | Dave.Taylor@idahoptv.org |  |  | DC-040-090 - Apply Overhead Costs | Conference Room Pilot (In Person) 1/31 - 2/4
12 | Post Transaction in GL |  | GL | [5 empty] | DC-030-050 - Allocate Indirect Costs | Conference Room Pilot (In Person) 1/31 - 2/4
13 | Journalize IB Projects Transactions | FSM.PP013 | Project Accountant |  | Dave Taylor | Dave.Taylor@idahoptv.org |  |  | DC-030-050 - Allocate Indirect Costs | Conference Room Pilot (In Person) 1/31 - 2/4
14 | Post Transaction in GL |  | GL | [5 empty] | DC-030-050 - Allocate Indirect Costs | Conference Room Pilot (In Person) 1/31 - 2/4
15 | Create, Generate ,Update Certification Number & Date and Journalize Milestone Invoice | FSM.PP020 | Project Accountant |  | Dave Taylor | Dave.Taylor@idahoptv.org |  |  | MF-280-030: Grant Billing Processing | Conference Room Pilot (In Person) 1/31 - 2/4
16 | Create, Generate ,Update Certification Number & Date and Journalize Cost Reimbursement Invoice | FSM.PP021 | Project Accountant |  | Dave Taylor | Dave.Taylor@idahoptv.org |  |  | MF-280-030: Grant Billing Processing | Conference Room Pilot (In Person) 1/31 - 2/4
17 | Generate Mass Contract Invoice w/wo Billing Group, Mass Journalize and Review AR Transaction | FSM.PP022 | Project Accountant |  | Dave Taylor | Dave.Taylor@idahoptv.org |  |  | MF-280-030: Grant Billing Processing | Conference Room Pilot (In Person) 1/31 - 2/4
27 | Process Project Capitalization | FSM.PP040 | Project Accountant |  | Dave Taylor | Dave.Taylor@idahoptv.org |  |  | DC-050-030 - Capitalize Leased Asset | Conference Room Pilot (In Person) 1/31 - 2/4
28 | Contract Balance Adjustments | FSM.PP050 | Project Accountant |  | Dave Taylor | Dave.Taylor@idahoptv.org |  |  | MF-280-021ZZ | Conference Room Pilot (In Person) 1/31 - 2/4
29 | Reverse Indirect Burden | FSM.PP051 | Project Accountant |  | Dave Taylor | Dave.Taylor@idahoptv.org |  |  | DC-040-090 - Apply Overhead Costs | Conference Room Pilot (In Person) 1/31 - 2/4
30 | Delete Invoice | FSM.PP052 | Project Accountant |  | Dave Taylor | Dave.Taylor@idahoptv.org |  |  | MF-280-031ZZ | Conference Room Pilot (In Person) 1/31 - 2/4
31 | Reverse Journalize Invoice | FSM.PP053 | Project Accountant |  | Dave Taylor | Dave.Taylor@idahoptv.org |  |  | MF-280-032ZZ | Conference Room Pilot (In Person) 1/31 - 2/4
32 | New Burden Rate | FSM.PP054 | Project Accountant |  | Dave Taylor | Dave.Taylor@idahoptv.org |  |  | DC-040-091ZZ | Conference Room Pilot (In Person) 1/31 - 2/4
33 | Retainer Adjustment/ Re Applying Retainers | FSM.PP055 | Project Accountant |  | Dave Taylor | Dave.Taylor@idahoptv.org |  |  | MF-280-022ZZ | Conference Room Pilot (In Person) 1/31 - 2/4
34 | Backout & Reallocate FES Transactions | FSM.PP056 | Project Accountant |  | Dave Taylor | Dave.Taylor@idahoptv.org |  |  | MF-020-051ZZ | Conference Room Pilot (In Person) 1/31 - 2/4
35 | Review Partially Billed Transactions | FSM.PP057 | Project Accountant |  | Dave Taylor | Dave.Taylor@idahoptv.org |  |  | MF-280-030: Grant Billing Processing | Conference Room Pilot (In Person) 1/31 - 2/4
36 | Move Project within Structure | FSM.PP059 | Project Accountant |  | Dave Taylor | Dave.Taylor@idahoptv.org |  |  | MF-050-010: Set up Project | Conference Room Pilot (In Person) 1/31 - 2/4
37 | Copy Posting project | FSM.PP060 | Project Accountant |  | Dave Taylor | Dave.Taylor@idahoptv.org |  |  | MF-050-010: Set up Project | Conference Room Pilot (In Person) 1/31 - 2/4
38 | Copy Project Funding Source | FSM.PP061 | Project Accountant |  | Dave Taylor | Dave.Taylor@idahoptv.org |  |  | MF-050-010: Set up Project | Conference Room Pilot (In Person) 1/31 - 2/4
39 | Change SEFA flag | FSM.PP062 | Project Accountant |  | Dave Taylor | Dave.Taylor@idahoptv.org |  |  | MF-050-010: Set up Project | Conference Room Pilot (In Person) 1/31 - 2/4
40 | Change PoP for Specific System Code on a Posting Project | FSM.PP063 | Project Accountant |  | Dave Taylor | Dave.Taylor@idahoptv.org |  |  | MF-050-010: Set up Project | Conference Room Pilot (In Person) 1/31 - 2/4
Note on I5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard

## Asset Management Maintenance
SIT 3 Scenario - Asset Management Maintenance
Agency:
SIT Week - Week 6 - 2/7 - 2/11
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Add Asset Manually | 8521 | 12012 | Asset Analyst | Create, add, transfer, adjust, retire, or dispose of assets, including privileges to run depreciation. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org | Add asset using fund override | MF-040-020-010 | 2022-02-07 | 8:45-9:30 AM
2 | Run Release Assets | 8524 | 12015 | Asset Manager | Manage the process to tract fixed asset activity: create, transfer, and retire fixed assets. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org |  | MF-040-020-020 | 2022-02-07 | 9:30-10AM
3 | Asset Disposal | 8523 | 12014 | Asset Analyst | Create, add, transfer, adjust, retire, or dispose of assets, including privileges to run depreciation. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org |  | MF-040-060-020 | 2022-02-07 | 10-11AM
4 | Asset Reinstatement | 8525 | 12016 | Asset Manager | Manage the process to tract fixed asset activity: create, transfer, and retire fixed assets. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org |  | MF-040-060-060 | 2022-02-07 | 1-1:30PM
5 | Adjust a Released Asset | 8526 | 12013 | Asset Analyst | Create, add, transfer, adjust, retire, or dispose of assets, including privileges to run depreciation. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org |  | MF-040-040-020 | 2022-02-07 | 1:30-2PM
6 | Transfer an Asset | 3173 | 12011 | Asset Analyst | Create, add, transfer, adjust, retire, or dispose of assets, including privileges to run depreciation. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org |  | MF-040-050-020 | 2022-02-07 | 2-2:30PM
7 | Create Mass Adjustment Selection Group | Refer to upload template | 12005 | Asset Analyst | Create, add, transfer, adjust, retire, or dispose of assets, including privileges to run depreciation. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org |  | MF-040-040-010 | 2022-02-08 | 8:45-9:30 AM
8 | Create Mass Disposal Selection Group | Refer to upload template | 12006 | Asset Analyst | Create, add, transfer, adjust, retire, or dispose of assets, including privileges to run depreciation. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org |  | MF-040-060-010 | 2022-02-08 | 9:30-10AM
9 | Create Mass Transfer Selection Group | Refer to upload template | 12007 | Asset Analyst | Create, add, transfer, adjust, retire, or dispose of assets, including privileges to run depreciation. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org |  | MF-040-050-010 | 2022-02-08 | 10-11AM
10 | Perform Mass Asset Adjustment | Refer to upload template | 12008 | Asset Manager | Manage the process to tract fixed asset activity: create, transfer, and retire fixed assets. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org |  | MF-040-040-030 | 2022-02-08 | 1-1:30PM
11 | Perform Mass Asset Disposal | Refer to upload template | 12009 | Asset Manager | Manage the process to tract fixed asset activity: create, transfer, and retire fixed assets. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org |  | MF-040-060-040 | 2022-02-08 | 1:30-2PM
12 | Perform Mass Asset Transfer | Refer to upload template | 12010 | Asset Manager | Manage the process to tract fixed asset activity: create, transfer, and retire fixed assets. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org |  | MF-040-050-030 | 2022-02-08 | 2-2:30PM
13 | Run Released Assets | 8524 | 12017 | Asset Manager | Manage the process to tract fixed asset activity: create, transfer, and retire fixed assets. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org |  | MF-040-070-870 | 2022-02-08 | 2:30-3PM
Note on J5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard

## Project 1.3 Reports and Inquiry
Project closing takes place after project processing generally).
SIT 3 Scenario - Closing Projects
Agency:
SIT 3 Week - Week 6: 2/7 - 2/11 & Week 7: 2/14 - 2/18
Sequence | Script ID | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Project Close | FSM.PC001 | Project Accountant | Create, maintain, and close projects and grants, with billing, receiving, and cost allocations. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org |  | MF-050-090 | 2022-02-15 | 8:45-9:30 AM
2 | Review Project | FSM.PIN001 | Project Accountant | Create, maintain, and close projects and grants, with billing, receiving, and cost allocations. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org |  | DC-030-080 | 2022-02-15 | 9:30-10AM
3 | GL Journal Transaction Detail | FSM.PIN002 | Project Accountant | Create, maintain, and close projects and grants, with billing, receiving, and cost allocations. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org |  | DC-030-080 | 2022-02-15 | 10-10:30 AM
4 | Project Searches - Transactions | FSM.PIN003 | Project Accountant | Create, maintain, and close projects and grants, with billing, receiving, and cost allocations. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org |  | DC-030-080 | 2022-02-15 | 10:30 - 11 AM
5 | View all Contact Invoices & all invoices Lines | FSM.PIN004 | Project Accountant | Create, maintain, and close projects and grants, with billing, receiving, and cost allocations. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org |  | DC-030-080 | 2022-02-15 | 1-1:30PM
6 | Assign Reports | FSM.PRP001 | Project Accountant | Create, maintain, and close projects and grants, with billing, receiving, and cost allocations. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org |  | DC-030-080 | 2022-02-15 | 1:30-2PM
7 | View Project Report | FSM.PRP002 | Project Accountant | Create, maintain, and close projects and grants, with billing, receiving, and cost allocations. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org |  | DC-030-080 | 2022-02-15 | 2-2:30PM
8 | Personalize Report | FSM.PRP003 | Project Accountant | Create, maintain, and close projects and grants, with billing, receiving, and cost allocations. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org |  | DC-030-080 | 2022-02-15 | 2:30-3PM
9 | View Funding Source List | FSM.PRA001 | Project Accountant | Create, maintain, and close projects and grants, with billing, receiving, and cost allocations. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org |  | DC-030-080 | 2022-02-15 | 3 - 3:30 PM
10 | View Project Contract Reports | FSM.PRA002 | Project Accountant | Create, maintain, and close projects and grants, with billing, receiving, and cost allocations. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org |  | DC-030-080 | 2022-02-15 | 3:30 - 4 PM
11 | View Payables Reports | FSM.PRA003 | Financials Viewer |  | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org |  | DC-030-080 | 2022-02-16 | 8:45-9:30 AM
12 | View Budget Reports | FSM.PRA004 | Project Accountant | Create, maintain, and close projects and grants, with billing, receiving, and cost allocations. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org |  | DC-030-080 | 2022-02-16 | 9:30-10AM
13 | View Receivables Reports | FSM.PRA005 | Financials Viewer |  | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org |  | DC-030-080 | 2022-02-16 | 10-10:30 AM
14 | View d/EPM Dashboard Reports | FSM.PBI001 | Project Accountant | Create, maintain, and close projects and grants, with billing, receiving, and cost allocations. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org |  | DC-030-080 | 2022-02-16 | 10-10:30 AM
Note on I5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard

## Procure to Pay Vendor Mgt Voids
SIT 3 Scenario - Procure to Pay with Void and Vendor Update
Agency:
SIT Week - Week 7 - 2/14 -2/18
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | Luma Role (role switcher) | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Create Requisition - Special | 8324 | Requester | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org |  | PR-020-010 | 2022-02-14 | 8:45-9:30 AM
2 | Approve Requisition | 8539 | Approver | Assigned Agency | Dave Taylor | Dave.Taylor@idahoptv.org | Requisition not approved | PR-010-060 | 2022-02-14 | 9:30-10AM
3 | Create Purchase Order | 8170 | Buyer | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org |  | PR-050-040 | 2022-02-14 | 10-10:30 AM
4 | Receive Purchase Order | 4587 | Receiver | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org |  | PR-050-070 | 2022-02-14 | 10:30 - 11 AM
5 | Create Invoice | 11519 | Payables Invoice Processor | Assigned Agency | Debbie Siddoway | debbie.siddoway@idahoptv.org |  | MF-070-050 Enter a PO Invoice | 2022-02-14 | 1-1:30PM
6 | Approve Invoice | 11520 | Approver | Assigned Agency | Dave Taylor | Dave.Taylor@idahoptv.org |  | MF-070-056 Invoice Approval Process | 2022-02-14 | 1:30-2PM
7 | Match Invoice | 11458 | Payables Manager | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org |  | MF-070-070 Match Invoices | 2022-02-14 | 2-2:30PM
8 | Process Payment for Invoice | 11442 | Payables Manager | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org |  | MF-070-100 Process Invoice Payments | 2022-02-14 | 2:30-3PM
9 | Journalize | 11440 | Payables Manager |  | Michelle Koehler | michelle.koehler@idahoptv.org |  | MF-070-110 Journalize AP Distributions | 2022-02-14 | 3 - 3:30 PM
10 | Void Payment | 12080 | Cash Accountant | SCO | Michelle Koehler | michelle.koehler@idahoptv.org |  | MF-200-060 Void Cash Transactions | 2022-02-14 | 3:30 - 4 PM
11 | Cancel Invoice | 11523 | Payables Manager | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org |  | MF-070-050 Enter a PO Invoice | 2022-02-15 | 8:45-9:30 AM
12 | Request a new vendor | 11524 | Payables Invoice Processor | Assigned Agency | Debbie Siddoway | debbie.siddoway@idahoptv.org |  | PR-040-030 Create and Maintain Vendor | 2022-02-15 | 9:30-10AM
13 | Approve and setup new vendor | 11525 - Only SCO staff can do this | Approver | SCO | Dave Taylor | Dave.Taylor@idahoptv.org | Disapprove vendor | PR-040-030 Create and Maintain Vendor | 2022-02-15 | 10-10:30 AM
14 | Create Invoice | 11519 | Payables Invoice Processor | Assigned Agency | Debbie Siddoway | debbie.siddoway@idahoptv.org |  | MF-070-050 Enter a PO Invoice | 2022-02-15 | 10:30 - 11 AM
15 | Approve Invoice | 11520 | Approver | Assigned Agency | Dave Taylor | Dave.Taylor@idahoptv.org |  | MF-070-056 Invoice Approval Process | 2022-02-15 | 1-1:30PM
16 | Match Invoice | 11522 | Payables Invoice Processor | Assigned Agency | Debbie Siddoway | debbie.siddoway@idahoptv.org |  | MF-070-070 Match Invoices | 2022-02-15 | 1:30-2PM
17 | Process Payment for Invoice | 11442 | Payables Manager | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org |  | MF-070-100 Process Invoice Payments | 2022-02-15 | 2-2:30PM
18 | Post Transactions - Journalize | 11440 | Payables Manager | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org |  | MF-070-110 Journalize AP Distributions | 2022-02-15 | 2:30-3PM
19 | Cash Ledger Journalize | 12079 | Cash Manager | Assigned Agency | Dave Taylor | Dave.Taylor@idahoptv.org |  | MF-200-050 Reconcile Payments Payables and Disbursements | 2022-02-15 | 3 - 3:30 PM
20 | Verify Voided Payables Checks | 12153 | Cash Accountant | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org |  | MF-200-060 Void Cash Transactions | 2022-02-15 | 3:30 - 4 PM
21 | View Fund Balance | Cash Fund Balance.xlsx (in ALM?)(in Cash Deposit to Revenue Scenario) | Cash Accountant | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org |  | MF-200-050 Reconcile Payments Payables and Disbursements | 2022-02-16 | 8:45-9:30 AM
22 | Comparative report from Birst |  | Cash Accountant | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org |  | MF-200-ZZ | 2022-02-16 | 9:30-10AM
23 | Cash Revenue Daily Report - Birst |  | Cash Manager | Assigned Agency | Dave Taylor | Dave.Taylor@idahoptv.org |  | MF-200-ZZ | 2022-02-16 | 10-10:30 AM
Note on H5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard

## Global Ledger Entries and Analy
SIT 3 Scenario - Global Legder Processing and Analysis
Agency:
SIT Week - Week 8 - 2/21/ - 2/25
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Create a Front-End Split Journal Entry (Front End Split Projects Only) | Refer to Upload Template | 12154 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org | May also be performed by CFO or Controller (SCO) | MF-020-010 | 2022-02-23 | 8:45-9:30 AM
2 | Create a Journal Entry | Refer to Upload Template | 11668 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org | May also be performed by CFO or Controller (SCO) | MF-020-010 | 2022-02-23 | 9:30-10AM
3 | Approve a Journal Entry | Refer to Upload Template | 11669 | Approver | Approve transactions such as requisitions, purchase orders, solicitation & journal entries. | Assigned Agency | Dave Taylor | Dave.Taylor@idahoptv.org |  | MF-025-060 | 2022-02-23 | 10-11AM
4 | Create a Journal Entry from an Existing Journal | Refer to Upload Template | 11671 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org | May also be performed by CFO or Controller (SCO) | MF-020-010 | 2022-02-23 | 1-1:30PM
5 | Create a Journal Entry from a Template | Refer to Upload Template | 11670 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org | May also be performed by CFO or Controller (SCO) | MF-020-010 | 2022-02-23 | 1:30-2PM
6 | Create a Recurring Journal | Refer to Upload Template | 11673 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org | May also be performed by CFO or Controller (SCO) | MF-020-020 | 2022-02-23 | 2-2:30PM
7 | Journalize a Recurring Journal Entry | Refer to Upload Template | 12155 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org | May also be performed by CFO or Controller (SCO) | MF-020-030 | 2022-02-23 | 2:30-3PM
8 | Post Multiple Journal Entries | Refer to Upload Template | 12156 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-23 | 3-3:30PM
9 | Post Journals from Subsystems | Refer to Upload Template | 12157 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org | May also be performed by CFO or Controller (SCO) | MF-020-050 | 2022-02-24 | 8:45-9:30 AM
10 | Validate (here) Reconcile (close) Subsystems to the General Ledger | Bill will put these scripts here and in close scenario | TBD | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-24 | 9:30-10AM
11 | Analyze Global Ledger Totals | Refer to Upload Template | 12158 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-24 | 10-11AM
12 | Perform Account Analysis | Refer to Upload Template | 11672 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-24 | 1-1:30PM
13 | Perform Fund Analysis | Refer to Upload Template | 12159 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-24 | 1:30-2PM
14 | Perform Organizational Unit Analysis | Refer to Upload Template | 12160 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-24 | 2-2:30PM
15 | View Transactions by Entity-Account | Refer to Upload Template | 11674 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-25 | 9- 9:30 AM
16 | BIRST/BI/CSF Analytic Reporting |  | TBD | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-25 | 9:30 - 10 AM
17 | Evaluate Encumbrances | Placeholder - Judy and Bill (and Eileen/Cathy) are working on script for this; will have this week (12/23/21) | TBD | Staff Accountant |  | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-25 | 10 - 11 AM
Note on J5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard

## Punchout Request to Payment
SIT 3 Scenario - Punchout Request to Payment
Agency:
SIT Week - Week 8 - 2/21 - 2/25
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Create Punchout Requisition using RSS | 3501 | 11924 | Requester | Determines requirements & cost estimates for purchase of goods & services. Submits purchase requisition. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org |  | PR-020-010 | 2022-02-22 | 8:45-9:30 AM
2 | Approve Requisition | 8539 | 11925 | Approver | Approve transactions such as requisitions, purchase orders, solicitation & journal entries. | Assigned Agency | Dave Taylor | Dave.Taylor@idahoptv.org | Deny Requisition - add note - need more information Approve Requisition | PR-010-060 | 2022-02-22 | 9:30-10AM
3 | Locate Punchout PO | Refer to Upload template | 12034 | Requester |  |  | Michelle Koehler | michelle.koehler@idahoptv.org |  | PR-050-040 | 2022-02-22 | 10-11AM
4 | Review Punchout PO | Refer to Upload template | 11927 | Buyer | Review requisitions & create purchase orders. Conduct market research & monitor vendor commitments. Approve vendor returns. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org | This will be a review of schedule job creating PO. Other variations would be manual creation, or Job run creation submitted as needed. | PR-050-040 | 2022-02-22 | 1-1:30PM
5 | Review Punchout Receipt | Refer to Upload template | 11928 | Receiver | Receive and inspect incoming goods. Pick items for shipment/transfer. Dispose of items. Vendor returns. Document variances. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org | Manual release of receipt vs. auto release | PR-050-070 | 2022-02-22 | 1:30-2PM
6 | Review Punchout Invoice | 11610 | 11922 | Payables Invoice Processor | Processes interface and XM files. Match Payables invoices. Manages vendor list. Processes Payables payments. Generates 1099. | Assigned Agency | Debbie Siddoway | debbie.siddoway@idahoptv.org |  | MF-070-050 Enter a PO Invoice | 2022-02-22 | 2-2:30PM
7 | Approve Invoice | 11611 | 11923 | Approver |  |  | Dave Taylor | Dave.Taylor@idahoptv.org |  | MF-070-056 Invoice Approval Process | 2022-02-22 | 2:30-3PM
8 | Match Invoice | 11613 | 11926 | Payables Manager | Void & cancel payments, reissue & mail warrants. Process period close. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org |  | MF-070-070 Match Invoices | 2022-02-22 | 3-3:30PM
9 | Process Invoice for Payment | 11442 | 11921 | Payables Manager | Void & cancel payments, reissue & mail warrants. Process period close. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org |  | MF-070-100 Process Invoice Payments | 2022-02-22 | 3:30 - 4 PM
Note on J5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard

## Chart of Accounts Maintenance
SIT 3 Scenario - Chart of Accounts Maintenance
Agency:
SIT Week - Week 10 - 3/7 - 3/11
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | View and Validate an Organizational Unit |  | TBD | Staff Accountant |  |  | Michelle Koehler | michelle.koehler@idahoptv.org |  |  | 2022-03-07 | 8:45-9:30 AM
2 | View and Validate a Project |  | TBD | Staff Accountant |  |  | Michelle Koehler | michelle.koehler@idahoptv.org |  |  | 2022-03-07 | 9:30-10AM
3 | View and Validate a Program |  | TBD | Staff Accountant |  |  | Michelle Koehler | michelle.koehler@idahoptv.org |  |  | 2022-03-07 | 10-11AM
4 | View and Validate a Location |  | TBD | Staff Accountant |  |  | Michelle Koehler | michelle.koehler@idahoptv.org |  |  | 2022-03-07 | 1-1:30PM
5 | View and Validate Additional Reporting |  | TBD | Staff Accountant |  |  | Michelle Koehler | michelle.koehler@idahoptv.org |  |  | 2022-03-07 | 1:30-2PM
6 | View and Validate Custodial Accounts (CAM) |  | TBD | Staff Accountant |  |  | Michelle Koehler | michelle.koehler@idahoptv.org |  |  | 2022-03-07 | 2-2:30PM
7 | Request a new account |  | TBD | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org |  |  | 2022-03-07 | 2:30-3PM
8 | Request a new organizational unit |  | TBD | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Michelle Koehler | michelle.koehler@idahoptv.org |  |  | 2022-03-07 | 3-3:30PM
9 | View and Validate Beginning Balances |  | TBD | Staff Accountant |  |  | Michelle Koehler | michelle.koehler@idahoptv.org |  |  | 2022-03-08 | 8:45-9:30 AM
10 | Update Summary Conversion Balances to Detail |  | TBD | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. |  | Michelle Koehler | michelle.koehler@idahoptv.org |  |  | 2022-03-08 | 9:30-10AM
Note on J5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard