## SIT 3 Listing & Schedule
SIT 3 End to End Scenarios | SIT 3 Scheduled Week | 955 - Health District 5 (SOUTH CENTRAL)
Inventory Management Cycle | Week 4: 1/24 - 1/28
Pcard End to End Process | Week 4: 1/24 - 1/28
Project Processing (RQ, PO, Contract, INV) | Week 4: 1/24 - 1/28 | X
XM Pcard NO Cash Advance | Week 4: 1/24 - 1/28
XM Pcard WITH Cash Advance | Week 4: 1/24 - 1/28
Payroll End to End | Week 4: 1/24 - 1/28
Fixed Asset Acquire to Retire | Week 5: 1/31 - 2/4 | X
Statewide Contract Procure to Pay | Week 5: 1/31 - 2/4 | X
GHR Shell | Week 5: 1/31 - 2/4
Project 1.1 Project Setup and Maintanance | Week 5: 1/31 - 2/4 | X
Project 1.2 Project Processing Master (P&G only) | Week 5: 1/31 - 2/4 | X
AR Credit Monitoring | Week 7: 2/14 - 2/18
Asset Management Maintenance | Week 6: 2/7 - 2/11
Service Contract Interagency Billing | Week 6: 2/7 - 2/11
Project 1.3 Reports and Inquiry Master | Week 6: 2/7 - 2/11 & Week 7: 2/14 - 2/18 | X
Cash Ledger Payment | Week 7: 2/14 - 2/18 | X
Interagency Billing to Settlement | Week 7: 2/14 - 2/18 | X
Non-State Billing | Week 6: 2/7 - 2/11
Procure to Pay Vendor Management Voids | Week 7: 2/14 - 2/18 | X
Vendor Refunds | Week 7: 2/14 - 2/18
Cash Management Deposit to Revenue | Week 8: 2/21 - 2/25
Custodial Accounts Setup | Week 8: 2/21 - 2/25
Global Ledger Entries and Analysis | Week 8: 2/21 - 2/25 | X
Punchout Request to Payment | Week 8: 2/21 - 2/25 | X
Tax Refunds | Week 8: 2/21 - 2/25
Allocations | Week 9: 2/28 - 3/4 | X
Budget | Week 9: 2/28 - 3/4
Custodial Accounts Transaction Processing | Week 9: 2/28 - 3/4
Month End/Year End | Week 9: 2/28 - 3/4
Define and Generate Recurring Invoices | Week 9: 2/28 - 3/4
Chart of Accounts Maintenance | Week 10: 3/7 - 3/11 | X
3rd Party Allocations | TBD

## Instructions
Luma System Integration Testing 3 (SIT 3) Instructions
Agency Functional Testing Dates | January 24 - March 11, 2022 Testing Schedule: Monday -Thursday 8:45 -11 am and 1:45 - 4:00 pm, Friday 9:00 - 11:00 am
Agency Testers Roles and Responsibilities | 1. Execute test scripts per SIT 3 schedule. 2. Review actual results against expected results. 3. Log defects as needed. 4. Retest failed test results to resolve defects. 5. Launch integrations during test cycle per schedule.
Testing Packet | 1. Test Scenario Excel File: Cover Page, Instruction Tab, Scenario Listing, Tab with each steps script detailed instruction to execute the script. 2. Data Sheets. 3. Email Template to use to report your testing results.
Testing Steps | 1. If you are the first step in the scenario, you may begin execution according to the the Date and Time in the Testing packet. If you are not on step 1, please wait for the step before you to complete their script and you receive communication to begin. 2. Execute assigned script(s) using the testing script and data sheet that was provided to you. 3. Sending Testing results via email using to the Test Management Team. (attached email sample) 4. Communicate to the next tester they can begin their script. (Slack or Email works)
What should you do if there are issues or you need assistance while testing? | 1. The Test Management Team will host an all-day SIT 3 Testing Support Hotline (WebEx Meeting). 2. Attendance is optional for SIT testers and testers should only join if they have questions or issues regarding SIT testing. 3. Testers should have an invite on their calendar that includes the WebEx Link.
How to submit a SIT 3 Testing Defect using ServiceNow: | 1. Visit https://auth.sco.idaho.gov/ in your web browser. Google Chrome and Microsoft Edge are recommended. 2. Enter your State ID number as the username and your password. Click the Sign In button. 3. You will be presented with a second page for Multi-Factor Authentication. Select an option and acknowledge the push or call, or enter a passcode from your Duo app. 4. You will see several buttons on your Enterprise Dashboard. One of these will be labeled Service Desk. This button will take you to the Service Portal. 5. There are four main buttons across the center of the page. Click Service Requests to be taken to the service menu. 7. Locate and select LUMA SIT3 Testing Issue from the options listed. 6. Select the SCO IT Services category from the list on the left side of the page. 7. Fill out form with Primary Contact, Short Description, Description, Category, Scenario Name, Script ID, add attachments/screenshots and submit the ticket.
What to do if there is a system outage? | 1. Please join the Testing Support Hotline if you run into any issues with the system and notify the meeting moderator of the issue. 2. If there is a system outage, the Test Management Team will work with the Communications team to notify Agency Testers.

## Email Submission Template
Click on Icon Below to Outlook Email Template

## Project Processing
SIT 3 Scenario - Project Procurement Processing
Agency:
SIT Week - Week 4 - 1/24 - 1/28
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Create RSS Requisition for a Project Item | 2968 | 12522 | Requester | Determines requirements & cost estimates for purchase of goods & services. Submits purchase requisition. | Assigned Agency | Lorna Meter | lmeter@phd5.idaho.gov |  | PR-020-010 | 2022-01-25 | 8:45-9:30 AM
2 | Approve Requisition | 8539 | 12528 | Approver | Approve transactions such as requisitions, purchase orders, solicitations, and journal entries. | Assigned Agency | Jeremy St Clair & Melody Bowyer | jstclair@phd5.idaho.gov & mbowyer@phd5.idaho.gov |  | PR-010-060 | 2022-01-25 | 9:30-10AM
3 | Create a Purchase Order | 8169 | 12523 | Buyer | Review requisition and create purchase orders. Conduct market research, and monitor vendor commitments. Approve vendor returns. | Assigned Agency | Lorna Meter | lmeter@phd5.idaho.gov |  | PR-050-040 | 2022-01-25 | 10-11AM
4 | Create a Receipt | 4581 | 12532 | Receiver | Receive and inspect incoming goods. Pick items for shipment/transfer. Dispose of items. Conduct vendor returns. Document variances. | Assigned Agency | Lorna Meter | lmeter@phd5.idaho.gov | Receiving Messages | PR-050-070 | 2022-01-25 | 1-1:30PM
5 | Create Contract (Sub-Award) with Service Lines | 7219 | 12533 | Contract Manager | Compile contract file, including entering contract line-item details, terms & conditions, and pricing, and amends and renews contracts. | Assigned Agency | Trish Larsen Smith | tlarsen@phd5.idaho.gov | First Line = $25,000 Second line = Remainder of the Sub-Award | PR-040-010 | 2022-01-25 | 1:30-2PM
6 | Create Contract - Contract Draft - Articles Tab | 7204 | 12531 | Contract Manager | Compile contract file, including entering contract line-item details, terms & conditions, and pricing, and amends and renews contracts. | Assigned Agency | Trish Larsen Smith | tlarsen@phd5.idaho.gov |  | PR-040-010 | 2022-01-25 | 2-2:30PM
7 | Create Contract - Contract Draft - Participants Tab | 2667 | 12537 | Contract Manager | Compile contract file, including entering contract line-item details, terms & conditions, and pricing, and amends and renews contracts. | Assigned Agency | Trish Larsen Smith | tlarsen@phd5.idaho.gov |  | PR-040-010 | 2022-01-25 | 2:30-3PM
8 | Create Contract - Contract Draft - Lines Tab - Service | 3375 | 12536 | Contract Manager | Compile contract file, including entering contract line-item details, terms & conditions, and pricing, and amends and renews contracts. | Assigned Agency | Trish Larsen Smith | tlarsen@phd5.idaho.gov |  | PR-040-010 | 2022-01-25 | 3-3:30PM
9 | Create Contract - Contract Draft - Contacts Tab | 3335 | 12534 | Contract Manager | Compile contract file, including entering contract line-item details, terms & conditions, and pricing, and amends and renews contracts. | Assigned Agency | Trish Larsen Smith | tlarsen@phd5.idaho.gov |  | PR-040-010 | 2022-01-26 | 8:45-9:30 AM
10 | Create Contract - Contract Draft - Releasing a Contract | 7203 | 12530 | Contract Manager | Compile contract file, including entering contract line-item details, terms & conditions, and pricing, and amends and renews contracts. | Assigned Agency | Trish Larsen Smith | tlarsen@phd5.idaho.gov |  | PR-040-010 | 2022-01-26 | 9:30-10AM
12 | Contract Approval | 8353 | 12524 | Approver | Approve transactions such as requisitions, purchase orders, solicitations, and journal entries. | Assigned Agency | Jeremy St Clair & Melody Bowyer | jstclair@phd5.idaho.gov & mbowyer@phd5.idaho.gov |  | PR-040-010 | 2022-01-26 | 1-1:30PM
11 | Create Contract - Contract Draft - Activating a Contract | 7202 | 12540 | Contract Manager | Compile contract file, including entering contract line-item details, terms & conditions, and pricing, and amends and renews contracts. | Assigned Agency | Trish Larsen Smith | tlarsen@phd5.idaho.gov |  | PR-040-010 | 2022-01-26 | 10-11AM
13 | Create Requisition - Service Lines from Contract (Sub-Award) | 8323 | 12529 | Requester | Determines requirements & cost estimates for purchase of goods & services. Submits purchase requisition. | Assigned Agency | Lorna Meter | lmeter@phd5.idaho.gov |  | PR-010-060 | 2022-01-26 | 1:30-2PM
14 | Approve Requisition | 8539 | 12539 | Approver | Approve transactions such as requisitions, purchase orders, solicitations, and journal entries. | Assigned Agency | Jeremy St Clair & Melody Bowyer | jstclair@phd5.idaho.gov & mbowyer@phd5.idaho.gov |  | PR-020-020 | 2022-01-26 | 2-2:30PM
15 | Create a Purchase Order | 2753 | 12538 | Buyer | Review requisition and create purchase orders. Conduct market research, and monitor vendor commitments. Approve vendor returns. | Assigned Agency | Lorna Meter | lmeter@phd5.idaho.gov |  | PR-050-040 | 2022-01-26 | 2:30-3PM
16 | Create Invoice | 11374 | 12525 | Payables Invoice Processor | Process interface and XM files. Match payables invoices, and vendor list. Process payables payments. Generate 1099. | Assigned Agency | Lorna Meter | lmeter@phd5.idaho.gov |  | MF-070-050 Enter a PO Invoice | 2022-01-26 | 3-3:30PM
17 | Approve Invoice | 11375 | 12527 | Approver | Approve transactions such as requisitions, purchase orders, solicitations, and journal entries. | Assigned Agency | Trish Larsen Smith, Jeremy St Clair, Melody Bowyer | tlarsen@phd5.idaho.gov, mbowyer@phd5.idaho.gov, tlarsen@phd5.idaho.gov |  | MF-070-056 Invoice Approval Process | 2022-01-26 | 3:30 -4 PM
18 | Match Invoice | 11457 | 12535 | Payables Manager | Void & cancel payments. Reissue & mail warrants. Process period close. | Assigned Agency | Trish Larsen Smith | tlarsen@phd5.idaho.gov |  | MF-070-070 Match Invoices | 2022-01-27 | 8:45-9:30 AM
19 | Process Payment for Invoice | 11442 | 12526 | Payables Manager | Void & cancel payments. Reissue & mail warrants. Process period close. | Assigned Agency | Trish Larsen Smith | tlarsen@phd5.idaho.gov |  | MF-070-100 Process Invoice Payments | 2022-01-27 | 9:30-10AM
Note on J4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard

## Fixed Assets Acquire To Retire
SIT 3 Scenario - Acquire Fixed Asset to Retire
Agency:
SIT 3 Week - Week 5 - 1/31-2/4
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | NEW SIT 3 ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Create Fixed Asset Requisition | 3041 | 11563 | Requester | Determines requirements & cost estimates for purchase of goods & services. Submits purchase requisition. | Assigned Agency | Lorna Meter | lmeter@phd5.idaho.gov | Associate with project | PR-010-060 | 2022-01-31 | 8:45-9:30 AM
2 | Approve Requisition | 8539 | 11564 | Approver | Approve transactions such as requisitions, purchase orders, solicitations, and journal entries. | Assigned Agency | Jeremy St Clair & Melody Bowyer | jstclair@phd5.idaho.gov & mbowyer@phd5.idaho.gov | Deny Requisition - add note - need more information Approve Requisition | PR-020-020 | 2022-01-31 | 9:30-10AM
3 | Identify Requistions to send to Sourcing Event | 2896 | 11565 | Buyer | Review requisition and create purchase orders. Conduct market research, and monitor vendor commitments. Approve vendor returns. | Assigned Agency | Lorna Meter | lmeter@phd5.idaho.gov |  | PR-030-020 | 2022-01-31 | 10-11AM
4 | Create Sourcing Event RFQ | 7186 | 11566 | Sourcing Manager | Create souring events, evaluate supplier responses, and oversee selection & award of sourcing events. | Assigned Agency | Robert Moulson | bmoulson@phd5.idaho.gov |  | PR-030-030 | 2022-01-31 | 1-1:30PM
5 | Approve Sourcing Event to Post | 8439 | 11567 | Approver | Approve transactions such as requisitions, purchase orders, solicitations, and journal entries. | Assigned Agency | Jeremy St Clair & Melody Bowyer | jstclair@phd5.idaho.gov & mbowyer@phd5.idaho.gov | Approve/Deny/Reject Sourcing Event to Post | PR-030-010 | 2022-01-31 | 1:30-2PM
6 | Enter A Manual response | 7187 | 11568 | Sourcing Manager | Develop/oversee supplier list; monitor & evaluate vendors. Evaluate proposals; create souring events, oversee selection & award contracts. | Assigned Agency | Robert Moulson | bmoulson@phd5.idaho.gov |  | PR-030-050 | 2022-01-31 | 2-2:30PM
7 | Analyze and Award an Event to Contract | 7189 | 11569 | Sourcing Manager | Develop/oversee supplier list; monitor & evaluate vendors. Evaluate proposals; create souring events, oversee selection & award contracts. | Assigned Agency | Robert Moulson | bmoulson@phd5.idaho.gov | Split Award by Line | PR-030-050 | 2022-01-31 | 2:30-3PM
8 | Sourcing Event Award Approval | 8440 | 11570 | Approver | Approve transactions such as requisitions, purchase orders, solicitations, and journal entries. | Assigned Agency | Jeremy St Clair & Melody Bowyer | jstclair@phd5.idaho.gov & mbowyer@phd5.idaho.gov | Approve/Deny/Reject | PR-030-050 | 2022-01-31 | 3-3:30PM
9 | Create Contract - Create a Contract - Contract Tab | 7219 | 11571 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | Assigned Agency | Trish Larsen Smith | tlarsen@phd5.idaho.gov |  | PR-040-010 | 2022-02-01 | 8:45 - 10:30AM
10 | Create Contract - Contract Draft - Articles Tab | 7204 | 11572 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | Assigned Agency | Trish Larsen Smith | tlarsen@phd5.idaho.gov |  | PR-040-010 | 2022-02-01 | 8:45 - 10:30AM
11 | Create Contract - Contract Draft - Participants Tab | 2667 | 11573 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | Assigned Agency | Trish Larsen Smith | tlarsen@phd5.idaho.gov |  | PR-040-010 | 2022-02-01 | 8:45 - 10:30AM
12 | Create Contract - Contract Draft - Lines Tab - Special | 8909 | 11574 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | Assigned Agency | Trish Larsen Smith | tlarsen@phd5.idaho.gov |  | PR-040-010 | 2022-02-01 | 8:45 - 10:30AM
13 | Create Contract - Contract Draft - Contacts Tab | 3335 | 11575 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | Assigned Agency | Trish Larsen Smith | tlarsen@phd5.idaho.gov |  | PR-040-010 | 2022-02-01 | 8:45 - 10:30AM
14 | Create Contract - Contract Draft - Releasing a Contract | 7203 | 11576 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | Assigned Agency | Trish Larsen Smith | tlarsen@phd5.idaho.gov |  | PR-040-010 | 2022-02-01 | 8:45 - 10:30AM
16 | Contract Approval | 8353 | 11578 | Approver | Approve transactions such as requisitions, purchase orders, solicitation & journal entries. | Assigned Agency | Jeremy St Clair & Melody Bowyer | jstclair@phd5.idaho.gov & mbowyer@phd5.idaho.gov | Approve/Deny/Reject | PR-040-010 | 2022-02-01 | 10:30-11AM
15 | Create Contract - Contract Draft - Activating a Contract | 7202 | 11577 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | Assigned Agency | Trish Larsen Smith | tlarsen@phd5.idaho.gov |  | PR-040-010 | 2022-02-01 | 8:45 - 10:30AM
17 | Create Fixed Asset Requisition | 3041 | 11579 | Requester | Determines requirements & cost estimates for purchase of goods & services. Submits purchase requisition. | Assigned Agency | Lorna Meter | lmeter@phd5.idaho.gov |  | PR-010-060 | 2022-02-01 | 1-1:30PM
18 | Approve Requisition | 8539 | 11580 | Approver | Approve transactions such as requisitions, purchase orders, solicitations, and journal entries. | Assigned Agency | Jeremy St Clair & Melody Bowyer | jstclair@phd5.idaho.gov & mbowyer@phd5.idaho.gov |  | PR-020-020 | 2022-02-01 | 1:30-2PM
19 | Create Purchase Order | 2753 | 11581 | Buyer | Review requisition and create purchase orders. Conduct market research, and monitor vendor commitments. Approve vendor returns. | Assigned Agency | Lorna Meter | lmeter@phd5.idaho.gov |  | PR-050-040 | 2022-02-01 | 2-2:30PM
20 | Receive Purchase Order | 2178 | 11582 | Receiver | Receive and inspect incoming goods. Pick items for shipment/transfer. Dispose of items. Conduct vendor returns. Document variances. | Assigned Agency | Lorna Meter | lmeter@phd5.idaho.gov | Receive less/more than ordered | PR-050-070 | 2022-02-01 | 2:30-3PM
21 | Inspect Item | 2181 | 11583 | Receiver | Receive and inspect incoming goods. Pick items for shipment/transfer. Dispose of items. Conduct vendor returns. Document variances. | Assigned Agency | Lorna Meter | lmeter@phd5.idaho.gov | Inspection Failed, Vendor Return | PR-050-070 | 2022-02-01 | 3-3:30PM
22 | Create Invoice | 11447 | 11584 | Payables Invoice Processor | Process interface and XM files. Match payables invoices, and vendor list. Process payables payments. Generate 1099. | Assigned Agency | Lorna Meter | lmeter@phd5.idaho.gov |  | MF-070-050 Enter a PO Invoice | 2022-02-02 | 8:45-9:30 AM
23 | Approve Invoice | 11448 | 11585 | Approver | Approve transactions such as requisitions, purchase orders, solicitations, and journal entries. | Assigned Agency | Trish Larsen Smith, Jeremy St Clair, Melody Bowyer | tlarsen@phd5.idaho.gov, mbowyer@phd5.idaho.gov, tlarsen@phd5.idaho.gov |  | MF-070-056 Invoice Approval Process | 2022-02-02 | 9:30-10AM
24 | Match Invoice | 11455 | 11586 | Payables Manager | Void & cancel payments. Reissue & mail warrants. Process period close. | Assigned Agency | Trish Larsen Smith | tlarsen@phd5.idaho.gov |  | MF-070-070 Match Invoices | 2022-02-02 | 10-10:30AM
25 | Process Payment for Invoice | 11442 | 11587 | Payables Manager | Void & cancel payments. Reissue & mail warrants. Process period close. | Assigned Agency | Trish Larsen Smith | tlarsen@phd5.idaho.gov |  | MF-070-100 Process Invoice Payments | 2022-02-02 | 10:30-11AM
26 | Interface AP Asset to Asset Management | 2713 | 11900 | Asset Analyst | Create, add, transfer, adjust, retire, or dispose of assets, including privileges to run depreciation. | Assigned Agency | Lorna Meter | lmeter@phd5.idaho.gov |  | MF-040-030-010 | 2022-02-02 | 1-1:30PM
27 | Run Release Assets - Update | 8524 | 11905 | Asset Analyst | Create, add, transfer, adjust, retire, or dispose of assets, including privileges to run depreciation. | Assigned Agency | Lorna Meter | lmeter@phd5.idaho.gov | Associate with project | MF-040-030-020 | 2022-02-02 | 1:30-2PM
28 | Run Depreciation | 8522 | 11904 | Asset Manager | Manage the process to tract fixed asset activity: create, transfer, and retire fixed assets. | Assigned Agency | Jeremy St Clair | jstclair@phd5.idaho.gov |  | MF-040-070-020 | 2022-02-02 | 2-2:30PM
29 | Review Fixed Asset GL Account Transactions |  |  | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate, and update allocations. | Assigned Agency | Trish Larsen Smith | tlarsen@phd5.idaho.gov |  | MF-020-010 | 2022-02-02 | 2:30-3PM
30 | Asset Surplus Disposal | 11062 | 11902 | Asset Analyst | Create, add, transfer, adjust, retire, or dispose of assets, including privileges to run depreciation. | Assigned Agency | Lorna Meter | lmeter@phd5.idaho.gov | Transfer, retire | MF-040-060-020 | 2022-02-02 | 3-3:30PM
31 | Approve Disposal | 11263 | 11903 | Asset Manager | Manage the process to tract fixed asset activity: create, transfer, and retire fixed assets. | Assigned Agency | Jeremy St Clair | jstclair@phd5.idaho.gov | Transfer | MF-040-060-020 | 2022-02-02 | 3:30-4PM
32 | Close Contract | 2636 | 11901 | Contract Manager | Compile contract file, including entering contract line-item details, terms & conditions, and pricing, and amends and renews contracts. | Assigned Agency | Trish Larsen Smith | tlarsen@phd5.idaho.gov |  | PR-050-030 | 2022-02-03 | 8:45-9:30 AM
Note on J5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard

## Statewide Contract Procure to P
SIT 3 Scenario - Statewide Contract Procure to Pay
Agency:
SIT 3 Week - Week 5 - 1/31-2/4
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Create Contract with Rebate and Price Breaks Statewide for Envelopes - Create a Contract (Contract Tab) | 7219 | 11992 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | DOP | Trish Larsen Smith | tlarsen@phd5.idaho.gov |  | PR-040-020 | 2022-01-31 | 8:45 - 11 AM
2 | Create Contract with Rebate and Price Breaks Statewide for Envelopes - Contract Draft (Articles) | 7204 | 11987 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | DOP | Trish Larsen Smith | tlarsen@phd5.idaho.gov |  | PR-040-020 | 2022-01-31 | 8:45 - 11 AM
3 | Create Contract with Rebate and Price Breaks Statewide for Envelopes - Contract Draft - Participants | 2667 | 11997 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | DOP | Trish Larsen Smith | tlarsen@phd5.idaho.gov |  | PR-040-020 | 2022-01-31 | 8:45 - 11 AM
4 | Create Contract with Rebate and Price Breaks Statewide for Envelopes - Contract Draft - Lines - Special | 8909 | 11995 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | DOP | Trish Larsen Smith | tlarsen@phd5.idaho.gov |  | PR-040-020 | 2022-01-31 | 8:45 - 11 AM
5 | Create Contract with Rebate and Price Breaks Statewide for Envelopes - Contract Draft - Lines - Purchase Type Detail - Purchase Pricing | 2663 | 11996 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | DOP | Trish Larsen Smith | tlarsen@phd5.idaho.gov |  | PR-040-020 | 2022-01-31 | 8:45 - 11 AM
6 | Create Contract with Rebate and Price Breaks Statewide for Envelopes - Contract Draft - Rebates | 2671 | 11998 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | DOP | Trish Larsen Smith | tlarsen@phd5.idaho.gov |  | PR-040-020 | 2022-01-31 | 8:45 - 11 AM
7 | Create Contract with Rebate and Price Breaks Statewide for Envelopes - Contract Draft - Contacts | 3335 | 11993 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | DOP | Trish Larsen Smith | tlarsen@phd5.idaho.gov |  | PR-040-020 | 2022-01-31 | 8:45 - 11 AM
8 | Create Contract with Rebate and Price Breaks Statewide for Envelopes - Releasing a Contract | 7203 | 11985 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | DOP | Trish Larsen Smith | tlarsen@phd5.idaho.gov |  | PR-040-020 | 2022-01-31 | 8:45 - 11 AM
10 | Contract Approval | 8353 | 11979 | Approver | Approve transactions such as requisitions, purchase orders, solicitation & journal entries. | DOP | Jeremy St Clair & Melody Bowyer | jstclair@phd5.idaho.gov & mbowyer@phd5.idaho.gov |  | PR-040-020 | 2022-01-31 | 1 - 1:30 PM
9 | Create Contract with Rebate and Price Breaks Statewide for Envelopes - Activating a Contract | 7202 | 11978 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | DOP | Trish Larsen Smith | tlarsen@phd5.idaho.gov |  | PR-040-020 | 2022-01-31 | 8:45 - 11 AM
11 | Requisition - RSS | 8325 | 11988 | Requester | Determines requirements & cost estimates for purchase of goods & services. Submits purchase requisition. | Assigned Agency | Lorna Meter | lmeter@phd5.idaho.gov | distribution to multiple org unit and agencies | PR-020-010 | 2022-01-31 | 1:30 - 2:30 PM
12 | Approve Requisition | 8539 | 11984 | Approver | Approve transactions such as requisitions, purchase orders, solicitation & journal entries. | Assigned Agency | Jeremy St Clair & Melody Bowyer | jstclair@phd5.idaho.gov & mbowyer@phd5.idaho.gov |  | PR-020-010 | 2022-01-31 | 2:30 - 3 PM
13 | Create PO from Requisition | 8327 | 11991 | Buyer | Review requisitions & create purchase orders. Conduct market research & monitor vendor commitments. Approve vendor returns. | Assigned Agency | Lorna Meter | lmeter@phd5.idaho.gov |  | PR-050-040 | 2022-02-01 | 8:45-9:30 AM
14 | Receive Purchase Order | 3064 | 11977 | Receiver | Receive and inspect incoming goods. Pick items for shipment/transfer. Dispose of items. Vendor returns. Document variances. | Assigned Agency | Lorna Meter | lmeter@phd5.idaho.gov |  | PR-050-070 | 2022-02-01 | 9:30-10AM
15 | Create Invoice | 11606 | 11983 | Payables Invoice Processor | Process interface and XM files. Match payables invoices, and vendor list. Process payables payments. Generate 1099. | Assigned Agency | Lorna Meter | lmeter@phd5.idaho.gov |  | MF-070-050 Enter a PO Invoice | 2022-02-01 | 10-11AM
16 | Notify Buyer of Discrepancy | 11605 | 11982 | Payables Invoice Processor | Process interface and XM files. Match payables invoices, and vendor list. Process payables payments. Generate 1099. |  | Lorna Meter | lmeter@phd5.idaho.gov |  | MF-070-050 Enter a PO Invoice | 2022-02-01 | 1-1:30PM
17 | Resolve Cost Discrepancy | New | 12004 | Buyer | Review requisition and create purchase orders. Conduct market research, and monitor vendor commitments. Approve vendor returns. | Assigned Agency | Lorna Meter | lmeter@phd5.idaho.gov |  |  | 2022-02-01 | 1:30-2PM
18 | Submit Resolved Invoice for Approval | 11607 | 11989 | Payables Invoice Processor | Process interface and XM files. Match payables invoices, and vendor list. Process payables payments. Generate 1099. |  | Lorna Meter | lmeter@phd5.idaho.gov |  | MF-070-050 Enter a PO Invoice | 2022-02-01 | 2-2:30PM
19 | Approve Invoice | 11608 | 11990 | Approver | Approve transactions such as requisitions, purchase orders, solicitations, and journal entries. | Assigned Agency | Trish Larsen Smith, Jeremy St Clair, Melody Bowyer | tlarsen@phd5.idaho.gov, mbowyer@phd5.idaho.gov, tlarsen@phd5.idaho.gov |  | MF-070-056 Invoice Approval Process | 2022-02-01 | 2:30-3PM
20 | Match Invoice | 11609 | 11994 | Payables Manager | Void & cancel payments. Reissue & mail warrants. Process period close. | Assigned Agency | Trish Larsen Smith | tlarsen@phd5.idaho.gov |  | MF-070-070 Match Invoices | 2022-02-01 | 3-3:30PM
21 | Process Payment for Invoice | 11442 | 11981 | Payables Manager | Void & cancel payments. Reissue & mail warrants. Process period close. | Assigned Agency | Trish Larsen Smith | tlarsen@phd5.idaho.gov |  | MF-070-100 Process Invoice Payments | 2022-02-01 | 3-3:30PM
22 | Journalize | 11440 | 11980 | Payables Manager | Void & cancel payments. Reissue & mail warrants. Process period close. |  | Trish Larsen Smith | tlarsen@phd5.idaho.gov |  | MF-070-110 Journalize AP Distributions | 2022-02-01 | 3-3:30PM
23 | Renew/Addendum Statewide Contract | 2773 | 11986 | Contract Manager | Compile contract file, including entering contract line-item details, terms & conditions, and pricing, and amends and renews contracts. | DOP | Trish Larsen Smith | tlarsen@phd5.idaho.gov |  | PR-050-010 | 2022-02-02 | 8:45-9:30 AM
24 | Load Rebate Invoices | New | 11999 | Supply Management Admin or Processor |  | Assigned Agency |  |  |  | PR-050-010 | 2022-02-02 | 9:30-10AM
25 | Calculate Rebate Amounts Due for a Contract | New | 12000 | Supply Management Admin or Processor | [5 empty] | PR-050-010 | 2022-02-02 | 10-11AM
26 | Review Rebate Due Information | New | 12001 | Contract Manager | Compile contract file, including entering contract line-item details, terms & conditions, and pricing, and amends and renews contracts. | Assigned Agency | Trish Larsen Smith | tlarsen@phd5.idaho.gov |  | PR-050-010 | 2022-02-02 | 1-1:30PM
27 | Apply Rebate (Enter a Rebate Invoice in Payables | New | 12002 | Payables Manager | Void & cancel payments. Reissue & mail warrants. Process period close. |  | Trish Larsen Smith | tlarsen@phd5.idaho.gov | There isn't an invoice type of Rebate Invoice???? | MF-260-070ZZ | 2022-02-03 | 8:45-9:30 AM
28 | Review Rebate Information | New | 12003 | Contract Manager | Compile contract file, including entering contract line-item details, terms & conditions, and pricing, and amends and renews contracts. |  | Trish Larsen Smith | tlarsen@phd5.idaho.gov |  | PR-050-010 | 2022-02-03 | 9:30-10AM
29 | Verify Rebates posted in Cash Account |  |  | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Trish Larsen Smith | tlarsen@phd5.idaho.gov |  | MF-260-070ZZ | 2022-02-03 | 10-11 AM
Note on J5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard

## Project 1.1 Project Setup and M
SIT 3 Scenario - Project Setup
Agency:
SIT 3 Week - Week 5 - 1/31-2/4
Sequence | Script ID | Tab | ALM Test ID # (view tab = "Tests" column A) | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Create Operational Project | FSM.PS001 |  | Project Administrator | Sets up projects and funding sources. | Assigned Agency | Jeremy St Clair | jstclair@phd5.idaho.gov |  | MF-050-010 | Conference Room Pilot (In Person) 1/31 - 2/4
2 | Create Billable MultiFunded Project - External Grant/External Customer | FSM.PS002 |  | Project Administrator | Sets up projects and funding sources. | Assigned Agency | Jeremy St Clair | jstclair@phd5.idaho.gov |  | MF-280-020 | Conference Room Pilot (In Person) 1/31 - 2/4
3 | Create Internal Only Project | FSM.PS003 |  | Project Administrator | Sets up projects and funding sources. | Assigned Agency | Jeremy St Clair | jstclair@phd5.idaho.gov |  | MF-050-010 | Conference Room Pilot (In Person) 1/31 - 2/4
4 | Create MultiFunded Project w Program Income (Additive/ Deductive/ Cost Sharing) or Rebates Income Funding Source | FSM.PS004 |  | Project Administrator | Sets up projects and funding sources. | Assigned Agency | Jeremy St Clair | jstclair@phd5.idaho.gov |  | MF-280-020 | Conference Room Pilot (In Person) 1/31 - 2/4
5 | Create Milestone Project(w/wo Override) | FSM.PS005 |  | Project Administrator | Sets up projects and funding sources. | Assigned Agency | Jeremy St Clair | jstclair@phd5.idaho.gov |  | MF-280-020 | Conference Room Pilot (In Person) 1/31 - 2/4
6 | Create Project with Intercompany Funding | FSM.PS006 |  | Project Administrator | Sets up projects and funding sources. | Assigned Agency | Jeremy St Clair | jstclair@phd5.idaho.gov |  | MF-280-020 | Conference Room Pilot (In Person) 1/31 - 2/4
7 | Create a New Posting Project (child) for existing Contract (new year project) | FSM.PS007 |  | Project Administrator | Sets up projects and funding sources. | Assigned Agency | Jeremy St Clair | jstclair@phd5.idaho.gov |  | MF-280-020 | Conference Room Pilot (In Person) 1/31 - 2/4
8 | Create New Burden Codes | FSM.PS009 |  | Project Administrator | Sets up projects and funding sources. | Assigned Agency | Jeremy St Clair | jstclair@phd5.idaho.gov |  | MF-280-000ZZ | Conference Room Pilot (In Person) 1/31 - 2/4
9 | Create New Selection Group | FSM.PS010 |  | Project Administrator | Sets up projects and funding sources. | Assigned Agency | Jeremy St Clair | jstclair@phd5.idaho.gov |  | MF-280-000ZZ | Conference Room Pilot (In Person) 1/31 - 2/4
10 | Assign Burden Code To Posting Project | FSM.PS011 |  | Project Administrator | Sets up projects and funding sources. | Assigned Agency | Jeremy St Clair | jstclair@phd5.idaho.gov |  | MF-280-030ZZ | Conference Room Pilot (In Person) 1/31 - 2/4
11 | Attach Burden to Funding Source | FSM.PS012 |  | Project Administrator | Sets up projects and funding sources. | Assigned Agency | Jeremy St Clair | jstclair@phd5.idaho.gov |  | MF-280-030ZZ | Conference Room Pilot (In Person) 1/31 - 2/4
12 | Program Income Additive | FSM.PM001 |  | Project Administrator | Sets up projects and funding sources. | Assigned Agency | Jeremy St Clair | jstclair@phd5.idaho.gov |  | MF-280-045ZZ | Conference Room Pilot (In Person) 1/31 - 2/4
13 | Program Income Deductive/Cost Sharing | FSM.PM002 |  | Project Administrator | Sets up projects and funding sources. | Assigned Agency | Jeremy St Clair | jstclair@phd5.idaho.gov |  | MF-280-045ZZ | Conference Room Pilot (In Person) 1/31 - 2/4
Note on J5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard

## Project 1.2 Project Processing
| NOTE: Project processing actions take place after Procurement/AP/Payroll Processing. | Other Teams Involvement Identified
SIT 3 Scenario - Project Processing (P&G Only)
Agency:
SIT Week - (dates)
Sequence | Script ID | SIT TEST ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Create Project transactions Journal Entry | FSM.PP001 | Project Accountant |  |  | Jeremy St Clair | jstclair@phd5.idaho.gov |  | MF-020-050 | Conference Room Pilot (In Person) 1/31 - 2/4
2 | In-Kind Journal Entry ("on the books"/off books) | FSM.PP002 | Project Accountant |  |  | Jeremy St Clair | jstclair@phd5.idaho.gov |  | MF-020-050 | Conference Room Pilot (In Person) 1/31 - 2/4
3 | Copy ( & Copy Reverse) Journal Entry | FSM.PP003 | Project Accountant |  |  | Jeremy St Clair | jstclair@phd5.idaho.gov |  | MF-020-050 | Conference Room Pilot (In Person) 1/31 - 2/4
4 | Create I/C Journal Entry | FSM.PP004 | Project Accountant |  |  | Jeremy St Clair | jstclair@phd5.idaho.gov |  | MF-020-050 | Conference Room Pilot (In Person) 1/31 - 2/4
5 | Create, Release and Journalize Recurring JE | FSM.PP005 | Project Accountant |  |  | Jeremy St Clair | jstclair@phd5.idaho.gov |  | MF-020-050 | Conference Room Pilot (In Person) 1/31 - 2/4
6 | Post Journal |  | GL | [5 empty] | MF-020-090 | Conference Room Pilot (In Person) 1/31 - 2/4
7 | Create and Process Retainer Invoice | FSM.PP010 | Project Accountant |  |  | Jeremy St Clair | jstclair@phd5.idaho.gov |  | MF-280-030: Grant Billing Processing | Conference Room Pilot (In Person) 1/31 - 2/4 |  | new process
8 | Generate Indirect Burdens | FSM.PP011 | Project Accountant |  |  | Jeremy St Clair | jstclair@phd5.idaho.gov |  | DC-040-090 - Apply Overhead Costs | Conference Room Pilot (In Person) 1/31 - 2/4
9 | Delete Indirect Burden | FSM.PP012 | Project Accountant |  |  | Jeremy St Clair | jstclair@phd5.idaho.gov |  | DC-040-090 - Apply Overhead Costs | Conference Room Pilot (In Person) 1/31 - 2/4
10 | Journalize Indirect Burden | FSM.PP013 | Project Accountant |  |  | Jeremy St Clair | jstclair@phd5.idaho.gov |  | DC-040-090 - Apply Overhead Costs | Conference Room Pilot (In Person) 1/31 - 2/4
11 | Reverse Indirect Burden | FSM.PP014 | Project Accountant |  |  | Jeremy St Clair | jstclair@phd5.idaho.gov |  | DC-040-090 - Apply Overhead Costs | Conference Room Pilot (In Person) 1/31 - 2/4
12 | Post Transaction in GL |  | GL | [5 empty] | DC-030-050 - Allocate Indirect Costs | Conference Room Pilot (In Person) 1/31 - 2/4
13 | Journalize IB Projects Transactions | FSM.PP013 | Project Accountant |  |  | Jeremy St Clair | jstclair@phd5.idaho.gov |  | DC-030-050 - Allocate Indirect Costs | Conference Room Pilot (In Person) 1/31 - 2/4
14 | Post Transaction in GL |  | GL | [5 empty] | DC-030-050 - Allocate Indirect Costs | Conference Room Pilot (In Person) 1/31 - 2/4
15 | Create, Generate ,Update Certification Number & Date and Journalize Milestone Invoice | FSM.PP020 | Project Accountant |  |  | Jeremy St Clair | jstclair@phd5.idaho.gov |  | MF-280-030: Grant Billing Processing | Conference Room Pilot (In Person) 1/31 - 2/4
16 | Create, Generate ,Update Certification Number & Date and Journalize Cost Reimbursement Invoice | FSM.PP021 | Project Accountant |  |  | Jeremy St Clair | jstclair@phd5.idaho.gov |  | MF-280-030: Grant Billing Processing | Conference Room Pilot (In Person) 1/31 - 2/4
17 | Generate Mass Contract Invoice w/wo Billing Group, Mass Journalize and Review AR Transaction | FSM.PP022 | Project Accountant |  |  | Jeremy St Clair | jstclair@phd5.idaho.gov |  | MF-280-030: Grant Billing Processing | Conference Room Pilot (In Person) 1/31 - 2/4
27 | Process Project Capitalization | FSM.PP040 | Project Accountant |  |  | Jeremy St Clair | jstclair@phd5.idaho.gov |  | DC-050-030 - Capitalize Leased Asset | Conference Room Pilot (In Person) 1/31 - 2/4
28 | Contract Balance Adjustments | FSM.PP050 | Project Accountant |  |  | Jeremy St Clair | jstclair@phd5.idaho.gov |  | MF-280-021ZZ | Conference Room Pilot (In Person) 1/31 - 2/4
29 | Reverse Indirect Burden | FSM.PP051 | Project Accountant |  |  | Jeremy St Clair | jstclair@phd5.idaho.gov |  | DC-040-090 - Apply Overhead Costs | Conference Room Pilot (In Person) 1/31 - 2/4
30 | Delete Invoice | FSM.PP052 | Project Accountant |  |  | Jeremy St Clair | jstclair@phd5.idaho.gov |  | MF-280-031ZZ | Conference Room Pilot (In Person) 1/31 - 2/4
31 | Reverse Journalize Invoice | FSM.PP053 | Project Accountant |  |  | Jeremy St Clair | jstclair@phd5.idaho.gov |  | MF-280-032ZZ | Conference Room Pilot (In Person) 1/31 - 2/4
32 | New Burden Rate | FSM.PP054 | Project Accountant |  |  | Jeremy St Clair | jstclair@phd5.idaho.gov |  | DC-040-091ZZ | Conference Room Pilot (In Person) 1/31 - 2/4
33 | Retainer Adjustment/ Re Applying Retainers | FSM.PP055 | Project Accountant |  |  | Jeremy St Clair | jstclair@phd5.idaho.gov |  | MF-280-022ZZ | Conference Room Pilot (In Person) 1/31 - 2/4
34 | Backout & Reallocate FES Transactions | FSM.PP056 | Project Accountant |  |  | Jeremy St Clair | jstclair@phd5.idaho.gov |  | MF-020-051ZZ | Conference Room Pilot (In Person) 1/31 - 2/4
35 | Review Partially Billed Transactions | FSM.PP057 | Project Accountant |  |  | Jeremy St Clair | jstclair@phd5.idaho.gov |  | MF-280-030: Grant Billing Processing | Conference Room Pilot (In Person) 1/31 - 2/4
36 | Move Project within Structure | FSM.PP059 | Project Accountant |  |  | Jeremy St Clair | jstclair@phd5.idaho.gov |  | MF-050-010: Set up Project | Conference Room Pilot (In Person) 1/31 - 2/4
37 | Copy Posting project | FSM.PP060 | Project Accountant |  |  | Jeremy St Clair | jstclair@phd5.idaho.gov |  | MF-050-010: Set up Project | Conference Room Pilot (In Person) 1/31 - 2/4
38 | Copy Project Funding Source | FSM.PP061 | Project Accountant |  |  | Jeremy St Clair | jstclair@phd5.idaho.gov |  | MF-050-010: Set up Project | Conference Room Pilot (In Person) 1/31 - 2/4
39 | Change SEFA flag | FSM.PP062 | Project Accountant |  |  | Jeremy St Clair | jstclair@phd5.idaho.gov |  | MF-050-010: Set up Project | Conference Room Pilot (In Person) 1/31 - 2/4
40 | Change PoP for Specific System Code on a Posting Project | FSM.PP063 | Project Accountant |  |  | Jeremy St Clair | jstclair@phd5.idaho.gov |  | MF-050-010: Set up Project | Conference Room Pilot (In Person) 1/31 - 2/4
Note on I5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard

## Project 1.3 Reports and Inquiry
Project closing takes place after project processing generally).
SIT 3 Scenario - Closing Projects
Agency:
SIT 3 Week - Week 6: 2/7 - 2/11 & Week 7: 2/14 - 2/18
Sequence | Script ID | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Project Close | FSM.PC001 | Project Accountant | Create, maintain, and close projects and grants, with billing, receiving, and cost allocations. | Assigned Agency | Jeremy St Clair | jstclair@phd5.idaho.gov |  | MF-050-090 | 2022-02-15 | 8:45-9:30 AM
2 | Review Project | FSM.PIN001 | Project Accountant | Create, maintain, and close projects and grants, with billing, receiving, and cost allocations. | Assigned Agency | Jeremy St Clair | jstclair@phd5.idaho.gov |  | DC-030-080 | 2022-02-15 | 9:30-10AM
3 | GL Journal Transaction Detail | FSM.PIN002 | Project Accountant | Create, maintain, and close projects and grants, with billing, receiving, and cost allocations. | Assigned Agency | Jeremy St Clair | jstclair@phd5.idaho.gov |  | DC-030-080 | 2022-02-15 | 10-10:30 AM
4 | Project Searches - Transactions | FSM.PIN003 | Project Accountant | Create, maintain, and close projects and grants, with billing, receiving, and cost allocations. | Assigned Agency | Jeremy St Clair | jstclair@phd5.idaho.gov |  | DC-030-080 | 2022-02-15 | 10:30 - 11 AM
5 | View all Contact Invoices & all invoices Lines | FSM.PIN004 | Project Accountant | Create, maintain, and close projects and grants, with billing, receiving, and cost allocations. | Assigned Agency | Jeremy St Clair | jstclair@phd5.idaho.gov |  | DC-030-080 | 2022-02-15 | 1-1:30PM
6 | Assign Reports | FSM.PRP001 | Project Accountant | Create, maintain, and close projects and grants, with billing, receiving, and cost allocations. | Assigned Agency | Jeremy St Clair | jstclair@phd5.idaho.gov |  | DC-030-080 | 2022-02-15 | 1:30-2PM
7 | View Project Report | FSM.PRP002 | Project Accountant | Create, maintain, and close projects and grants, with billing, receiving, and cost allocations. | Assigned Agency | Jeremy St Clair | jstclair@phd5.idaho.gov |  | DC-030-080 | 2022-02-15 | 2-2:30PM
8 | Personalize Report | FSM.PRP003 | Project Accountant | Create, maintain, and close projects and grants, with billing, receiving, and cost allocations. | Assigned Agency | Jeremy St Clair | jstclair@phd5.idaho.gov |  | DC-030-080 | 2022-02-15 | 2:30-3PM
9 | View Funding Source List | FSM.PRA001 | Project Accountant | Create, maintain, and close projects and grants, with billing, receiving, and cost allocations. | Assigned Agency | Jeremy St Clair | jstclair@phd5.idaho.gov |  | DC-030-080 | 2022-02-15 | 3 - 3:30 PM
10 | View Project Contract Reports | FSM.PRA002 | Project Accountant | Create, maintain, and close projects and grants, with billing, receiving, and cost allocations. | Assigned Agency | Jeremy St Clair | jstclair@phd5.idaho.gov |  | DC-030-080 | 2022-02-15 | 3:30 - 4 PM
11 | View Payables Reports | FSM.PRA003 | Financials Viewer |  | Assigned Agency | Jeremy St Clair | jstclair@phd5.idaho.gov |  | DC-030-080 | 2022-02-16 | 8:45-9:30 AM
12 | View Budget Reports | FSM.PRA004 | Project Accountant | Create, maintain, and close projects and grants, with billing, receiving, and cost allocations. | Assigned Agency | Jeremy St Clair | jstclair@phd5.idaho.gov |  | DC-030-080 | 2022-02-16 | 9:30-10AM
13 | View Receivables Reports | FSM.PRA005 | Financials Viewer |  | Assigned Agency | Jeremy St Clair | jstclair@phd5.idaho.gov |  | DC-030-080 | 2022-02-16 | 10-10:30 AM
14 | View d/EPM Dashboard Reports | FSM.PBI001 | Project Accountant | Create, maintain, and close projects and grants, with billing, receiving, and cost allocations. | Assigned Agency | Jeremy St Clair | jstclair@phd5.idaho.gov |  | DC-030-080 | 2022-02-16 | 10-10:30 AM
Note on I5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard

## Cash Ledger Payment
SIT 3 Scenario - Cash Ledger Payment
Agency:
SIT Week - Week 7 - 2/14 -2/18
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Enter Cash Payment | Cash Payment Entry.xlsx | 12075 | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Trish Larsen Smith | tlarsen@phd5.idaho.gov | Rotary/Site Draft, L Warrants |  | 2022-02-14 | 8:45 - 10 AM
1A | Record Cash Payment |  | 12525 | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Trish Larsen Smith | tlarsen@phd5.idaho.gov |  |  | 2022-02-14 | 8:45 - 10 AM
2 | Approve Cash Payment | Cash Approve Cash Payment.xlsx | 12076 | Cash Manager | Manage all cash transactions. Review and update cash management policy as needed. | Assigned Agency | Jeremy St Clair | jstclair@phd5.idaho.gov |  |  | 2022-02-14 | 10 - 11:30 AM
3 | Cash Requirements | Cash Requirements.xlsx | 12077 | Payables Payment Processor | Perform Cash Requirements, Schedule Payments, Complete Payment Cycle | Assigned Agency | Trish Larsen Smith | tlarsen@phd5.idaho.gov |  | MF-070-100 Process Invoice Payments | 2022-02-14 | 1 - 2:30 PM
4 | Review Check in Cash | Cash Review Check in Cash Management.xlsx | 12078 | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Trish Larsen Smith | tlarsen@phd5.idaho.gov | Redeem or Void then Review again |  | 2022-02-14 | 2:30 - 4 PM
5 | Journalize Distributions | Cash Journalize Cash Transaction.xlsx | 12079 | Cash Manager | Manage all cash transactions. Review and update cash management policy as needed. | Assigned Agency | Jeremy St Clair | jstclair@phd5.idaho.gov |  |  | 2022-02-15 | 8:45 - 10 AM
6 | Verify Results in Global Ledger Account Analysis |  | 12082 | Staff Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Trish Larsen Smith | tlarsen@phd5.idaho.gov |  |  | 2022-02-15 | 10 - 11:30 AM
7 | Optional Void Cash Payment for Status Updates | Cash Void Cash Payment.xlsx | 12080 | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Trish Larsen Smith | tlarsen@phd5.idaho.gov |  |  | 2022-02-15 | 1 - 2:30 PM
8 | Optional Void Cash Payment: Payment Void Stop Pay Update | 12161 | 12161 | Payables Payment Processor | Perform Cash Requirements, Schedule Payments, Complete Payment Cycle | Assigned Agency | Trish Larsen Smith | tlarsen@phd5.idaho.gov |  |  | 2022-02-15 | 1 - 2:30 PM
9 | Optional Redeem Warrant for Status Updates | Cash Redeem Warrant.xlsx | 12081 | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Trish Larsen Smith | tlarsen@phd5.idaho.gov |  |  | 2022-02-15 | 2:30 - 4 PM
Note on I4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard
Note on K5: Glenda Smith: Cash BPR's are not correct, do not reference.

## Interagency Billing to Settleme
SIT 3 Scenario - Interagency Billing to Settlement
Agency:
SIT Week - Week 7 - 2/14 -2/18
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Create Interagency Billing - Basic | 8795 | 11909 | Intercompany Billing Specialist | Handle setup and processing of intercompany billing. | Assigned Agency | Trish Larsen Smith | tlarsen@phd5.idaho.gov |  | MF-260-030ZZ | 2022-02-14 | 8:45-9:30 AM
2 | Identify Unpaid Interagency Billings | 11536 | 11907 | Payables Invoice Processor | Process interface and XM files. Match payables invoices, and vendor list. Process payables payments. Generate 1099. | Assigned Agency | Lorna Meter | lmeter@phd5.idaho.gov |  | MF-070-050 Enter a PO Invoice | 2022-02-14 | 9:30 - 10:30 AM
3 | Reclassify Interagency Expenditure Coding (AP110 Distribution Changes on Paid Invoice) | 11624 | 11906 | Payables Invoice Processor | Process interface and XM files. Match payables invoices, and vendor list. Process payables payments. Generate 1099. | Assigned Agency | Lorna Meter | lmeter@phd5.idaho.gov |  | MF-070-050 Enter a PO Invoice | 2022-02-14 | 10:30 -11:30 AM
4 | Settle an Interagency Billing | 8794 | 11908 | Intercompany Billing Specialist | Handle setup and processing of intercompany billing. | Assigned Agency | Trish Larsen Smith | tlarsen@phd5.idaho.gov |  | MF-260-030ZZ | 2022-02-14 | 1-1:30PM
Note on J5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard

## Procure to Pay Vendor Mgt Voids
SIT 3 Scenario - Procure to Pay with Void and Vendor Update
Agency:
SIT Week - Week 7 - 2/14 -2/18
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | Luma Role (role switcher) | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Create Requisition - Special | 8324 | Requester | Assigned Agency | Lorna Meter | lmeter@phd5.idaho.gov |  | PR-020-010 | 2022-02-14 | 8:45-9:30 AM
2 | Approve Requisition | 8539 | Approver | Assigned Agency | Jeremy St Clair & Melody Bowyer | jstclair@phd5.idaho.gov & mbowyer@phd5.idaho.gov | Requisition not approved | PR-010-060 | 2022-02-14 | 9:30-10AM
3 | Create Purchase Order | 8170 | Buyer | Assigned Agency | Lorna Meter | lmeter@phd5.idaho.gov |  | PR-050-040 | 2022-02-14 | 10-10:30 AM
4 | Receive Purchase Order | 4587 | Receiver | Assigned Agency | Lorna Meter | lmeter@phd5.idaho.gov |  | PR-050-070 | 2022-02-14 | 10:30 - 11 AM
5 | Create Invoice | 11519 | Payables Invoice Processor | Assigned Agency | Lorna Meter | lmeter@phd5.idaho.gov |  | MF-070-050 Enter a PO Invoice | 2022-02-14 | 1-1:30PM
6 | Approve Invoice | 11520 | Approver | Assigned Agency | Trish Larsen Smith, Jeremy St Clair, Melody Bowyer | tlarsen@phd5.idaho.gov, mbowyer@phd5.idaho.gov, tlarsen@phd5.idaho.gov |  | MF-070-056 Invoice Approval Process | 2022-02-14 | 1:30-2PM
7 | Match Invoice | 11458 | Payables Manager | Assigned Agency | Trish Larsen Smith | tlarsen@phd5.idaho.gov |  | MF-070-070 Match Invoices | 2022-02-14 | 2-2:30PM
8 | Process Payment for Invoice | 11442 | Payables Manager | Assigned Agency | Trish Larsen Smith | tlarsen@phd5.idaho.gov |  | MF-070-100 Process Invoice Payments | 2022-02-14 | 2:30-3PM
9 | Journalize | 11440 | Payables Manager |  | Trish Larsen Smith | tlarsen@phd5.idaho.gov |  | MF-070-110 Journalize AP Distributions | 2022-02-14 | 3 - 3:30 PM
10 | Void Payment | 12080 | Cash Accountant | SCO | Trish Larsen Smith | tlarsen@phd5.idaho.gov |  | MF-200-060 Void Cash Transactions | 2022-02-14 | 3:30 - 4 PM
11 | Cancel Invoice | 11523 | Payables Manager | Assigned Agency | Trish Larsen Smith | tlarsen@phd5.idaho.gov |  | MF-070-050 Enter a PO Invoice | 2022-02-15 | 8:45-9:30 AM
12 | Request a new vendor | 11524 | Payables Invoice Processor | Assigned Agency | Lorna Meter | lmeter@phd5.idaho.gov |  | PR-040-030 Create and Maintain Vendor | 2022-02-15 | 9:30-10AM
13 | Approve and setup new vendor | 11525 - Only SCO staff can do this | Approver | SCO | Trish Larsen Smith, Jeremy St Clair, Melody Bowyer | tlarsen@phd5.idaho.gov, mbowyer@phd5.idaho.gov, tlarsen@phd5.idaho.gov | Disapprove vendor | PR-040-030 Create and Maintain Vendor | 2022-02-15 | 10-10:30 AM
14 | Create Invoice | 11519 | Payables Invoice Processor | Assigned Agency | Lorna Meter | lmeter@phd5.idaho.gov |  | MF-070-050 Enter a PO Invoice | 2022-02-15 | 10:30 - 11 AM
15 | Approve Invoice | 11520 | Approver | Assigned Agency | Trish Larsen Smith, Jeremy St Clair, Melody Bowyer | tlarsen@phd5.idaho.gov, mbowyer@phd5.idaho.gov, tlarsen@phd5.idaho.gov |  | MF-070-056 Invoice Approval Process | 2022-02-15 | 1-1:30PM
16 | Match Invoice | 11522 | Payables Invoice Processor | Assigned Agency | Lorna Meter | lmeter@phd5.idaho.gov |  | MF-070-070 Match Invoices | 2022-02-15 | 1:30-2PM
17 | Process Payment for Invoice | 11442 | Payables Manager | Assigned Agency | Trish Larsen Smith | tlarsen@phd5.idaho.gov |  | MF-070-100 Process Invoice Payments | 2022-02-15 | 2-2:30PM
18 | Post Transactions - Journalize | 11440 | Payables Manager | Assigned Agency | Trish Larsen Smith | tlarsen@phd5.idaho.gov |  | MF-070-110 Journalize AP Distributions | 2022-02-15 | 2:30-3PM
19 | Cash Ledger Journalize | 12079 | Cash Manager | Assigned Agency | Jeremy St Clair | jstclair@phd5.idaho.gov |  | MF-200-050 Reconcile Payments Payables and Disbursements | 2022-02-15 | 3 - 3:30 PM
20 | Verify Voided Payables Checks | 12153 | Cash Accountant | Assigned Agency | Trish Larsen Smith | tlarsen@phd5.idaho.gov |  | MF-200-060 Void Cash Transactions | 2022-02-15 | 3:30 - 4 PM
21 | View Fund Balance | Cash Fund Balance.xlsx (in ALM?)(in Cash Deposit to Revenue Scenario) | Cash Accountant | Assigned Agency | Trish Larsen Smith | tlarsen@phd5.idaho.gov |  | MF-200-050 Reconcile Payments Payables and Disbursements | 2022-02-16 | 8:45-9:30 AM
22 | Comparative report from Birst |  | Cash Accountant | Assigned Agency | Trish Larsen Smith | tlarsen@phd5.idaho.gov |  | MF-200-ZZ | 2022-02-16 | 9:30-10AM
23 | Cash Revenue Daily Report - Birst |  | Cash Manager | Assigned Agency | Jeremy St Clair | jstclair@phd5.idaho.gov |  | MF-200-ZZ | 2022-02-16 | 10-10:30 AM
Note on H5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard

## Punchout Request to Payment
SIT 3 Scenario - Punchout Request to Payment
Agency:
SIT Week - Week 8 - 2/21 - 2/25
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Create Punchout Requisition using RSS | 3501 | 11924 | Requester | Determines requirements & cost estimates for purchase of goods & services. Submits purchase requisition. | Assigned Agency | Lorna Meter | lmeter@phd5.idaho.gov |  | PR-020-010 | 2022-02-22 | 8:45-9:30 AM
2 | Approve Requisition | 8539 | 11925 | Approver | Approve transactions such as requisitions, purchase orders, solicitation & journal entries. | Assigned Agency | Jeremy St Clair & Melody Bowyer | jstclair@phd5.idaho.gov & mbowyer@phd5.idaho.gov | Deny Requisition - add note - need more information Approve Requisition | PR-010-060 | 2022-02-22 | 9:30-10AM
3 | Locate Punchout PO | Refer to Upload template | 12034 | Requester |  |  | Lorna Meter | lmeter@phd5.idaho.gov |  | PR-050-040 | 2022-02-22 | 10-11AM
4 | Review Punchout PO | Refer to Upload template | 11927 | Buyer | Review requisitions & create purchase orders. Conduct market research & monitor vendor commitments. Approve vendor returns. | Assigned Agency | Lorna Meter | lmeter@phd5.idaho.gov | This will be a review of schedule job creating PO. Other variations would be manual creation, or Job run creation submitted as needed. | PR-050-040 | 2022-02-22 | 1-1:30PM
5 | Review Punchout Receipt | Refer to Upload template | 11928 | Receiver | Receive and inspect incoming goods. Pick items for shipment/transfer. Dispose of items. Vendor returns. Document variances. | Assigned Agency | Lorna Meter | lmeter@phd5.idaho.gov | Manual release of receipt vs. auto release | PR-050-070 | 2022-02-22 | 1:30-2PM
6 | Review Punchout Invoice | 11610 | 11922 | Payables Invoice Processor | Processes interface and XM files. Match Payables invoices. Manages vendor list. Processes Payables payments. Generates 1099. | Assigned Agency | Lorna Meter | lmeter@phd5.idaho.gov |  | MF-070-050 Enter a PO Invoice | 2022-02-22 | 2-2:30PM
7 | Approve Invoice | 11611 | 11923 | Approver |  |  | Trish Larsen Smith, Jeremy St Clair, Melody Bowyer | tlarsen@phd5.idaho.gov, mbowyer@phd5.idaho.gov, tlarsen@phd5.idaho.gov |  | MF-070-056 Invoice Approval Process | 2022-02-22 | 2:30-3PM
8 | Match Invoice | 11613 | 11926 | Payables Manager | Void & cancel payments, reissue & mail warrants. Process period close. | Assigned Agency | Trish Larsen Smith | tlarsen@phd5.idaho.gov |  | MF-070-070 Match Invoices | 2022-02-22 | 3-3:30PM
9 | Process Invoice for Payment | 11442 | 11921 | Payables Manager | Void & cancel payments, reissue & mail warrants. Process period close. | Assigned Agency | Trish Larsen Smith | tlarsen@phd5.idaho.gov |  | MF-070-100 Process Invoice Payments | 2022-02-22 | 3:30 - 4 PM
Note on J5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard

## Allocations
SIT 3 Scenario - Allocations
Agency:
SIT 3 Week - Week 9 - 2/28 - 3/4
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Create Allocation Control | Allocation Control.xlsx | 12063 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate, and update allocations. | Assigned Agency | Trish Larsen Smith | tlarsen@phd5.idaho.gov |  | MF-025-030 | 2022-02-28 | 8:45-9:30 AM
2 | Create Allocation | Allocation.xlsx | 12064 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate, and update allocations. | Assigned Agency | Trish Larsen Smith | tlarsen@phd5.idaho.gov |  | MF-025-030 | 2022-02-28 | 9:30-10:30 AM
3 | Enter Allocation Lines 1 Dimension Override | Allocation Lines 1 Dimension Override.xlsx | 12065 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate, and update allocations. | Assigned Agency | Trish Larsen Smith | tlarsen@phd5.idaho.gov |  | MF-025-030 | 2022-02-28 | 10:30-11:30 AM
4 | Enter Allocation Lines 2+ Dimension Manual Override | Allocation Lines 2+ Dimension Manual Override.xlsx | 12066 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate, and update allocations. | Assigned Agency | Trish Larsen Smith | tlarsen@phd5.idaho.gov |  | MF-025-031 | 2022-02-28 | 1-1:30PM
5 | Create Group Override List | Allocation Group Overrides.xlsx | 12067 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate, and update allocations. | Assigned Agency | Trish Larsen Smith | tlarsen@phd5.idaho.gov |  | MF-025-040 | 2022-02-28 | 1:30-2PM
6 | Calculate Allocations | Allocations Calculation.xlsx | 12068 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate, and update allocations. | Assigned Agency | Trish Larsen Smith | tlarsen@phd5.idaho.gov |  | MF-025-030 | 2022-02-28 | 2-2:30PM
7 | Journalize Allocations | Allocations Journalize.xlsx | 12069 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate, and update allocations. | Assigned Agency | Trish Larsen Smith | tlarsen@phd5.idaho.gov |  | MF-025-040 | 2022-02-28 | 2:30-3PM
8 | JE Approve and Post | 2920 | 12070 | Approver | Approve transactions such as requisitions, purchase orders, solicitations, and journal entries. | Assigned Agency | Trish Larsen Smith, Jeremy St Clair, Melody Bowyer | tlarsen@phd5.idaho.gov, mbowyer@phd5.idaho.gov, tlarsen@phd5.idaho.gov |  | MF-025-060 | 2022-02-28 | 3:30 - 4 PM
Note on J5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard

## Global Ledger Entries and Analy
SIT 3 Scenario - Global Legder Processing and Analysis
Agency:
SIT Week - Week 8 - 2/21/ - 2/25
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Create a Front-End Split Journal Entry (Front End Split Projects Only) | Refer to Upload Template | 12154 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Trish Larsen Smith | tlarsen@phd5.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-010 | 2022-02-23 | 8:45-9:30 AM
2 | Create a Journal Entry | Refer to Upload Template | 11668 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Trish Larsen Smith | tlarsen@phd5.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-010 | 2022-02-23 | 9:30-10AM
3 | Approve a Journal Entry | Refer to Upload Template | 11669 | Approver | Approve transactions such as requisitions, purchase orders, solicitation & journal entries. | Assigned Agency | Trish Larsen Smith, Jeremy St Clair, Melody Bowyer | tlarsen@phd5.idaho.gov, mbowyer@phd5.idaho.gov, tlarsen@phd5.idaho.gov |  | MF-025-060 | 2022-02-23 | 10-11AM
4 | Create a Journal Entry from an Existing Journal | Refer to Upload Template | 11671 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Trish Larsen Smith | tlarsen@phd5.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-010 | 2022-02-23 | 1-1:30PM
5 | Create a Journal Entry from a Template | Refer to Upload Template | 11670 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Trish Larsen Smith | tlarsen@phd5.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-010 | 2022-02-23 | 1:30-2PM
6 | Create a Recurring Journal | Refer to Upload Template | 11673 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Trish Larsen Smith | tlarsen@phd5.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-020 | 2022-02-23 | 2-2:30PM
7 | Journalize a Recurring Journal Entry | Refer to Upload Template | 12155 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Trish Larsen Smith | tlarsen@phd5.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-030 | 2022-02-23 | 2:30-3PM
8 | Post Multiple Journal Entries | Refer to Upload Template | 12156 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Trish Larsen Smith | tlarsen@phd5.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-23 | 3-3:30PM
9 | Post Journals from Subsystems | Refer to Upload Template | 12157 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Trish Larsen Smith | tlarsen@phd5.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-050 | 2022-02-24 | 8:45-9:30 AM
10 | Validate (here) Reconcile (close) Subsystems to the General Ledger | Bill will put these scripts here and in close scenario | TBD | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Trish Larsen Smith | tlarsen@phd5.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-24 | 9:30-10AM
11 | Analyze Global Ledger Totals | Refer to Upload Template | 12158 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Trish Larsen Smith | tlarsen@phd5.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-24 | 10-11AM
12 | Perform Account Analysis | Refer to Upload Template | 11672 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Trish Larsen Smith | tlarsen@phd5.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-24 | 1-1:30PM
13 | Perform Fund Analysis | Refer to Upload Template | 12159 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Trish Larsen Smith | tlarsen@phd5.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-24 | 1:30-2PM
14 | Perform Organizational Unit Analysis | Refer to Upload Template | 12160 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Trish Larsen Smith | tlarsen@phd5.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-24 | 2-2:30PM
15 | View Transactions by Entity-Account | Refer to Upload Template | 11674 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Trish Larsen Smith | tlarsen@phd5.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-25 | 9- 9:30 AM
16 | BIRST/BI/CSF Analytic Reporting |  | TBD | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Trish Larsen Smith | tlarsen@phd5.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-25 | 9:30 - 10 AM
17 | Evaluate Encumbrances | Placeholder - Judy and Bill (and Eileen/Cathy) are working on script for this; will have this week (12/23/21) | TBD | Staff Accountant |  | Assigned Agency | Trish Larsen Smith | tlarsen@phd5.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-25 | 10 - 11 AM
Note on J5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard

## Chart of Accounts Maintenance
SIT 3 Scenario - Chart of Accounts Maintenance
Agency:
SIT Week - Week 10 - 3/7 - 3/11
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | View and Validate an Organizational Unit |  | TBD | Staff Accountant |  |  | Trish Larsen Smith | tlarsen@phd5.idaho.gov |  |  | 2022-03-07 | 8:45-9:30 AM
2 | View and Validate a Project |  | TBD | Staff Accountant |  |  | Trish Larsen Smith | tlarsen@phd5.idaho.gov |  |  | 2022-03-07 | 9:30-10AM
3 | View and Validate a Program |  | TBD | Staff Accountant |  |  | Trish Larsen Smith | tlarsen@phd5.idaho.gov |  |  | 2022-03-07 | 10-11AM
4 | View and Validate a Location |  | TBD | Staff Accountant |  |  | Trish Larsen Smith | tlarsen@phd5.idaho.gov |  |  | 2022-03-07 | 1-1:30PM
5 | View and Validate Additional Reporting |  | TBD | Staff Accountant |  |  | Trish Larsen Smith | tlarsen@phd5.idaho.gov |  |  | 2022-03-07 | 1:30-2PM
6 | View and Validate Custodial Accounts (CAM) |  | TBD | Staff Accountant |  |  | Trish Larsen Smith | tlarsen@phd5.idaho.gov |  |  | 2022-03-07 | 2-2:30PM
7 | Request a new account |  | TBD | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Trish Larsen Smith | tlarsen@phd5.idaho.gov |  |  | 2022-03-07 | 2:30-3PM
8 | Request a new organizational unit |  | TBD | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Trish Larsen Smith | tlarsen@phd5.idaho.gov |  |  | 2022-03-07 | 3-3:30PM
9 | View and Validate Beginning Balances |  | TBD | Staff Accountant |  |  | Trish Larsen Smith | tlarsen@phd5.idaho.gov |  |  | 2022-03-08 | 8:45-9:30 AM
10 | Update Summary Conversion Balances to Detail |  | TBD | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. |  | Trish Larsen Smith | tlarsen@phd5.idaho.gov |  |  | 2022-03-08 | 9:30-10AM
Note on J5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard