## SIT 3 Listing & Schedule
Agencies Participating in SIT 3 End to End Functional Testing
SIT 3 End to End Scenarios | SIT 3 Scheduled Week | 140 - Office of the State Controller (All Agencies) | 230 - Department of Correction
Inventory Management Cycle | Week 4: 1/24 - 1/28 |  | X
Pcard End to End Process | Week 4: 1/24 - 1/28
Project Processing (RQ, PO, Contract, INV) | Week 4: 1/24 - 1/28 | X
XM Pcard NO Cash Advance | Week 4: 1/24 - 1/28
XM Pcard WITH Cash Advance | Week 4: 1/24 - 1/28
Payroll End to End | Week 4: 1/24 - 1/28
Fixed Asset Acquire to Retire | Week 5: 1/31 - 2/4 |  | X
Statewide Contract Procure to Pay | Week 5: 1/31 - 2/4 |  | X
GHR Shell | Week 5: 1/31 - 2/4
Project 1.1 Project Setup and Maintanance | Week 5: 1/31 - 2/4 | X
Project 1.2 Project Processing Master (P&G only) | Week 5: 1/31 - 2/4 | X
AR Credit Monitoring | Week 6: 2/7 - 2/11 | X
Asset Management Maintenance | Week 6: 2/7 - 2/11
Service Contract Interagency Billing | Week 6: 2/7 - 2/11 | X
Project 1.3 Reports and Inquiry Master | Week 6: 2/7 - 2/11 & Week 7: 2/14 - 2/18 | X
Cash Ledger Payment | Week 7: 2/14 - 2/18 | X | X
Interagency Billing to Settlement | Week 7: 2/14 - 2/18 | X
Non-State Billing | Week 7: 2/14 - 2/18 | X
Procure to Pay Vendor Management Voids | Week 7: 2/14 - 2/18 |  | X
Vendor Refunds | Week 7: 2/14 - 2/18 | X | X
Cash Management Deposit to Revenue | Week 8: 2/21 - 2/25 | X | X
Custodial Accounts Setup | Week 8: 2/21 - 2/25 |  | X
Global Ledger Entries and Analysis | Week 8: 2/21 - 2/25 | X | X
Punchout Request to Payment | Week 8: 2/21 - 2/25 |  | X
Tax Refunds | Week 8: 2/21 - 2/25 | X
Allocations | Week 9: 2/28 - 3/4
Budget | Week 9: 2/28 - 3/4 | X
Custodial Accounts Transaction Processing | Week 9: 2/28 - 3/4 |  | X
Month End/Year End | Week 9: 2/28 - 3/4 | X
Define and Generate Recurring Invoices | Week 9: 2/28 - 3/4
Chart of Accounts Maintenance | Week 10: 3/7 - 3/11 | X | X
3rd Party Allocations | TBD

## Instructions
Luma System Integration Testing 3 (SIT 3) Instructions
Agency Functional Testing Dates | January 24 - March 11, 2022 Testing Schedule: Monday -Thursday 8:45 -11 am and 1:45 - 4:00 pm, Friday 9:00 - 11:00 am
Agency Testers Roles and Responsibilities | 1. Execute test scripts per SIT 3 schedule. 2. Review actual results against expected results. 3. Log defects as needed. 4. Retest failed test results to resolve defects. 5. Launch integrations during test cycle per schedule.
Testing Packet | 1. Test Scenario Excel File: Cover Page, Instruction Tab, Scenario Listing, Tab with each steps script detailed instruction to execute the script. 2. Data Sheets. 3. Email Template to use to report your testing results.
Testing Steps | 1. If you are the first step in the scenario, you may begin execution according to the the Date and Time in the Testing packet. If you are not on step 1, please wait for the step before you to complete their script and you receive communication to begin. 2. Execute assigned script(s) using the testing script and data sheet that was provided to you. 3. Sending Testing results via email using to the Test Management Team. (attached email sample) 4. Communicate to the next tester they can begin their script. (Slack or Email works)
What should you do if there are issues or you need assistance while testing? | 1. The Test Management Team will host an all-day SIT 3 Testing Support Hotline (WebEx Meeting). 2. Attendance is optional for SIT testers and testers should only join if they have questions or issues regarding SIT testing. 3. Testers should have an invite on their calendar that includes the WebEx Link.
How to submit a SIT 3 Testing Defect using ServiceNow: | 1. Visit https://auth.sco.idaho.gov/ in your web browser. Google Chrome and Microsoft Edge are recommended. 2. Enter your State ID number as the username and your password. Click the Sign In button. 3. You will be presented with a second page for Multi-Factor Authentication. Select an option and acknowledge the push or call, or enter a passcode from your Duo app. 4. You will see several buttons on your Enterprise Dashboard. One of these will be labeled Service Desk. This button will take you to the Service Portal. 5. There are four main buttons across the center of the page. Click Service Requests to be taken to the service menu. 7. Locate and select LUMA SIT3 Testing Issue from the options listed. 6. Select the SCO IT Services category from the list on the left side of the page. 7. Fill out form with Primary Contact, Short Description, Description, Category, Scenario Name, Script ID, add attachments/screenshots and submit the ticket.
What to do if there is a system outage? | 1. Please join the Testing Support Hotline if you run into any issues with the system and notify the meeting moderator of the issue. 2. If there is a system outage, the Test Management Team will work with the Communications team to notify Agency Testers.

## Email Submission Template
Click on Icon Below to Outlook Email Template

## Inventory Mgt Cycle
SIT 3 Scenario - Inventory Management Cycle
Agency:
SIT Week - Week 4 - 1/24 - 1/28
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | ALM SIT 3 Test ID # | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Request a New Item | 3289 | 11659 | Requester | Determines requirements & cost estimates for purchase of goods & services. Submits purchase requisition. | Assigned Agency | Jenna Marshall | jenmarsh@idoc.idaho.gov |  | PR-010-060 | 2022-01-24 | 8:45-9:30 AM
2 | Approve New Item - Add Item | added | 12035 | Approver | Approve transactions such as requisitions, purchase orders, solicitation & journal entries. | SCO | Jenna Marshall | janmarsh@idoc.idaho.gov |  | PR-010-060 | 2022-01-24 | 9:30-10AM
3 | Add Item - Manually | 1680 | 12040 | Inventory Manager | Manage/monitor: reconciliation of counts, item master, forecast methods & replenishment, reorder & disposal policy compliance. | SCO | Janice Packard | japackar@idoc.idaho.gov | Manually Add New Item (Test ID 1680) - This test will use the Inventory Manager Role | PR-010-060 | 2022-01-24 | 10-11AM
4 | Attach Item to Inventory Location | 1682 | 11667 | Inventory Manager | Manage/monitor: reconciliation of counts, item master, forecast methods & replenishment, reorder & disposal policy compliance. | Assigned Agency | Janice Packard | japackar@idoc.idaho.gov |  | PR-050-090 | 2022-01-24 | 1-1:30PM
5 | Inventory Issue - Requisition Inventory Item | 3243 | 11663 | Warehouse Clerk | Receive and inspect incoming goods. Pick items for shipment/transfer. Dispose of items. Document variances. | Assigned Agency | Janice Packard | japackar@idoc.idaho.gov |  | PR-020-010 | 2022-01-24 | 1:30-2PM
6 | Inventory Issue - Item - Warehouse Pick List Print | 2889 | 11657 | Warehouse Clerk |  |  | Janice Packard | japackar@idoc.idaho.gov |  | PR-050-090 | 2022-01-24 | 2-2:30PM
7 | Inventory Issue - Item - Warehouse Shipment Feedback | 2890 | 11660 | Warehouse Clerk | Receive and inspect incoming goods. Pick items for shipment/transfer. Dispose of items. Document variances. | Assigned Agency | Janice Packard | japackar@idoc.idaho.gov |  | PR-050-090 | 2022-01-24 | 2:30-3PM
8 | Inventory Replenishment - Auto Replenishment | 2914 | 11658 | Inventory Manager | Manage/monitor: reconciliation of counts, item master, forecast methods & replenishment, reorder & disposal policy compliance. | Assigned Agency | Janice Packard | japackar@idoc.idaho.gov | Update levels and Manual Replenishment | PR-050-090 | 2022-01-24 | 3-3:30PM
9 | Purchasing - Create Purchase Order | 2753 | 12041 | Buyer | Review requisitions & create purchase orders. Conduct market research & monitor vendor commitments. Approve vendor returns. | Assigned Agency | David Brooks | dbrooks@idoc.idaho.gov | Update levels and Manual Replenishment | PR-050-090 | 2022-01-25 | 8:45-9:30 AM
10 | Receive Items to Inventory | 1695 | 11666 | Receiver | Receive and inspect incoming goods. Pick items for shipment/transfer. Dispose of items. Vendor returns. Document variances. | Assigned Agency | Jenna Marshall | jenmarsh@idoc.idaho.gov | Receipt Discrepancies | PR-050-090 | 2022-01-25 | 9:30-10AM
11 | Perform Physical Inventory - Mass Freeze Items | 2607 | 11656 | Inventory Manager | Manage/monitor: reconciliation of counts, item master, forecast methods & replenishment, reorder & disposal policy compliance. | Assigned Agency | Janice Packard | japackar@idoc.idaho.gov |  | PR-050-090 | 2022-01-25 | 10-11AM
12 | Perform Physical Inventory - View and Print Count Sheets | 2608 | 11661 | Inventory Manager | Manage/monitor: reconciliation of counts, item master, forecast methods & replenishment, reorder & disposal policy compliance. | Assigned Agency | Janice Packard | japackar@idoc.idaho.gov |  | PR-050-090 | 2022-01-25 | 1-1:30PM
13 | Perform Physical Inventory - Enter Counts | 2775 | 11662 | Inventory Manager | Manage/monitor: reconciliation of counts, item master, forecast methods & replenishment, reorder & disposal policy compliance. | Assigned Agency | Janice Packard | japackar@idoc.idaho.gov |  | PR-050-090 | 2022-01-25 | 1:30-2PM
14 | Perform Physical Inventory - Inventory Variance Update | Added | 12033 | Inventory Manager | Manage/monitor: reconciliation of counts, item master, forecast methods & replenishment, reorder & disposal policy compliance. | Assigned Agency | Janice Packard | japackar@idoc.idaho.gov |  | PR-050-090 | 2022-01-25 | 2-2:30PM
15 | Perform Physical Inventory - Delete Freeze Records | 2776 | 11664 | Inventory Manager | Manage/monitor: reconciliation of counts, item master, forecast methods & replenishment, reorder & disposal policy compliance. | Assigned Agency | Janice Packard | japackar@idoc.idaho.gov |  | PR-050-090 | 2022-01-25 | 2:30-3PM
16 | Post Physical Inventory Adjustments | 1693 | 11665 | Inventory Manager | Manage/monitor: reconciliation of counts, item master, forecast methods & replenishment, reorder & disposal policy compliance. | Assigned Agency | Janice Packard | japackar@idoc.idaho.gov |  | PR-050-090 | 2022-01-25 | 3-3:30PM
17 | Review Beginning/End Inventory Balance |  |  | Staff Accountant | Account analysis to verify Inventory GL balance reflects inventory balance and adjustments. | Assigned Agency | Mathel Castleton | mcastlet@idoc.idaho.gov |  | IL-20-ZZ Manage Inventory, Storage, and Movement (See Finance workbook MF-020 diagram) | 2022-01-25 | 3:30 -4 PM
Note on J5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard

## Fixed Assets Acquire To Retire
SIT 3 Scenario - Acquire Fixed Asset to Retire
Agency:
SIT 3 Week - Week 5 - 1/31-2/4
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | NEW SIT 3 ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Create Fixed Asset Requisition | 3041 | 11563 | Requester | Determines requirements & cost estimates for purchase of goods & services. Submits purchase requisition. | Assigned Agency | Jenna Marshall | jenmarsh@idoc.idaho.gov | Associate with project | PR-010-060 | 2022-01-31 | 8:45-9:30 AM
2 | Approve Requisition | 8539 | 11564 | Approver | Approve transactions such as requisitions, purchase orders, solicitations, and journal entries. | Assigned Agency | Jenna Marshall | janmarsh@idoc.idaho.gov | Deny Requisition - add note - need more information Approve Requisition | PR-020-020 | 2022-01-31 | 9:30-10AM
3 | Identify Requistions to send to Sourcing Event | 2896 | 11565 | Buyer | Review requisition and create purchase orders. Conduct market research, and monitor vendor commitments. Approve vendor returns. | Assigned Agency | David Brooks | dbrooks@idoc.idaho.gov |  | PR-030-020 | 2022-01-31 | 10-11AM
4 | Create Sourcing Event RFQ | 7186 | 11566 | Sourcing Manager | Create souring events, evaluate supplier responses, and oversee selection & award of sourcing events. | Assigned Agency | Cindy Lee | cilee@idoc.idaho.gov |  | PR-030-030 | 2022-01-31 | 1-1:30PM
5 | Approve Sourcing Event to Post | 8439 | 11567 | Approver | Approve transactions such as requisitions, purchase orders, solicitations, and journal entries. | Assigned Agency | Cindy Lee | cilee@idoc.idaho.gov | Approve/Deny/Reject Sourcing Event to Post | PR-030-010 | 2022-01-31 | 1:30-2PM
6 | Enter A Manual response | 7187 | 11568 | Sourcing Manager | Develop/oversee supplier list; monitor & evaluate vendors. Evaluate proposals; create souring events, oversee selection & award contracts. | Assigned Agency | Cindy Lee | cilee@idoc.idaho.gov |  | PR-030-050 | 2022-01-31 | 2-2:30PM
7 | Analyze and Award an Event to Contract | 7189 | 11569 | Sourcing Manager | Develop/oversee supplier list; monitor & evaluate vendors. Evaluate proposals; create souring events, oversee selection & award contracts. | Assigned Agency | Cindy Lee | cilee@idoc.idaho.gov | Split Award by Line | PR-030-050 | 2022-01-31 | 2:30-3PM
8 | Sourcing Event Award Approval | 8440 | 11570 | Approver | Approve transactions such as requisitions, purchase orders, solicitations, and journal entries. | Assigned Agency | Cindy Lee | cilee@idoc.idaho.gov | Approve/Deny/Reject | PR-030-050 | 2022-01-31 | 3-3:30PM
9 | Create Contract - Create a Contract - Contract Tab | 7219 | 11571 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | Assigned Agency | Cindy Lee | cilee@idoc.idaho.gov |  | PR-040-010 | 2022-02-01 | 8:45 - 10:30AM
10 | Create Contract - Contract Draft - Articles Tab | 7204 | 11572 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | Assigned Agency | Cindy Lee | cilee@idoc.idaho.gov |  | PR-040-010 | 2022-02-01 | 8:45 - 10:30AM
11 | Create Contract - Contract Draft - Participants Tab | 2667 | 11573 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | Assigned Agency | Cindy Lee | cilee@idoc.idaho.gov |  | PR-040-010 | 2022-02-01 | 8:45 - 10:30AM
12 | Create Contract - Contract Draft - Lines Tab - Special | 8909 | 11574 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | Assigned Agency | Cindy Lee | cilee@idoc.idaho.gov |  | PR-040-010 | 2022-02-01 | 8:45 - 10:30AM
13 | Create Contract - Contract Draft - Contacts Tab | 3335 | 11575 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | Assigned Agency | Cindy Lee | cilee@idoc.idaho.gov |  | PR-040-010 | 2022-02-01 | 8:45 - 10:30AM
14 | Create Contract - Contract Draft - Releasing a Contract | 7203 | 11576 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | Assigned Agency | Cindy Lee | cilee@idoc.idaho.gov |  | PR-040-010 | 2022-02-01 | 8:45 - 10:30AM
16 | Contract Approval | 8353 | 11578 | Approver | Approve transactions such as requisitions, purchase orders, solicitation & journal entries. | Assigned Agency | Cindy Lee | cilee@idoc.idaho.gvo | Approve/Deny/Reject | PR-040-010 | 2022-02-01 | 10:30-11AM
15 | Create Contract - Contract Draft - Activating a Contract | 7202 | 11577 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | Assigned Agency | Cindy Lee | cilee@idoc.idaho.gov |  | PR-040-010 | 2022-02-01 | 8:45 - 10:30AM
17 | Create Fixed Asset Requisition | 3041 | 11579 | Requester | Determines requirements & cost estimates for purchase of goods & services. Submits purchase requisition. | Assigned Agency | Jenna Marshall | jenmarsh@idoc.idaho.gov |  | PR-010-060 | 2022-02-01 | 1-1:30PM
18 | Approve Requisition | 8539 | 11580 | Approver | Approve transactions such as requisitions, purchase orders, solicitations, and journal entries. | Assigned Agency | Jenna Marshall | janmarsh@idoc.idaho.gov |  | PR-020-020 | 2022-02-01 | 1:30-2PM
19 | Create Purchase Order | 2753 | 11581 | Buyer | Review requisition and create purchase orders. Conduct market research, and monitor vendor commitments. Approve vendor returns. | Assigned Agency | David Brooks | dbrooks@idoc.idaho.gov |  | PR-050-040 | 2022-02-01 | 2-2:30PM
20 | Receive Purchase Order | 2178 | 11582 | Receiver | Receive and inspect incoming goods. Pick items for shipment/transfer. Dispose of items. Conduct vendor returns. Document variances. | Assigned Agency | Jenna Marshall | jenmarsh@idoc.idaho.gov | Receive less/more than ordered | PR-050-070 | 2022-02-01 | 2:30-3PM
21 | Inspect Item | 2181 | 11583 | Receiver | Receive and inspect incoming goods. Pick items for shipment/transfer. Dispose of items. Conduct vendor returns. Document variances. | Assigned Agency | Jenna Marshall | jenmarsh@idoc.idaho.gov | Inspection Failed, Vendor Return | PR-050-070 | 2022-02-01 | 3-3:30PM
22 | Create Invoice | 11447 | 11584 | Payables Invoice Processor | Process interface and XM files. Match payables invoices, and vendor list. Process payables payments. Generate 1099. | Assigned Agency | Lisa Starks | lstarks@idoc.idaho.gov |  | MF-070-050 Enter a PO Invoice | 2022-02-02 | 8:45-9:30 AM
23 | Approve Invoice | 11448 | 11585 | Approver | Approve transactions such as requisitions, purchase orders, solicitations, and journal entries. | Assigned Agency | Sharlett Laufenberg | slaufenb@idoc.idaho.gov |  | MF-070-056 Invoice Approval Process | 2022-02-02 | 9:30-10AM
24 | Match Invoice | 11455 | 11586 | Payables Manager | Void & cancel payments. Reissue & mail warrants. Process period close. | Assigned Agency | Mathel Castleton | mcastlet@idoc.idaho.gov |  | MF-070-070 Match Invoices | 2022-02-02 | 10-10:30AM
25 | Process Payment for Invoice | 11442 | 11587 | Payables Manager | Void & cancel payments. Reissue & mail warrants. Process period close. | Assigned Agency | Mathel Castleton | mcastlet@idoc.idaho.gov |  | MF-070-100 Process Invoice Payments | 2022-02-02 | 10:30-11AM
26 | Interface AP Asset to Asset Management | 2713 | 11900 | Asset Analyst | Create, add, transfer, adjust, retire, or dispose of assets, including privileges to run depreciation. | Assigned Agency | Tami Nick | tnick@idoc.idaho.gov |  | MF-040-030-010 | 2022-02-02 | 1-1:30PM
27 | Run Release Assets - Update | 8524 | 11905 | Asset Analyst | Create, add, transfer, adjust, retire, or dispose of assets, including privileges to run depreciation. | Assigned Agency | Tami Nick | tnick@idoc.idaho.gov | Associate with project | MF-040-030-020 | 2022-02-02 | 1:30-2PM
28 | Run Depreciation | 8522 | 11904 | Asset Manager | Manage the process to tract fixed asset activity: create, transfer, and retire fixed assets. | Assigned Agency | Sharlett Laufenberg | slaufenb@idoc.idaho.gov |  | MF-040-070-020 | 2022-02-02 | 2-2:30PM
29 | Review Fixed Asset GL Account Transactions |  |  | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate, and update allocations. | Assigned Agency | Mathel Castleton | mcastlet@idoc.idaho.gov |  | MF-020-010 | 2022-02-02 | 2:30-3PM
30 | Asset Surplus Disposal | 11062 | 11902 | Asset Analyst | Create, add, transfer, adjust, retire, or dispose of assets, including privileges to run depreciation. | Assigned Agency | Tami Nick | tnick@idoc.idaho.gov | Transfer, retire | MF-040-060-020 | 2022-02-02 | 3-3:30PM
31 | Approve Disposal | 11263 | 11903 | Asset Manager | Manage the process to tract fixed asset activity: create, transfer, and retire fixed assets. | Assigned Agency | Sharlett Laufenberg | slaufenb@idoc.idaho.gov | Transfer | MF-040-060-020 | 2022-02-02 | 3:30-4PM
32 | Close Contract | 2636 | 11901 | Contract Manager | Compile contract file, including entering contract line-item details, terms & conditions, and pricing, and amends and renews contracts. | Assigned Agency | Cindy Lee | cilee@idoc.idaho.gov |  | PR-050-030 | 2022-02-03 | 8:45-9:30 AM
Note on J5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard

## Statewide Contract Procure to P
SIT 3 Scenario - Statewide Contract Procure to Pay
Agency:
SIT 3 Week - Week 5 - 1/31-2/4
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Create Contract with Rebate and Price Breaks Statewide for Envelopes - Create a Contract (Contract Tab) | 7219 | 11992 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-020 | 2022-01-31 | 8:45 - 11 AM
2 | Create Contract with Rebate and Price Breaks Statewide for Envelopes - Contract Draft (Articles) | 7204 | 11987 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-020 | 2022-01-31 | 8:45 - 11 AM
3 | Create Contract with Rebate and Price Breaks Statewide for Envelopes - Contract Draft - Participants | 2667 | 11997 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-020 | 2022-01-31 | 8:45 - 11 AM
4 | Create Contract with Rebate and Price Breaks Statewide for Envelopes - Contract Draft - Lines - Special | 8909 | 11995 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-020 | 2022-01-31 | 8:45 - 11 AM
5 | Create Contract with Rebate and Price Breaks Statewide for Envelopes - Contract Draft - Lines - Purchase Type Detail - Purchase Pricing | 2663 | 11996 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-020 | 2022-01-31 | 8:45 - 11 AM
6 | Create Contract with Rebate and Price Breaks Statewide for Envelopes - Contract Draft - Rebates | 2671 | 11998 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-020 | 2022-01-31 | 8:45 - 11 AM
7 | Create Contract with Rebate and Price Breaks Statewide for Envelopes - Contract Draft - Contacts | 3335 | 11993 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-020 | 2022-01-31 | 8:45 - 11 AM
8 | Create Contract with Rebate and Price Breaks Statewide for Envelopes - Releasing a Contract | 7203 | 11985 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-020 | 2022-01-31 | 8:45 - 11 AM
10 | Contract Approval | 8353 | 11979 | Approver | Approve transactions such as requisitions, purchase orders, solicitation & journal entries. | DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-020 | 2022-01-31 | 1 - 1:30 PM
9 | Create Contract with Rebate and Price Breaks Statewide for Envelopes - Activating a Contract | 7202 | 11978 | Contract Manager | Compile contract file including entering contract line item details, terms & conditions along with pricing. | DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-040-020 | 2022-01-31 | 8:45 - 11 AM
11 | Requisition - RSS | 8325 | 11988 | Requester | Determines requirements & cost estimates for purchase of goods & services. Submits purchase requisition. | Assigned Agency | Jenna Marshall | jenmarsh@idoc.idaho.gov | distribution to multiple org unit and agencies | PR-020-010 | 2022-01-31 | 1:30 - 2:30 PM
12 | Approve Requisition | 8539 | 11984 | Approver | Approve transactions such as requisitions, purchase orders, solicitation & journal entries. | Assigned Agency | Jenna Marshall | janmarsh@idoc.idaho.gov |  | PR-020-010 | 2022-01-31 | 2:30 - 3 PM
13 | Create PO from Requisition | 8327 | 11991 | Buyer | Review requisitions & create purchase orders. Conduct market research & monitor vendor commitments. Approve vendor returns. | Assigned Agency | David Brooks | dbrooks@idoc.idaho.gov |  | PR-050-040 | 2022-02-01 | 8:45-9:30 AM
14 | Receive Purchase Order | 3064 | 11977 | Receiver | Receive and inspect incoming goods. Pick items for shipment/transfer. Dispose of items. Vendor returns. Document variances. | Assigned Agency | Jenna Marshall | jenmarsh@idoc.idaho.gov |  | PR-050-070 | 2022-02-01 | 9:30-10AM
15 | Create Invoice | 11606 | 11983 | Payables Invoice Processor | Process interface and XM files. Match payables invoices, and vendor list. Process payables payments. Generate 1099. | Assigned Agency | Lisa Starks | lstarks@idoc.idaho.gov |  | MF-070-050 Enter a PO Invoice | 2022-02-01 | 10-11AM
16 | Notify Buyer of Discrepancy | 11605 | 11982 | Payables Invoice Processor | Process interface and XM files. Match payables invoices, and vendor list. Process payables payments. Generate 1099. |  | Lisa Starks | lstarks@idoc.idaho.gov |  | MF-070-050 Enter a PO Invoice | 2022-02-01 | 1-1:30PM
17 | Resolve Cost Discrepancy | New | 12004 | Buyer | Review requisition and create purchase orders. Conduct market research, and monitor vendor commitments. Approve vendor returns. | Assigned Agency | David Brooks | dbrooks@idoc.idaho.gov |  |  | 2022-02-01 | 1:30-2PM
18 | Submit Resolved Invoice for Approval | 11607 | 11989 | Payables Invoice Processor | Process interface and XM files. Match payables invoices, and vendor list. Process payables payments. Generate 1099. |  | Lisa Starks | lstarks@idoc.idaho.gov |  | MF-070-050 Enter a PO Invoice | 2022-02-01 | 2-2:30PM
19 | Approve Invoice | 11608 | 11990 | Approver | Approve transactions such as requisitions, purchase orders, solicitations, and journal entries. | Assigned Agency | Sharlett Laufenberg | slaufenb@idoc.idaho.gov |  | MF-070-056 Invoice Approval Process | 2022-02-01 | 2:30-3PM
20 | Match Invoice | 11609 | 11994 | Payables Manager | Void & cancel payments. Reissue & mail warrants. Process period close. | Assigned Agency | Mathel Castleton | mcastlet@idoc.idaho.gov |  | MF-070-070 Match Invoices | 2022-02-01 | 3-3:30PM
21 | Process Payment for Invoice | 11442 | 11981 | Payables Manager | Void & cancel payments. Reissue & mail warrants. Process period close. | Assigned Agency | Mathel Castleton | mcastlet@idoc.idaho.gov |  | MF-070-100 Process Invoice Payments | 2022-02-01 | 3-3:30PM
22 | Journalize | 11440 | 11980 | Payables Manager | Void & cancel payments. Reissue & mail warrants. Process period close. |  | Mathel Castleton | mcastlet@idoc.idaho.gov |  | MF-070-110 Journalize AP Distributions | 2022-02-01 | 3-3:30PM
23 | Renew/Addendum Statewide Contract | 2773 | 11986 | Contract Manager | Compile contract file, including entering contract line-item details, terms & conditions, and pricing, and amends and renews contracts. | DOP | DOP Tester | contractadmin@adm.idaho.gov |  | PR-050-010 | 2022-02-02 | 8:45-9:30 AM
24 | Load Rebate Invoices | New | 11999 | Supply Management Admin or Processor |  | Assigned Agency |  |  |  | PR-050-010 | 2022-02-02 | 9:30-10AM
25 | Calculate Rebate Amounts Due for a Contract | New | 12000 | Supply Management Admin or Processor | [5 empty] | PR-050-010 | 2022-02-02 | 10-11AM
26 | Review Rebate Due Information | New | 12001 | Contract Manager | Compile contract file, including entering contract line-item details, terms & conditions, and pricing, and amends and renews contracts. | Assigned Agency | DOP Tester | contractadmin@adm.idaho.gov |  | PR-050-010 | 2022-02-02 | 1-1:30PM
27 | Apply Rebate (Enter a Rebate Invoice in Payables | New | 12002 | Payables Manager | Void & cancel payments. Reissue & mail warrants. Process period close. |  | Lynn Christian | lynn.christian@adm.idaho.gov | There isn't an invoice type of Rebate Invoice???? | MF-260-070ZZ | 2022-02-03 | 8:45-9:30 AM
28 | Review Rebate Information | New | 12003 | Contract Manager | Compile contract file, including entering contract line-item details, terms & conditions, and pricing, and amends and renews contracts. |  | DOP Tester | contractadmin@adm.idaho.gov |  | PR-050-010 | 2022-02-03 | 9:30-10AM
29 | Verify Rebates posted in Cash Account |  |  | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Genny Casiano | genny.casiano@adm.idaho.gov |  | MF-260-070ZZ | 2022-02-03 | 10-11 AM
Note on J5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard

## Cash Ledger Payment
SIT 3 Scenario - Cash Ledger Payment
Agency:
SIT Week - Week 7 - 2/14 -2/18
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Enter Cash Payment | Cash Payment Entry.xlsx | 12075 | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Jami Haan | jhaan@idoc.idaho.gov | Rotary/Site Draft, L Warrants |  | 2022-02-14 | 8:45 - 10 AM
1A | Record Cash Payment |  | 12525 | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Jami Haan | jhaan@idoc.idaho.gov |  |  | 2022-02-14 | 8:45 - 10 AM
2 | Approve Cash Payment | Cash Approve Cash Payment.xlsx | 12076 | Cash Manager | Manage all cash transactions. Review and update cash management policy as needed. | Assigned Agency | Sharlett Laufenberg | slaufenb@idoc.idaho.gov |  |  | 2022-02-14 | 10 - 11:30 AM
3 | Cash Requirements | Cash Requirements.xlsx | 12077 | Payables Payment Processor | Perform Cash Requirements, Schedule Payments, Complete Payment Cycle | Assigned Agency | Sharlett Laufenberg | slaufenb@idoc.idaho.gov |  | MF-070-100 Process Invoice Payments | 2022-02-14 | 1 - 2:30 PM
4 | Review Check in Cash | Cash Review Check in Cash Management.xlsx | 12078 | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Jami Haan | jhaan@idoc.idaho.gov | Redeem or Void then Review again |  | 2022-02-14 | 2:30 - 4 PM
5 | Journalize Distributions | Cash Journalize Cash Transaction.xlsx | 12079 | Cash Manager | Manage all cash transactions. Review and update cash management policy as needed. | Assigned Agency | Sharlett Laufenberg | slaufenb@idoc.idaho.gov |  |  | 2022-02-15 | 8:45 - 10 AM
6 | Verify Results in Global Ledger Account Analysis |  | 12082 | Staff Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Addy Matamoros | amatamor@idoc.idaho.gov |  |  | 2022-02-15 | 10 - 11:30 AM
7 | Optional Void Cash Payment for Status Updates | Cash Void Cash Payment.xlsx | 12080 | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Jami Haan | jhaan@idoc.idaho.gov |  |  | 2022-02-15 | 1 - 2:30 PM
8 | Optional Void Cash Payment: Payment Void Stop Pay Update | 12161 | 12161 | Payables Payment Processor | Perform Cash Requirements, Schedule Payments, Complete Payment Cycle | Assigned Agency | Sharlett Laufenberg | slaufenb@idoc.idaho.gov |  |  | 2022-02-15 | 1 - 2:30 PM
9 | Optional Redeem Warrant for Status Updates | Cash Redeem Warrant.xlsx | 12081 | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Jami Haan | jhaan@idoc.idaho.gov |  |  | 2022-02-15 | 2:30 - 4 PM
Note on I4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard
Note on K5: Glenda Smith: Cash BPR's are not correct, do not reference.

## Procure to Pay Vendor Mgt Voids
SIT 3 Scenario - Procure to Pay with Void and Vendor Update
Agency:
SIT Week - Week 7 - 2/14 -2/18
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | Luma Role (role switcher) | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Create Requisition - Special | 8324 | Requester | Assigned Agency | Jenna Marshall | jenmarsh@idoc.idaho.gov |  | PR-020-010 | 2022-02-14 | 8:45-9:30 AM
2 | Approve Requisition | 8539 | Approver | Assigned Agency | Jenna Marshall | janmarsh@idoc.idaho.gov | Requisition not approved | PR-010-060 | 2022-02-14 | 9:30-10AM
3 | Create Purchase Order | 8170 | Buyer | Assigned Agency | David Brooks | dbrooks@idoc.idaho.gov |  | PR-050-040 | 2022-02-14 | 10-10:30 AM
4 | Receive Purchase Order | 4587 | Receiver | Assigned Agency | Jenna Marshall | jenmarsh@idoc.idaho.gov |  | PR-050-070 | 2022-02-14 | 10:30 - 11 AM
5 | Create Invoice | 11519 | Payables Invoice Processor | Assigned Agency | Lisa Starks | lstarks@idoc.idaho.gov |  | MF-070-050 Enter a PO Invoice | 2022-02-14 | 1-1:30PM
6 | Approve Invoice | 11520 | Approver | Assigned Agency | Sharlett Laufenberg | slaufenb@idoc.idaho.gov |  | MF-070-056 Invoice Approval Process | 2022-02-14 | 1:30-2PM
7 | Match Invoice | 11458 | Payables Manager | Assigned Agency | Sharlett Laufenberg | slaufenb@idoc.idaho.gov |  | MF-070-070 Match Invoices | 2022-02-14 | 2-2:30PM
8 | Process Payment for Invoice | 11442 | Payables Manager | Assigned Agency | Sharlett Laufenberg | slaufenb@idoc.idaho.gov |  | MF-070-100 Process Invoice Payments | 2022-02-14 | 2:30-3PM
9 | Journalize | 11440 | Payables Manager |  | Sharlett Laufenberg | slaufenb@idoc.idaho.gov |  | MF-070-110 Journalize AP Distributions | 2022-02-14 | 3 - 3:30 PM
10 | Void Payment | 12080 | Cash Accountant | SCO | Jami Haan | jhaan@idoc.idaho.gov |  | MF-200-060 Void Cash Transactions | 2022-02-14 | 3:30 - 4 PM
11 | Cancel Invoice | 11523 | Payables Manager | Assigned Agency | Sharlett Laufenberg | slaufenb@idoc.idaho.gov |  | MF-070-050 Enter a PO Invoice | 2022-02-15 | 8:45-9:30 AM
12 | Request a new vendor | 11524 | Payables Invoice Processor | Assigned Agency | Lisa Starks | lstarks@idoc.idaho.gov |  | PR-040-030 Create and Maintain Vendor | 2022-02-15 | 9:30-10AM
13 | Approve and setup new vendor | 11525 - Only SCO staff can do this | Approver | SCO | Sharlett Laufenberg | slaufenb@idoc.idaho.gov | Disapprove vendor | PR-040-030 Create and Maintain Vendor | 2022-02-15 | 10-10:30 AM
14 | Create Invoice | 11519 | Payables Invoice Processor | Assigned Agency | Lisa Starks | lstarks@idoc.idaho.gov |  | MF-070-050 Enter a PO Invoice | 2022-02-15 | 10:30 - 11 AM
15 | Approve Invoice | 11520 | Approver | Assigned Agency | Sharlett Laufenberg | slaufenb@idoc.idaho.gov |  | MF-070-056 Invoice Approval Process | 2022-02-15 | 1-1:30PM
16 | Match Invoice | 11522 | Payables Invoice Processor | Assigned Agency | Lisa Starks | lstarks@idoc.idaho.gov |  | MF-070-070 Match Invoices | 2022-02-15 | 1:30-2PM
17 | Process Payment for Invoice | 11442 | Payables Manager | Assigned Agency | Sharlett Laufenberg | slaufenb@idoc.idaho.gov |  | MF-070-100 Process Invoice Payments | 2022-02-15 | 2-2:30PM
18 | Post Transactions - Journalize | 11440 | Payables Manager | Assigned Agency | Sharlett Laufenberg | slaufenb@idoc.idaho.gov |  | MF-070-110 Journalize AP Distributions | 2022-02-15 | 2:30-3PM
19 | Cash Ledger Journalize | 12079 | Cash Manager | Assigned Agency | Sharlett Laufenberg | Sharlett Laufenberg |  | MF-200-050 Reconcile Payments Payables and Disbursements | 2022-02-15 | 3 - 3:30 PM
20 | Verify Voided Payables Checks | 12153 | Cash Accountant | Assigned Agency | Jami Haan | jhaan@idoc.idaho.gov |  | MF-200-060 Void Cash Transactions | 2022-02-15 | 3:30 - 4 PM
21 | View Fund Balance | Cash Fund Balance.xlsx (in ALM?)(in Cash Deposit to Revenue Scenario) | Cash Accountant | Assigned Agency | Jami Haan | jhaan@idoc.idaho.gov |  | MF-200-050 Reconcile Payments Payables and Disbursements | 2022-02-16 | 8:45-9:30 AM
22 | Comparative report from Birst |  | Cash Accountant | Assigned Agency | Jami Haan | jhaan@idoc.idaho.gov |  | MF-200-ZZ | 2022-02-16 | 9:30-10AM
23 | Cash Revenue Daily Report - Birst |  | Cash Manager | Assigned Agency | Addy Matamoros | amatamor@idoc.idaho.gov |  | MF-200-ZZ | 2022-02-16 | 10-10:30 AM
Note on H5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard

## Vendor Refund
SIT 3 Scenario - Vendor Refund
Agency:
SIT 3 Week - Week 7 - 2/14 - 2/18
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Invoice Entry - Non-PO | 12444 | 12444 | Payables Invoice Processor |  |  | Lisa Starks | lstarks@idoc.idaho.gov |  | MF-070-060 Enter Non-PO Invoice | 2022-02-15 | 8:45-9:30 AM
2 | Invoice Approver | 12445 | 12445 | Approver |  |  | Sharlett Laufenberg | slaufenb@idoc.idaho.gov |  | MF-070-056 Invoice Approval Process | 2022-02-15 | 9:30-10AM
3 | Cash Requirements | 12442 | 12442 | Payables Manager |  |  | Sharlett Laufenberg | slaufenb@idoc.idaho.gov |  | MF-070-100 Process Invoice Payments | 2022-02-15 | 10-10:30 AM
4 | Journalize | 12443 | 12443 | Payables Manager |  |  | Sharlett Laufenberg | slaufenb@idoc.idaho.gov |  | MF-070-110 Journalize AP Distributions | 2022-02-15 | 10:30 - 11 AM
5 | Create Cash Receipts |  | TBD | Cash Accountant |  |  | Jami Haan | jhaan@idoc.idaho.gov |  |  | 2022-02-15 | 1-1:30PM
6 | Approve Cash Receipt |  | TBD | Approver |  |  | Addy Matamoros | amatamor@idoc.idaho.gov |  |  | 2022-02-15 | 1:30-2PM
7 | Cash Receipt Final Release |  | TBD | Cash Manager |  |  | Sharlett Laufenberg | slaufenb@idoc.idaho.gov |  |  | 2022-02-15 | 2-2:30PM
8 | Jornalize Cash Transactions |  | TBD | Staff Accountant |  |  | Addy Matamoros | amatamor@idoc.idaho.gov |  |  | 2022-02-15 | 2:30-3PM
9 | Post GL Journals |  | TBD | Staff Accountant |  |  | Addy Matamoros | amatamor@idoc.idaho.gov |  |  | 2022-02-15 | 3 - 3:30 PM
10 | Adjust Reportable Income | 11837 | 12047 | Payables Manager | Void & cancel payments. Reissue & mail warrants. Process period close. | Assigned Agency | Sharlett Laufenberg | slaufenb@idoc.idaho.gov |  | MF-070-020 Maintain Invoice | 2022-02-15 | 3:30 - 4 PM
Note on J5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard

## Cash Managem Deposit to Revenue
SIT 3 Scenario - Deposit to Revenue
Agency:
SIT Week - Week 8 - 2/21/ - 2/25
Sequence | Script ID | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 BPR PROCESSES | Execution date | Window to Complete Script
1 | Cash Fund Balance - Before Processing Transactions | TBD | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Jami Haan | jhaan@idoc.idaho.gov |  |  | 2022-02-22 | 8:45-9:30 AM
2 | Create Cash Receipt | TBD | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Jami Haan | jhaan@idoc.idaho.gov |  |  | 2022-02-22 | 9:30-10AM
3 | Approve Cash Receipt (Approve Cash Transactions in InBasket) | TBD | Cash Manager | Manage all cash transactions. Review and update cash management policy as needed. | Assigned Agency | Mathel Castleton | mcastlet@idoc.idaho.gov |  |  | 2022-02-22 | 10-11AM
4 | Cash Receipt Final Release (Approve Cash Transactions in InBasket) | TBD | Cash Manager | Manage all cash transactions. Review and update cash management policy as needed. | 150 | Mathel Castleton | mcastlet@idoc.idaho.gov |  |  | 2022-02-22 | 1-1:30PM
5 | Process NSF | TBD | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Jami Haan | jhaan@idoc.idaho.gov |  |  | 2022-02-22 | 1:30-2PM
6 | Approve NSF (Approve Cash Transactions in InBasket) | TBD | Cash Manager | Manage all cash transactions. Review and update cash management policy as needed. | Assigned Agency | Mathel Castleton | mcastlet@idoc.idaho.gov |  |  | 2022-02-22 | 2-2:30PM
7 | NSF Final Release (Approve Cash Transactions in InBasket) | TBD | Cash Manager | Manage all cash transactions. Review and update cash management policy as needed. | 150 | Mathel Castleton | mcastlet@idoc.idaho.gov |  |  | 2022-02-22 | 2:30-3PM
8 | Reclass From Suspense: No Customer (Cash Receipt Transfer) | TBD | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Jami Haan | jhaan@idoc.idaho.gov |  |  | 2022-02-22 | 3-3:30PM
9 | Reclass From Suspense Customer (Go to AR Scenario) | TBD | Receivables Specialist | Process Accounts Receivable payments, collection letters, and related late fees. Journalize entries. | Assigned Agency | Jami Haan | jhaan@idoc.idaho.gov | Process under development. |  | 2022-02-23 | 8:45-9:30 AM
10 | Operating Transfer (Cash Ledger Transaction Transfer) | TBD | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Jami Haan | jhaan@idoc.idaho.gov |  |  | 2022-02-23 | 9:30-10AM
11 | Statutory Transfer (Cash Ledger Transaction Transfer) | TBD | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Jami Haan | jhaan@idoc.idaho.gov |  |  | 2022-02-23 | 10-11AM
12 | Approve Cash Transfer (Approve Cash Transactions in InBasket) | TBD | Cash Manager | Manage all cash transactions. Review and update cash management policy as needed. | Assigned Agency | Mathel Castleton | mcastlet@idoc.idaho.gov |  |  | 2022-02-23 | 1-1:30PM
13 | Cash Fund Balance - After Processing Transactions | TBD | Cash Manager | Manage all cash transactions. Review and update cash management policy as needed. | Assigned Agency | Mathel Castleton | mcastlet@idoc.idaho.gov |  |  | 2022-02-23 | 1:30-2PM
14 | Journalize Cash Transactions | TBD | Cash Manager | Manage all cash transactions. Review and update cash management policy as needed. | Assigned Agency | Mathel Castleton | mcastlet@idoc.idaho.gov |  |  | 2022-02-23 | 2-2:30PM
15 | Post GL Journals | TBD | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate, and update allocations. | Assigned Agency | Mathel Castleton | mcastlet@idoc.idaho.gov | Check for autopost |  | 2022-02-23 | 2:30-3PM
16 | Review Global Ledger for Transactions Processed | TBD | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate, and update allocations. | Assigned Agency | Mathel Castleton | mcastlet@idoc.idaho.gov |  |  | 2022-02-23 | 3-3:30PM
Note on I5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard

## Custodial Account Set Up
SIT 3 Scenario - Custodial Account Set Up
Agency:
SIT Week - Week 8 - 2/21/ - 2/25
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Custodial Account Setup | TBD | 12071 | Custodial Account Manager | Monitor financial structure and Chart of Account dimensions for their Agency and recommendations for updates. Manage all financial processes. | Assigned Agency | Lisa Johnson | lisjohns@idoc.idaho.gov |  |  | 2022-02-22 | 8:45 - 10AM
2 | CAM Structure Setup | Refer to Upload Template | 12072 | Custodial Account Manager | 0 | Assigned Agency | Lisa Johnson | lisjohns@idoc.idaho.gov |  |  | 2022-02-22 | 10 - 11:30 AM
3 | Custodial Account Hierarchy Setup | Refer to Upload Template | 12073 | Custodial Account Manager | Monitor financial structure and Chart of Account dimensions for their Agency and recommendations for updates. Manage all financial processes. | Assigned Agency | Lisa Johnson | lisjohns@idoc.idaho.gov |  |  | 2022-02-22 | 1 - 2:30 PM
4 | Custodial Account Record Setup | Refer to Upload Template | 12074 | Custodial Account Manager | 0 | Assigned Agency | Lisa Johnson | lisjohns@idoc.idaho.gov |  |  | 2022-02-22 | 2:30 -4 PM
Note on J5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard

## Punchout Request to Payment
SIT 3 Scenario - Punchout Request to Payment
Agency:
SIT Week - Week 8 - 2/21 - 2/25
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Create Punchout Requisition using RSS | 3501 | 11924 | Requester | Determines requirements & cost estimates for purchase of goods & services. Submits purchase requisition. | Assigned Agency | Jenna Marshall | jenmarsh@idoc.idaho.gov |  | PR-020-010 | 2022-02-22 | 8:45-9:30 AM
2 | Approve Requisition | 8539 | 11925 | Approver | Approve transactions such as requisitions, purchase orders, solicitation & journal entries. | Assigned Agency | Jenna Marshall | janmarsh@idoc.idaho.gov | Deny Requisition - add note - need more information Approve Requisition | PR-010-060 | 2022-02-22 | 9:30-10AM
3 | Locate Punchout PO | Refer to Upload template | 12034 | Requester |  |  | Jenna Marshall | jenmarsh@idoc.idaho.gov |  | PR-050-040 | 2022-02-22 | 10-11AM
4 | Review Punchout PO | Refer to Upload template | 11927 | Buyer | Review requisitions & create purchase orders. Conduct market research & monitor vendor commitments. Approve vendor returns. | Assigned Agency | David Brooks | dbrooks@idoc.idaho.gov | This will be a review of schedule job creating PO. Other variations would be manual creation, or Job run creation submitted as needed. | PR-050-040 | 2022-02-22 | 1-1:30PM
5 | Review Punchout Receipt | Refer to Upload template | 11928 | Receiver | Receive and inspect incoming goods. Pick items for shipment/transfer. Dispose of items. Vendor returns. Document variances. | Assigned Agency | Jenna Marshall | jenmarsh@idoc.idaho.gov | Manual release of receipt vs. auto release | PR-050-070 | 2022-02-22 | 1:30-2PM
6 | Review Punchout Invoice | 11610 | 11922 | Payables Invoice Processor | Processes interface and XM files. Match Payables invoices. Manages vendor list. Processes Payables payments. Generates 1099. | Assigned Agency | Lisa Starks | lstarks@idoc.idaho.gov |  | MF-070-050 Enter a PO Invoice | 2022-02-22 | 2-2:30PM
7 | Approve Invoice | 11611 | 11923 | Approver |  |  | Sharlett Laufenberg | slaufenb@idoc.idaho.gov |  | MF-070-056 Invoice Approval Process | 2022-02-22 | 2:30-3PM
8 | Match Invoice | 11613 | 11926 | Payables Manager | Void & cancel payments, reissue & mail warrants. Process period close. | Assigned Agency | Mathel Castleton | mcastlet@idoc.idaho.gov |  | MF-070-070 Match Invoices | 2022-02-22 | 3-3:30PM
9 | Process Invoice for Payment | 11442 | 11921 | Payables Manager | Void & cancel payments, reissue & mail warrants. Process period close. | Assigned Agency | Mathel Castleton | mcastlet@idoc.idaho.gov |  | MF-070-100 Process Invoice Payments | 2022-02-22 | 3:30 - 4 PM
Note on J5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard

## Custodial Accounts
SIT 3 Scenario - Budget Reporting and Trust Accounting
Agency:
SIT 3 Week - Week 9 - 2/28 - 3/4
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Set up Custodial Accounts |  | TBD | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate, and update allocations. | Assigned Agency | Mathel Castleton | mcastlet@idoc.idaho.gov | Associate with project | PR-050-070 | 2022-02-28 | 8:45-9:30 AM
2 | Enter cash receipt for the Custodial Account |  | TBD | Cash Accountant | Post and reconcile cash transactions, including refunds, non-vendor payments, and stale-dated/escheated transactions. | Assigned Agency | Jami Haan | jhaan@idoc.idaho.gov | Deny Requisition - add note - need more information Approve Requisition | MF-260-070 Enter Cash Receipts | 2022-02-28 | 9:30-10AM
2 | Approve Cash Receipt |  | TBD | Cash Manager | Manage all cash transactions. Review and update cash management policy as needed. | Assigned Agency | Mathel Castleton | mcastlet@idoc.idaho.gov |  | MF-260-070 Enter Cash Receipts | 2022-02-28 | 10-11AM
3 | Final Approval of Cash Receipt |  | TBD | Cash Manager | Manage all cash transactions. Review and update cash management policy as needed. | STO | Mathel Castleton | mcastlet@idoc.idaho.gov |  | MF-260-070 Enter Cash Receipts | 2022-02-28 | 1-1:30PM
4 | Journalize Cash Management |  | TBD | Cash Manager | Manage all cash transactions. Review and update cash management policy as needed. | Assigned Agency | Mathel Castleton | mcastlet@idoc.idaho.gov |  | MF-260-090 Post to General Ledger | 2022-02-28 | 1:30-2PM
5 | View Trust Balance report in Birst |  | TBD | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate, and update allocations. | Assigned Agency | Mathel Castleton | mcastlet@idoc.idaho.gov |  |  | 2022-02-28 | 2-2:30PM
6 | Enter Invoice for trust account | 11443 | TBD | Payables Invoice Processor | Process interface and XM files. Match payables invoices, and vendor list. Process payables payments. Generate 1099. | Assigned Agency | Lisa Starks | lstarks@idoc.idaho.gov |  | MF-070-060 Enter a Non-PO invoice | 2022-02-28 | 2:30-3PM
7 | Enter Comments & Attachments | 11445 | TBD | Payables Invoice Processor |  |  | Lisa Starks | lstarks@idoc.idaho.gov |  | MF-070-060 Enter a Non-PO invoice | 2022-02-28 | 3-3:30PM
8 | Approve invoice | 11444 | TBD | Approver | Approve transactions such as requisitions, purchase orders, solicitations, and journal entries. | Assigned Agency | Sharlett Laufenberg | slaufenb@idoc.idaho.gov |  | MF-070-080 Invoice Approval Process | 2022-03-02 | 8:45-9:30 AM
9 | Run Cash Requirements | 11442 | TBD | Payables Manager | Void & cancel payments. Reissue & mail warrants. Process period close. | Assigned Agency | Mathel Castleton | mcastlet@idoc.idaho.gov |  | MF-070-100 Process Invoice Payments | 2022-03-02 | 9:30-10AM
10 | Journalize Payables | 11440 | TBD | Payables Manager | Void & cancel payments. Reissue & mail warrants. Process period close. | Assigned Agency | Mathel Castleton | mcastlet@idoc.idaho.gov |  | MF-070-110 Journalize Distributions | 2022-03-02 | 10-11AM
11 | View Trust Balance Report in Birst |  | TBD | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate, and update allocations. | Assigned Agency | Mathel Castleton | mcastlet@idoc.idaho.gov | Receive less/more than ordered |  | 2022-03-02 | 1-1:30PM
12 | Run Average Daily Balance Report |  | TBD | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate, and update allocations. | Assigned Agency | Mathel Castleton | mcastlet@idoc.idaho.gov | Inspection Failed, Vendor Return |  | 2022-03-02 | 1:30-2PM
Note on J5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard

## Global Ledger Entries and Analy
SIT 3 Scenario - Global Legder Processing and Analysis
Agency:
SIT Week - Week 8 - 2/21/ - 2/25
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | Create a Front-End Split Journal Entry (Front End Split Projects Only) | Refer to Upload Template | 12154 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Mathel Castleton | mcastlet@idoc.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-010 | 2022-02-23 | 8:45-9:30 AM
2 | Create a Journal Entry | Refer to Upload Template | 11668 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Mathel Castleton | mcastlet@idoc.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-010 | 2022-02-23 | 9:30-10AM
3 | Approve a Journal Entry | Refer to Upload Template | 11669 | Approver | Approve transactions such as requisitions, purchase orders, solicitation & journal entries. | Assigned Agency | Mathel Castleton | mcastlet@idoc.idaho.gov |  | MF-025-060 | 2022-02-23 | 10-11AM
4 | Create a Journal Entry from an Existing Journal | Refer to Upload Template | 11671 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Mathel Castleton | mcastlet@idoc.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-010 | 2022-02-23 | 1-1:30PM
5 | Create a Journal Entry from a Template | Refer to Upload Template | 11670 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Mathel Castleton | mcastlet@idoc.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-010 | 2022-02-23 | 1:30-2PM
6 | Create a Recurring Journal | Refer to Upload Template | 11673 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Mathel Castleton | mcastlet@idoc.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-020 | 2022-02-23 | 2-2:30PM
7 | Journalize a Recurring Journal Entry | Refer to Upload Template | 12155 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Mathel Castleton | mcastlet@idoc.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-030 | 2022-02-23 | 2:30-3PM
8 | Post Multiple Journal Entries | Refer to Upload Template | 12156 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Mathel Castleton | mcastlet@idoc.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-23 | 3-3:30PM
9 | Post Journals from Subsystems | Refer to Upload Template | 12157 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Mathel Castleton | mcastlet@idoc.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-050 | 2022-02-24 | 8:45-9:30 AM
10 | Validate (here) Reconcile (close) Subsystems to the General Ledger | Bill will put these scripts here and in close scenario | TBD | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Mathel Castleton | mcastlet@idoc.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-24 | 9:30-10AM
11 | Analyze Global Ledger Totals | Refer to Upload Template | 12158 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Mathel Castleton | mcastlet@idoc.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-24 | 10-11AM
12 | Perform Account Analysis | Refer to Upload Template | 11672 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Mathel Castleton | mcastlet@idoc.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-24 | 1-1:30PM
13 | Perform Fund Analysis | Refer to Upload Template | 12159 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Mathel Castleton | mcastlet@idoc.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-24 | 1:30-2PM
14 | Perform Organizational Unit Analysis | Refer to Upload Template | 12160 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Mathel Castleton | mcastlet@idoc.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-24 | 2-2:30PM
15 | View Transactions by Entity-Account | Refer to Upload Template | 11674 | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Mathel Castleton | mcastlet@idoc.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-25 | 9- 9:30 AM
16 | BIRST/BI/CSF Analytic Reporting |  | TBD | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Mathel Castleton | mcastlet@idoc.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-25 | 9:30 - 10 AM
17 | Evaluate Encumbrances | Placeholder - Judy and Bill (and Eileen/Cathy) are working on script for this; will have this week (12/23/21) | TBD | Staff Accountant |  | Assigned Agency | Mathel Castleton | mcastlet@idoc.idaho.gov | May also be performed by CFO or Controller (SCO) | MF-020-040 | 2022-02-25 | 10 - 11 AM
Note on J5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard

## Chart of Accounts Maintenance
SIT 3 Scenario - Chart of Accounts Maintenance
Agency:
SIT Week - Week 10 - 3/7 - 3/11
Sequence | Script ID | ALM Test ID # (view tab = "Tests" column A) | SIT 3 Test ID | Luma Role (role switcher) | Role Description | Agency | Tester Name | Tester Email Address/Username | Variations | L3 Process Name (BPRs) | Execution date | Window to Complete Script
1 | View and Validate an Organizational Unit |  | TBD | Staff Accountant |  |  | Mathel Castleton | mcastlet@idoc.idaho.gov |  |  | 2022-03-07 | 8:45-9:30 AM
2 | View and Validate a Project |  | TBD | Staff Accountant |  |  | Mathel Castleton | mcastlet@idoc.idaho.gov |  |  | 2022-03-07 | 9:30-10AM
3 | View and Validate a Program |  | TBD | Staff Accountant |  |  | Mathel Castleton | mcastlet@idoc.idaho.gov |  |  | 2022-03-07 | 10-11AM
4 | View and Validate a Location |  | TBD | Staff Accountant |  |  | Mathel Castleton | mcastlet@idoc.idaho.gov |  |  | 2022-03-07 | 1-1:30PM
5 | View and Validate Additional Reporting |  | TBD | Staff Accountant |  |  | Mathel Castleton | mcastlet@idoc.idaho.gov |  |  | 2022-03-07 | 1:30-2PM
6 | View and Validate Custodial Accounts (CAM) |  | TBD | Staff Accountant |  |  | Mathel Castleton | mcastlet@idoc.idaho.gov |  |  | 2022-03-07 | 2-2:30PM
7 | Request a new account |  | TBD | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Mathel Castleton | mcastlet@idoc.idaho.gov |  |  | 2022-03-07 | 2:30-3PM
8 | Request a new organizational unit |  | TBD | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. | Assigned Agency | Mathel Castleton | mcastlet@idoc.idaho.gov |  |  | 2022-03-07 | 3-3:30PM
9 | View and Validate Beginning Balances |  | TBD | Staff Accountant |  |  | Mathel Castleton | mcastlet@idoc.idaho.gov |  |  | 2022-03-08 | 8:45-9:30 AM
10 | Update Summary Conversion Balances to Detail |  | TBD | Staff Accountant | Post manual and interfaced journal entries. Prepare intra/inter agency journal entries. Define, calculate & update allocations. |  | Mathel Castleton | mcastlet@idoc.idaho.gov |  |  | 2022-03-08 | 9:30-10AM
Note on J5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each Employee has a unique State ID# found on the Enterprise Dashboard